Description and Procedure for RF Conditioning and High Power Tests of HINS RFQ

G. Romanov, J. Steimel, B. Webber, W. Tam

May 19, 2008

## Introduction and System Description

Personnel Safety

The commissioning of the RFQ involves the operation of the Toshiba E3740A 2.5 MW klystron at the Meson Detector Building (MDB) and certain LOTO procedures. Operators should follow the procedures documented in “HINS Klystron Operating Procedures” (Beams-doc-2616) and “325 MHz RF Power Distribution System LOTO” (Beams-doc-2710).

The RFQ vendor indicates that the steel vacuum vessel surrounding the RFQ provides sufficient x-ray attenuation such that no external x-ray hazard is expected. Based on this expectation, the RFQ will be installed in a location that is neither shielded nor interlocked. X-ray radiation levels due to operation of the RFQ must be checked during commissioning. Personnel from Accelerator Division ES&H Radiation Safety Group shall be present for x-ray inspection once the RFQ commissioning starts.

RF Power System

The high power RF system consists of a klystron, circulator, waveguide components, loads and couplers as shown in Figure 1.  RF power is supplied by a 325 MHz, 2.5 MW, Toshiba E3740A klystron. A 2.5 MW circulator protects the klystron from high reflected power. Reflected power is dissipated in a full power dummy load.

A high power vector modulator, ultimately part of the RF power transmission and control circuit, will be absent from the power circuit during the initial commissioning of the RFQ. The RF power line connects to a 4-port hybrid that splits the power into two, equal amplitude, 180 degree outputs that feed the two power coupler ports on the RFQ. The fourth (sum) port on the hybrid is terminated with a RF load.

Cooling System

The nominal LCW system water temperature varies about ±1.0( F. Without additional water temperature regulation, the average RFQ temperature and resonant frequency will vary accordingly. Differential cooling will be used as a means of resonance control. The RFQ water system is divided into two circuits: body and vane. The temperature sensitivity of resonant frequency for each water path shall be measured. Water temperature sensors are mounted near the inlet to each water circuit. In the vane circuit, a water heater is mounted upstream of the sensor and will be implemented as an element of a local inlet temperature regulation loop as needed.

Resonant frequency variation as a result of non-uniform temperature distribution from RF heating in the RFQ is difficult to simulate and predict. The resonant frequency sensitivity to RF power shall be measured as part of the RF power testing.  The cooling water temperature rise between inlet and outlet at the RFQ is estimated to be about 2.3 (F for a flow of 12 Gal/min at an average RF power loss of 4 kW (400 kW pulse at 1% duty cycle).

The nominal pressure of the water system is higher than the rated pressure of the RFQ cooling lines.  A pressure regulation circuit controls the water pressure flowing in the RFQ.  The regulation circuit consists of a pressure reducer, a solenoid activated flow stop, a pressure switch, and a relief valve.  The pressure reducer is designed to bring the water pressure to 40psi.  The pressure switch activates at 50psi and drives the solenoid flow stop.  If that fails, there is a final relief valve upstream of the RFQ that will redirect water at pressures over 50psi.  The system includes a water flow switch that will inhibit RF power if water is not flowing through the cavity cooling circuit.  It also includes a check valve on the return line in case the return pressure goes above 40psi.

Vacuum System

Three turbo pumps will be used to pump the RFQ vacuum. A base pressure of 5x10-7 Torr, before application of RF power, is acceptable for beginning power tests. The system shall, as discussed in the following paragraph, include a cavity vacuum pressure interlock capable of inhibiting RF power. The nominal design vacuum level of the un-powered RFQ is <5x10-8 Torr.

Monitors and interlocks.

Fast interlocks for forward power to the RFQ, reflected power from the RFQ, vacuum pressure, and water flow are integral to the RFQ equipment protection system. These are in addition to any personnel protection interlocks and interlocks protecting the RF power system itself.

The power potentially available to the RFQ and linac cave line (after the waveguide switch) is 2.5 MW; this is more than four times the maximum power consumption of 550 kW of the RFQ. Excessive power can potentially damage the RFQ inner surfaces, the RFQ power input couplers, and the coupler windows. Administrative configuration controls and the forward power interlock will limit the applied power. The forward power interlock circuit is active during a time window set by control system timer card channels; these timing channels must be set appropriately to protect the cavity during the entire  RF pulse. The timer must be re-set for each change of RF pulse length.

Any power reflected from the RFQ ends up in RF distribution system loads and does not harm the klystron. However, the reflected power may indicate serious problems such as electrical breakdown in the RFQ or the RFQ going off resonance. The reflected power potentially doubles the voltage in the coupler and RF transmission line and might initiate breakdowns there. A reflected power interlock shuts off the RF power in such potentially damaging conditions. The reflected power interlock circuit is active during a time window set by control system timer card channels; these timing channels must be set appropriately to protect against excessive reflected power during the ‘flattop’ of the RF pulse. The timer must be re-set for each change of RF pulse length.  Both the forward and reflected power couplers for the RF power interlocks are located immediately downstream of the RF switch.

The vacuum interlock shall be set to inhibit the RF at 8x10-7 to prevent operation at high power with bad vacuum, as this can be hazardous for the RFQ inner surface, coupler and coupler window. If, at the beginning of RF conditioning, trips occur too frequently, the interlock threshold can be raised to 1.3x10-6 Torr to start commissioning at lower voltage and/or short pulse length. The goal is to condition the RFQ to operate at <5x10-7 at full power.

The interlock system should also include a water flow switch that will inhibit the RF power if water flow is below 10 Gal/min.

The parameters that should be monitored during conditioning are RF drive level to the klystron, vacuum, residual gas spectrum (if RGA is available), the RF signal from the cavity field probe, forward and reflected power, and RFQ body temperature or inlet-outlet water temperature. These parameters will be monitored and periodically recorded with the HINS EPICS control system.

The Cavity Resonant Frequency Tuning

Before its delivery to the Fermilab, the RFQ’s field flatness is to be tuned to an acceptable level at the vendor’s site. Upon the installation of the RFQ at the MDB, the field flatness should be checked before the wiring of the RF power and the water system. In a low power measurement, signals from the twelve RF pickup ports on the RFQ can be measured. These measurements are to be compared to pre-measured values obtained at the vendor’s site. In case of significant discrepancy, expert consultation should be obtained before proceeding.

A phase detector circuit (mixer and low-pass filter) comparing the phase of the RFQ drive forward power signal to that of the RFQ RF pick-up signal shall be installed and tuned to provide a monitor of the cavity resonant frequency. This circuit shall be in place, operational, and calibrated before high-power commissioning commences.  Initially, it provides monitoring capability only; at some point, it can provide a feedback signal to an automatic frequency tracking loop or resonance control loop. Detuning of the RFQ can be compensated by the RFQ mechanical tuner and/or the vane water heater. At the first stage the tuning will be done manually; later a tuner feedback loop will be developed to keep the RFQ on resonance.

An SNS-style LLRF system, networked with the EPICS controls system, shall be available for use as desired when high-power commissioning commences. This system can provide a monitor of the RFQ resonant frequency. It compares the phase of the RFQ drive forward power signal to that of the RFQ RF pickup signal and provides feedback via EPICS to the RF source for frequency tracking or to the water heater and/or RFQ mechanical tuner for resonance control purposes. The SNS-style system only supports RF pulse lengths up to 1 millisecond; therefore this system is not suitable for RFQ commissioning at pulse lengths between 1.0 and 3.5 msec.

A temperature feedback loop can be developed in EPICS to keep the RFQ near the desired resonant frequency even when RF phase feedback signals are not available.

Success Completion of RF conditioning

Completion of RF conditioning is defined as 8 hours continuous operation of the RFQ at a repetition rate of 2.0 Hz, a RF pulse length of 3.5 msec at 450 kW, and a vacuum level of <5x10-7 torr with spark rate <1/10,000 pulses.

## General Conditioning Procedure Conditions

Prior to the start of RF conditioning for the RFQ, a signed approval to commence must be obtained from the HINS program manager or his designee.  That approval shall also assign a person who is responsible for execution of this commissioning procedure for the respective cavity. A sample form is provided at end of this document. The signed approval and assignment form shall be placed in the HINS Operating Procedures Book in the Meson Detector Building.

The specific goal of the RF conditioning of the RFQ is to achieve pulsed operation at 450 kW for a 3.5 msec RF pulse length and a repetition rate of 2.0 Hz with acceptable vacuum maintained only by the ion pump. The RF conditioning process will be accomplished manually by a human operator who is physically present at all times, not by an automatic programmed conditioning routine.

A general strategy of RF conditioning is to maintain a low intensity and frequency of electrical breakdown or arcing in a RFQ, while avoiding long interruptions caused by RF trips due to the vacuum and reverse power interlocks. Vacuum activity and even arcing are a normal part of RF conditioning at high electric fields; the rate of breakdowns should decrease with processing as small surface imperfections or dust particles are burned off. RF power is slowly increased while keeping the vacuum pressure below a pre-set threshold. If the vacuum goes above threshold, the RF power must be turned down. As vacuum recovers and the pressure is good again the operation resumes.

Along with low initial RF power level, a shortened pulse length and lowered repetition rate help to control outgassing in the cavity during conditioning. A suitable combination of RF level, pulse length and repetition rate can usually keep vacuum surge below the trip level. This delicate choice depends on skill and experience of operator. Occasionally a larger gas burst or hard breakdowns will trip off the klystron and this must be manually reset by operator.

## Specific Conditioning Procedure Steps

The procedure for RF testing and conditioning the RFQ is as follows:

- ____ Notify the Accelerator Division Radiation Safety Officer that power testing of the RFQ is ready to begin. In general, he will require that a radiation safety technician be present to perform radiation measurements at some stage(s) of the commissioning. Proceed only according to RSO’s instructions.

- ____ Verify, at nominal cavity temperature, using a network analyzer connected to the RFQ drive input, that the cavity resonant frequency is 325 ± 0.020 MHz. Adjust the resonant frequency with the motorized tuners or vane water heater as necessary.

- ____ Connect the high power RF transmission line to the RFQ.

- ____ Verify calibration of RF power monitors and proper connection of monitoring cabling.

- ____ Verify proper operation of vacuum and forward and reverse RF power interlocks.

- ____ Verify that the RFQ vacuum is <5x10-7 Torr and that the cooling water is flowing.

- ____ Verify the phase detector circuit operation and calibration (mixer type phase detector or that of the SNS LLRF system, whichever is being used).

- ____ Start conditioning with an input power of 1 kW at a RF pulse length of 10 μsec and repetition rate of 1 Hz or slower.

- ____ Monitor the cavity vacuum pressure and check reflected power for signs of sparking.

- ____ Increase RF power slowly, maintaining the 10 μsec pulse length, up to 225 kW. If vacuum pressure deteriorates to 1x10-6 Torr or sparking becomes evident the power level should be reduced by ~10% until the vacuum improves and the sparking rate is reduced to <1 per 10 pulses. If vacuum does not improve or sparking continues at high rate, experts must evaluate the situation and determine how to proceed.

- ____ When 225 kW power is achieved at 10 μsec RF pulse length, increase RF pulse length in sequence below, adjusting reflected power interlock timer settings accordingly at each pulse width. Verify that acceptable vacuum pressure and spark rate can be achieved at each step before proceeding to next. Monitor the RF phase and reflected power signals to assure that RF heating of the RFQ does not push the resonance too far from the drive frequency. If phase exceeds ±15 degrees, adjust vane water heater or RFQ mechanical tuner to return phase to nominal. Anytime vacuum does not improve or sparking continues at high rate, experts must evaluate the situation and determine how to proceed.

____ 20 μsec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

____ 50 μsec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

____ 100 μsec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

____ 200 μsec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

____ 500 μsec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

____ 1 msec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

[Note: SNS LLRF system does not support pulse lengths > 1 msec.

____ 2 msec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

____3.5 msec at < 1*10-6 Torr, < 1/10 spark rate and phase <±15 degrees

- ____ Reduce pulse length to 10 μsec and slowly increase power level up to 450 kW. Then repeat the pulse length increase sequence as in Step 11 above. If vacuum pressure or sparking is problematic, iterate at intermediate power levels to achieve full nominal power operation.

- ____ Repeat above steps to condition RFQ up to its nominal operating power of 450 kW.

- ____ Once full nominal operating power is achieved at 3.5 msec pulse length and repetition rate of 2.0 Hz is achieved, operate the cavity at this level for 8 hours to verify that the vacuum improves to < 5x10-7 Torr and that the cavity can run for this extended period without tripping.

## Subsequent Operating Procedure

After the RF conditioning goals are achieved, it is permissible to operate the RFQ at any power level within the achieved conditioning range for additional RFQ performance and sensitivity measurements or for low level RF and RFQ resonance control system development purposes. In particular, the resonant frequency sensitivity to RF power should be measured for the RFQ.

# HINS RFQ RF Conditioning Approval and Responsibility Assignment

Approval to proceed with RF power conditioning of the HINS RFQ according to the prescribed procedure is granted.

____________________ is assigned as the person responsible for executing the prescribed conditioning procedure for this cavity.

_______________________________                      ___________________________

HINS Program Manager or Designee                                        Date

# Text boxes

Coax Switch

2.5 MW

250 kW

to Cavity Test Cave

25 kW

Load

Load

10 db Waveguide Coupler

to RF Component Test Area Cage

Load

2.5 MW to RFQ and Linac Cave

Waveguide Switch

Circulator

Load

2.5 MW

Klystron

Figure 1.   RF Power and Distribution System Diagram

Waveguide Shutter