Pre-injector Upgrade Updates
(29 Apr – 12 May 2010)
C.Y. Tan
12 May 2010

---
RFQ PO is DONE! (05 May 2010)
- Approximate time line:
  - Started Trace simulations in Oct-Nov 2008
  - LBNL RFQ quote in July-Aug 2009
  - Swenson quote in Sep 2009
  - Schempp quote in Nov 2009
  - First “proposal” which got the attention of Steve Holmes: PAC2009 (Apr 2009)
  - First meeting with management with official proposal: Sep 2009
  - RFQ spec for vendors: Jan 2010
  - Approval with MONEY: Feb 2010
  - Purchasing: Mar 2010
  - Sole source PO done: 05 May 2010

---
Budget

---
Source Status

---
Insufficent Einzel Lens focusing for 100mA Beam

---
LEBT Status

---
MEBT Status

---
RFQ Status
- PS for RFQ is at ANL.
  - Bill has looked at it. Looks good. Paperwork done to bring it here.
- Source test area will be cleared to become RFQ test area.
- PO is DONE! (05 May 2010)

---
Test Stand
- Room preparation
  - After beam line layout (Kevin) Progress?
    - Water – Jim Slazak
    - Electrical – Jim Ranson
- Beam dump
  - Jim Walton
    - Data has been communicated to Jim. Will get back to us.
- Instrumentation (Vic)
  - Wires
  - Dipole for energy
  - Faraday cup (longitudinal bunch length and charge)

---
Controls
Mike Kucera will need to be involved.

---
Safety
After beam line layout in test area.

---
RFQ reminders
- Schempp is vendor
  - Make sure that the vanes are cleaned! See ISIS email.
    - Some cleaning details supplied by ISIS.
  - Review and verify on site mechanical design and construction (already in contract).
- Add current transformers at beginning and end of RFQ. (Save space in MEBT).
  - Once vendor is finalized, we have to design “ends” of the vacuum structure.