Pre-injector Upgrade Updates
(27 Oct – 10 Nov 2010)
C.Y. Tan
10 Nov 2010

---
Source Status

---
Source Priorities
- HINS wants their source back
  - Priority must be to get the Einzel lens test work done before we return the source.
  - Crowbar circuit assembled by end of week
    - Dan off to Japan next week.

---
LEBT Status

---
Chopper Timing
Needs to be verified
that they are fast enough
Courtesy of Dan Bollinger

---
There is current even when lens is off in test stand
Good for Einzel lens testing because we will be setting the Einzel lens to zero volts with crowbar circuit.

---
MEBT Status
Seriously considering replacing 3 quads with doublets.
See next talk.

---
Buncher
Indent for flange to save 1 cm.

---
BNL MEBT Quads
½ windings are hollow for cooling.
The other ½ are solid.
Gradient is still 60T/m max.
Not installed yet in the MEBT.

---
RFQ Status
- Schempp
  - Has corrected energy to 750keV
    - Still waiting for particle distribution and output files.
  - Drawings have been sent
  - Tank has been made. See pictures.
- PA assembly
  - Waiting for new engineer, coming on 01/01/11

---
RFQ tank waiting to be Cu plated
“Grooves” are an artifact of compression. Not there in real life.

---
Test Stand
- Room has been cleaned up.
  - Beam line layout in progress
    - Water – Bob Slazak
    - Electrical – Jim Ranson
- Need to test LEBT before RFQ connection
  - Wires, toroids at the end of the LEBT, same position as the RFQ.
- Design diagnostic line.
- Are drawings from Schempp sufficient to build table?

---
Test Area

---
Instrumentation
- Toroids clamp on
  - 1.5” over 3” flange toroids (7810)
    - sensitivity 0.1V/A. c.f. 1V/A
    - Rise time 50ns (same as non clamp on, 2x slower than present)
    - Length 1.25”
  - 6” toroids (7655)
    - 0.1V/A
    - Rise time 100 ns.
    - Length 1.5” (2.5x or 3x shorter than non clamp on)
Present

---
Conclusions
Some of Vic's conclusions last week
Persion CTs
  - 3100, 2854, 8583, 7810, 7655 have been used at FNAL
    - ~ 6 to 8 weeks
    - ~$15K with stand, ceramic, etc
    - ~$20K with VME readout electronics

---
Safety
When can the beam line layout in test area be done?

---
Controls
In flux
Status?

---
RFQ reminders
- Schempp is vendor
  - Make sure that the vanes are cleaned! See ISIS email.
    - Some cleaning details supplied by ISIS.
  - Review and verify on site mechanical design and construction (already in contract).