Pre-injector Upgrade Updates
(16 Mar 2011 – 30 Mar 2011)
C.Y. Tan
30 Mar 2011

---
Reminders
- Fill in the MS Project time lines.
- Fill in paper sections for the review.

---
Source Status

---
LEBT Status

---
Solenoid status
- #1 and #2 are good
  - #1 potted and being measured. Preliminary measurements show that field is higher than expected. Temperature rise only a few deg C at 600A. Results will be given to me soon.
  - #2 not potted yet but good.
- #3 winding is bad
  - New technique of adding insulation at the transitions to be tried out.
- #4 waiting.

---
RFQ Status
No news

---
MEBT Status

---
Grids are different from BNL

---
Preliminary Measurements (No grids)
Resonant frequency = 203MHz
Q=2300
S11=-10dB
c.f. Measured in Japan
Q = 3500
S11 = -43dB at resonance
Resonant freq = 201.25 MHz

---
Comparing Tuner Plunger Data
Japanese measuremnt
Our measurement at 203 MHz

---
Controls
Deprecated

---
Controls
- Controls meeting (23 Mar 2011)
  - See Elmie's summary
  - Worry about whether the room is too cramped
    - Do we want to temporarily tear out the source test stand?

---
Test Stand
- Room has been cleaned up.
  - Beam line layout in progress
    - Water – Bob Slazyk
    - Electrical – Jim Ranson
- Need to test LEBT before RFQ connection
  - Wires, toroids at the end of the LEBT, same position as the RFQ.
- Design diagnostic line.
- Drawings from Schempp are sufficient to build table.

---
Test Area

---
Safety
When can the beam line layout in test area be done?

---
RFQ reminders
- Schempp is vendor
  - Make sure that the vanes are cleaned! See ISIS email.
    - Some cleaning details supplied by ISIS.
  - Review and verify on site mechanical design and construction (already in contract).