RFQ Testing Timeline
C.Y. Tan
13 Apr 2011

---
June
May
July
Aug
Sep
April
Connect to LEBT, Beam test
Connect RFQ
H- testing
H- box
Vacuum, solenoids, controls etc.
New test stand
RFQ delivered
Vacuum test and lower power test
High power test
RFQ built
RFQ stand ready, RFQ driver must be ready
Solenoid delivered
Solenoid power up
Controls and ACNET

---
Expected Timeline
H- source testing
completed in old test stand May/June.
Completed in new test stand June/July
Solenoid testing done in June.
Receive RFQ May/June.
Low power testing.
High power testing complete in July.
Requires driver to be ready June/July.
Controls, vacuum.
LEBT must be ready by July.
PS, controls, vacuum, instrumentation.

---
Time line continued.
LEBT test with beam
Solenoid scans (No correctors) July.
Einzel lens test Aug.
Corrector scans Aug.
Beam thru RFQ Sept.
Instrumentation.
1st Quads should be here in Sept./Oct