Pre-injector Upgrade Updates
(11 May 2011 – 01 Jun 2011)
C.Y. Tan
01 Jun 2011

---
News
Vacuum meeting held on 24 May.

---
Reminders
- Fill in the MS Project time lines. See Elmie.
  - Steve Hays
  - Jim Lackey
  - Mike Kucera
  - Dan Bollinger
  - Brian Schupbach
- Fill in paper sections for the review.

---
June
May
July
Aug
Sep
April
Connect to LEBT, Beam test
Connect RFQ
H- testing
H- box
Vacuum, solenoids, controls etc.
New test stand
RFQ delivered
Vacuum test and lower power test
High power test
RFQ built
RFQ stand ready, RFQ driver must be ready
Solenoid delivered
Solenoid power up
Controls and ACNET
Note delay in RFQ delivery
We are here!

---
Source Status

---
LEBT Status

---
Solenoid status
- #1 Measurements are complete. Now in test area.
- #2 Measurements complete. Results are similar to #1.
- #3 will be aligned this week.
- #4 waiting for parts.

---
Quick Checks
- Correctors have a x-position change ~0.0175mm going from 500A to 600A.
  - Change in position is < 3% of beam sigma at the entrance of the RFQ if there is an x-position change at the upstream solenoid. Not significant.

---
RFQ Status
See next talk

---
MEBT Status

---
Bead Pull Station

---
Controls

---
Test Area

---
Safety
When can the beam line layout in test area be done?