Pre-injector Upgrade Updates
(01 Jun 2011 – 22 Jun 2011)
C.Y. Tan
22 Jun 2011

---
News
First shutdown meeting held on 15 Jun.

---
Reminders
- Fill in the MS Project time lines. See Elmie.
  - Steve Hays
  - Jim Lackey
  - Mike Kucera
  - Dan Bollinger
  - Brian Schupbach
- Fill in paper sections for the review.

---
June
July
Aug
Sep
Oct
Nov
Connect RFQ
Connect to LEBT, Beam test
H- box
H- testing
Vacuum, solenoids, controls etc.
Vacuum test and lower power test
High power test
RFQ built and tuned
RFQ delivered
RFQ stand ready, RFQ driver must be ready
Solenoid power up
Controls and ACNET
LEBT + stands end of July
H- box end of June, (extractor PS status?)
We are here!

---
Source Status

---
LEBT Status

---
Solenoid status
- #1, #2, #3 measurements are complete.
- Beam tubes to be welded on.
- #4 waiting for parts.

---
Solenoid 1
Solenoid 2

---
Solenoid 3

---
RFQ Status
As of 17 June
mechanic alignement has been remeasured – OK
now we are working on the final tuning the field is now +- 8% the frequency 202 MHz (not final)
now we are doing the tuner ball and prepare the coupler
the end plates are in our workshop, and silver coating of the screws

---
MEBT Status

---
Instrumentation and Test Stand

---
Controls

---
Test Area

---
Safety
Beam parameters submitted to safety (Gary Lauten) 10 Jun.