Pre-injector Upgrade Updates
(22 Jun 2011 – 06 Jul 2011)
C.Y. Tan
06 Jul 2011

---
News
- Review for solenoid testing (29 Jun)
  - Add a smoke detector to each power supply space and not install Klixons on the cables.
  - finish the interlock switch installation.
  - Install 480vac labels on lexan panels and on the terminal block and fuse covers.
  - Do a thermal scan of the rack at full load current when the magnet is back. This will require that we turn the rack during the test.
  - Have a mini walk through after complete.

---
Reminders
- Fill in the MS Project time lines. See Elmie.
  - Mike Kucera
  - Vic Scarpine
- Fill in paper sections for the review.

---
June
July
Aug
Sep
Oct
Nov
Connect RFQ
Connect to LEBT, Beam test
H- box
H- testing
Vacuum, solenoids, controls etc.
Vacuum test and lower power test
High power test
RFQ built and tuned
RFQ delivered
RFQ stand ready, RFQ driver must be ready
Solenoid power up
Controls and ACNET
LEBT + stands end of July
H- box end of June, (extractor PS status?)
We are here!

---
Note modification: position of toroid and pump out port flipped.

---
Source Status

---
LEBT Status

---
RFQ Status
Should be done. Waiting for email from Schempp (06 Jul)

---
MEBT Status

---
Relay Racks

---
Old drawing

---
Test area, test stand and instrumentation

---
Controls

---
Safety
Beam parameters submitted to safety (Gary Lauten) 10 Jun.