Pre-injector Upgrade Updates
(06 Jul 2011 – 20 Jul 2011)
C.Y. Tan
20 Jul 2011

---
News
- Vacuum controls meeting 13 Jul 2011.
- Shutdown meeting 13 Jul 2011.
- Review: 01 Sep 2011
  - Fill in paper sections for the review.

---
Reminders
- Fill in the MS Project time lines. See Elmie.
  - Mike Kucera
  - Vic Scarpine

---
June
July
Aug
Sep
Oct
Nov
Connect to LEBT, Beam test
Connect RFQ
H- box
H- testing
Vacuum, solenoids, controls etc.
Vacuum test and lower power test
RFQ built and tuned
High power test
RFQ delivered
RFQ stand ready, RFQ driver must be ready
Solenoid power up
SLIP by 2 weeks
Controls and ACNET
LEBT + stands end of July
H- box end of June, (extractor PS status?)
We are here!

---
Source Status

---
LEBT Status

---
RFQ Status
problems with the coupler (leak) and now wait on the brazing of the final loop our workshop is tight and its half manned because of holydays (sic) (08 Jul 2011)
we finally got our loop and it worked well but-
we had a leak in the coupling loop
back to the workshop
Janet and Benni working well, the UniTerms have finished, so that helps too (20 Jul)

---
MEBT Status

---
Test area, test stand and instrumentation

---
Controls
Needs update?

---
Safety