## Slide 1: Linac/400 MeV BPM System Plans and Status Nathan Eddy PIP Meeting 9/7/11

## Slide 2: Motivation
Update existing RF Logamp electronics with Digital electronics
  FPGA, ADC, Digital Signal Processing
  Long term stability
  Flexibility to modify system as needed
Implement calibration system to improve long-term stability
Implement phase measurement for Time of Flight/Energy measurement

## Slide 3: Project Scope
Includes the processing of the BPM pickup signals to determine beam position through the duration of the Linac beam pulse
Compute position averages and deliver all of the position data to the ACNET control system every 66 ms (15HZ)
A limited number of BPM’s in the Linac and 400 MeV line will be required to deliver all of the position data samples to applications running in ACNET at the 15 Hz rate
Does not involve changing the BPM detectors or the cabling that comes up from the Linac enclosure.

## Slide 4: BPM Specifications Document Craig Drennan
BPM Phase ~ 0.1 degrees @201MHz

## Slide 5: Linac Section
Instrument all existing Linac BPMs
Total of 76 BPMs (2 plates/channels)
  LE Linac (13)
  Transition (6)
  HE Linac (57)
    Module 1 & 2 - 6 each (12)
    Module 3-6 – 8 each (32)
    Module 7 (9)

## Slide 6: 400 MeV Area
48 BPMs of varying styles
  8 Dump Area
  40 in Transport Line
Support existing applications
  Beam Steering
  Momentum Measurements

## Slide 7: BPM Styles

## Slide 8: Use Updated MTA BPM Electronics
Low cost NIM based design developed by PPD previously used in Anti-proton source
Satisfies all required specifications
Make use of existing rack/crate infrastructure
Use Linac Controls Software developed for MTA

## Slide 9: MTA BPM Board
Upgrade MTA board
  mC, FPGA, ADC, clock & LO scheme
  Add ability to measure beam phase (relative to RF)
mC
fpga
Ethernet
USB
LVDS
Bus
ADCs
50MS/s
Analog
Quad
DCs
Digital I/O
DDS
SlowDAC

## Slide 10: MTA Installation
Readout speeds for 8 (1Kbyte + header) UDP packets
  Provides all RAW digitized I/Q data for 20usec @25MHz
  2.4ms for master and 7ms from single slave
Ethernet
LVDS Serial Bus
LinacCLK

## Slide 11: MTA BPM Software
Position & Intensity Parameters
Standard Controls BPM Application
Software for Needed for Linac
Waveform data currently readout via Python script
  Need to implement into ACNET
  Application?
Phase Measurement
Setup & Control Parameters

## Slide 12: Linac BPM Test
Split signals to 4 BPMs
  BPV204, BPH204
  D42BPV, D43BPH
Two MTA boards were installed in March and are being readout and data logged
  Need to confirm scale factors

## Slide 13: Phase Measurement Test
LO generated at Ref+1.25MHz (locked)
I/Q sampled at 25MHz (unlocked)
See <0.05 degree rms for single channel (plate) when averaged over 19us
4way
splitter
MTA
Board
201MHz
Ref
Inputs
A
B
C

## Slide 14: Triggering
Fully configurable within the FPGA
  Linac Clock Event
  External Trigger (TTL)
  Delay & Acquisition Window
  Beam Search
MTA System currently uses Linac Clock Event with a fixed Delay and Acquisition Window

## Slide 15: Data Acquisition
Provide average Position, Intensity, & Relative Phase over each beam pulse for every BPM @15Hz
Provide “waveform” data for select BPMs @15Hz
  Can select minimum of 1 BPM per crate
  Decimate data rate to 5-10MHz
Option to store all data to on-board ram for “slow” readback

## Slide 16: RF Signals – Use 2nd Harmonic
Chart: Linac BPM BPV20T, (201MHz) region
Chart: Linac BPM BPV20T, (201MHz) region

## Slide 17: Linac BPM Prototype
Ethernet
USB
LVDS
Serial Bus
JTAG
RF Input (805)
TTL I/O
4 Input
Channels
Ref
Channel
FPGA
uC
LO
Dist
Clock
Select

## Slide 18: Basic Components
Analog Quadrature Downcoverter – AD8348
  Provide from 0-40db variable gain
ADC – LTC2265 (upgrade)
  12 bits @ 805MHz/16 = 50.3MHz
FPGA – Altera Cyclone III (upgrade)
  Can provide all needed DSP
uController – Stelaris LM3S5B (upgrade)
  32 bit ARM processor operating at 80MHz
Ethernet – Wiznet W5300 (upgrade)
  16 bit providing ~4MB/s bandwidth
Custom LVDS Serial Data Bus (modified)
  25MHz providing ~2.5MB/s data transfer
  Can be sped up if needed

## Slide 19: Timing & Calibration Scheme
IN A0
Band
Pass
292-490 MHz
Quadrature
Downconverters
AD8348
Balun
1610 -1640
MHz VCO
PFD
Osc
÷ 8
FP
804.96
MHz
Ref
FGPA
AD9518
3dB
Pad
Coupler
LVDS bus
100.62 MHz
100.622
MHz VXO
PFD
Osc
ADF4001
100.62 MHz
LVDS 2:2
Mux/Fanout
Ref
402.48 MHz
CAL Tone
Directional
Coupler
Mini-Circuits
ROS-1640-219
Mini-Circuits
RBP-400
Micrel
SY89474
Micrel
SY89872
AD8348
Ref
Sel
÷ 2
Micrel
SY89872
1622.4975MHz
811.24875
Mhz LO
Base band is set to 22.5° per ADC sample at 50.31Msps
AD4360
Synthesizer
Coupler
Coupler
Splitter
101.406 MHz

## Slide 20: Board Status
4 Prototype Boards produced
  1 prototype 99% assembled. (Had to order cal tone amps with correct footprint)
  3 additional prototypes 15% assembled - Paula is working on these now
Testing Status
  Nominally checked
    Power Supplies (+1.2,+1.8,+2.5+3.3,+5)
    Microcontroller, FPGA, Network connection
    Clock Fanout PLL chip. Generates 404.0614MHz
    From 100.6223 MHz reference -> 3.144 MHz IF.
    Mixers, Offset Trim DACs, Gain DACs for the mixers
    IF BB Filters appear to be OK.
    ADC serial links for setting internal registers.
  Yet to do
    ADC data – adjust timing
    CAL tone
    Ref Channel
Mixer IF Output after
BB Filter, ADC clock
Scope FFT of IF

## Slide 21: Rough Schedule Projection
Complete bench testing of initial prototype – 1-2 week
Complete assembly of 3 remaining prototypes – 1 week
Begin Linac Beam testing – end of September
  Verify all Data Acquisition Modes
    Position, Intensity, Phase
  Benchmark readout time for “waveform” data
  2 months
Place order for 75 production boards – November
  Once convinced no hardware modification needed
Begin testing assembled boards – early 2012
Install and begin operation – before shutdown

## Slide 22: Rough Budget Estimate
Produce 75 Boards
  Parts purchased
  PCB, Front-Panels & Assembly ($20k)
Infrastructure
  15 refurbished NIM crates acquired
    Replacing 15 of 25 existing crates
  Cables ($10k)
  805MHz RF Distribution?