## Slide 1: PIP Update
June 13 2012

## Slide 2: Agenda
Summary Update
  Budget/RLS
  Current Activities
  Upcoming Activities/ Changes
Update Slides
  Booster 150KW PA S. Kotz
  Booster Lattice Measurements Meghan McAteer
  Short Kickers Salah Chaurize

## Slide 3: Update
General Info
Latest Budget Numbers
  No Change from last week
Labor
  Keep an eye on labor changes – impact to schedule!
RLS Info
  Elmie
Task Info
RFQ
  Still more simulations –
  Some agreement on energy – efficiency still being discussed
  Alignment work – then pump down and recheck of energy (without endplate)
High Power Testing of Ferrites – making progress – Testing Today
Cavity 7 Refurb - Tuners were removed to make better connection?
Absorber work continuing – Drawings Complete – (see pic)
Linac Modulator Work - Continental Electronics – approval to proceed

## Slide 4
Booster Absorber – note the fine Italian pink marble

## Slide 5
RFQ Energy Update – Simulation Slides

## Slide 6: Booster 150 KW Power Amplifier
Status Update
6/12/2012
S. Kotz

## Slide 7: As of June 12, 2012
2 Completed units for NoVA
7 Stations installed (East Side):
    1,2,4,5,6,7 and 8
1 Additional unit built & tested
    Station 3 (Not Mounted Yet)
2 Units partially built
    1 repaired unit awaiting testing
    1 unit awaiting Y567 Tube

## Slide 8: Schedule
14 Additional PA’s Needed
  10 Stations (West Booster Gallery)
  4 Spares
P.O. Requests Submitted
40% of Material Received & Inventoried
    All hardware
    Most of FNAL Machine Shop Items
    Still waiting for some larger pieces
      Cathode Resonator
      Copper Shroud
      Power Module Outer Shell

## Slide 9: Budget
First 12 Units Cost
$170,500 Total
$14,208 / PA
Next 14 Units Costs
$207,700 Total
$14,835 / PA
(Increase of 4.4%)
Budgeted: $323,859
Year to Date Obligations: $41,774
Balance: $282,085
(As of 12/31/2011)

## Slide 10: Timeline
Complete build & testing of first 12 PA’s
    June 2012 (On Track)
Begin build of next 14 PA’s
    July 2012
Build & test units (2 / Month)
    Goal is January 2013
Install into Stations
    When able

## Slide 11: Booster Optics Correction: Progress and Plans
6/13/2012
M. McAteer

## Slide 12: Outline
Beta beating correction results
Optics measurements with corrector packages turned off
Work to be done

## Slide 13: Beta Beating Correction Results

## Slide 14: Optics measurements with corrector magnets turned off

## Slide 15: Dispersion, with and without corrector magnets

## Slide 16: To Do Next:
Once magnet moves are completed and orbit is optimized, we will measure and correct optics again
Since we can significantly reduce beta and dispersion beating, it may be a good idea to do that before the next round of aperture scans
Source of apparent BPM scaling problem is still unknown; Manfred Wendt suggested a straightforward test of BPM response that we can do when beam is back

## Slide 17: We could make better optics measurements right after injection and after transition if we added a few more breakpoints to the dipole ramps.