## Slide 1: Booster 150 KW Power Amplifier
Status Update
10/3/2012
S. Kotz

## Slide 2: As of October 3, 2012
2 Completed units for NoVA
All East Side Stations installed
2 Additional units built & tested
    Waiting for install in West Booster Tunnel
Remaining units partially built
    Require Cathode Cooling Rings
    1 unit awaiting Y567 Tube

## Slide 3: Schedule
14 Additional PA’s Needed
  10 Stations (West Booster Gallery)
  4 Spares
95% of Material Received & Inventoried
    All hardware (Including Water Manifold items)
    Power Module Outer Shell
    Most of FNAL Machine Shop Items
      Still need Cathode Cooling Rings (in process)
    Cathode Resonator
    Copper Shroud

## Slide 4: Timeline
Completed building & testing of first 12 PA’s
Begun build of next 14 PA’s
    Two complete
    Remaining units built as far as possible
Build & test units (2+ / Month)
    Goal is still January 2013
    At least 8 for Booster West Gallery
Install into Stations
    During conversion