## Slide 1: PIP Update
Oct 10 2012

## Slide 2: Agenda
Summary Update
  Current Activities
Updates/Talks:
Dave Johnson – Linac Notching (laser)

## Slide 3: Update
General Info
Current Work
  Booster RF cavity rework – RF 6
  LCW – Fill is not done – fixing leaks
  RFQ – Never ending Electrical work, New Injector being installed
  HPower RF – A 1.4M is waiting for signature - ODDONE,PIERMARIA
    Waiting for 1.4 req. before submitting second req. for remaining cost
  High Power Ferrite Testing –
  Booster Absorber – Kicker and PS work continues – Kicker Testing
  Linac Modulator – Working out labor for task vs funding
  Booster Solid State – Rack work was in progress last week?
  Booster Modulator work – 7 done 3 in progress, 12 still need socket rings (due Oct 25)
  Tuner with new ferrite – waiting for RF6 completion/testing
  Cogging – Software work continues
  Booster Shielding – Started to review again old doc/absorber/penetrations
Shutdown - comments (Fernanda, Todd, Mary)
End of Fiscal Year – cleaning up Pro-Card numbers/ Lab still looking at FY12 for FY13 (Pier – decisions)

## Slide 6
Required for 12 Hz Required for Flux
Required for 15 Hz Required for Reliability
Completion Date
Before FY13 Budget
Task identified as a goal requirement but many of these overlap.
Recent Budget guidance still being worked through the planning and RLS process.

## Slide 7: Upcoming
RLS – Just about done with updates
Fiscal Year Start –
  Reports (October)
    PMG
    Quarterly Report
  Will have special meeting today with Ann to discuss FY13
  Need to have
PIP talk at PAC (Monday)
  Where’s the beam

## Slide 8: Talks
Dave Johnson – Linac Notching