## Slide 1: PIP Update
Dec 5th 2012

## Slide 2: Agenda
Summary Update
  Current Activities
Updates/Talks:
CY Tan – RIL Status/Plans
F. Garcia – Linac Status/Plans

## Slide 3: Update
General Info
Current Work
  Booster RF cavity rework – Two cavities waiting (1&3) – 3 is at MI-60
  Tuner Work – Completed a set of ~ 9 cones
  Starting Tuner work. Complete a tuner in a couple of next week – then start on RF3.
LCW – L2-1 manifold leak – finished, Replacing L3, MP02 tubing – progressing, Replace strainer valves on magnet bus – complete, Repair L5 choke leak - continues, Replace reference magnet hosing – complete at L1-2 manifold, replace "Y" strainer valves leaking (7), re-hose reference magnet
  RFQ – Beam down to NTF/tuning – shutdown this week for work – Tan’s Talk
  HPower NO word
  Booster Absorber: One steel block modified/alignment done/finish stacking
  Linac Modulator – EE continues testing (update talk sometime)
  Booster SS: 12 out of 19 stations have had the attenuation and phase measured for the BRF fanback system, prepping for modulators
  Booster Modulator work – Did not ship last week – 4 this week, 2 next week, 4CW800F filament transformers going and should be completed this week
  Cogging – Software work continues
  Booster Shielding – Safety meeting – went over penetration issues
Shutdown - comments (Fernanda, Todd, Mary)
End of Fiscal Year – Not much change –

## Slide 4
Mary:
Scheduling meeting tomorrow
In Huddle

## Slide 5: Upcoming
RLS – updates (last week ) Due back
  (Elmie is gone but not forgotten – Ken is now the controls person)
Reports (upcoming)
  December 12:
  Jon Reid - Collected results from first four cavity refurbishments, new-ferrite tuner, potential stem interface modifications, and cavity 1013
  Todd Sullivan - Booster Startup Plans
To be scheduled:
  Alex Macridin - Simulations of Transverse Instabilities
  Dan Wolff et al. - Linac Modulator Prototyping
  Dave Hixson - Booster LCW Upgrades Final Report
PIP Talks/Lab Meetings/Management
  AEM - January
  Quarterly Report - January
  PIP PMG - January