## Slide 1: PIP Update
April 24th 2013

## Slide 2: Agenda
Summary Update
  Current Activities/Updates
  Startup Plans
  Upcoming Talks, Reports, Meetings
Updates/Talks:
Ken Domann - Project Schedule and Budget Report
Fernanda Garcia - Report on CPI site visit

## Slide 3: Update
General Info
  Booster Beam: Running still at reduced levels (Shutdown today due to feeder work)
  Studies are underway:
    Apertures / Orbit Smoothing will continue – Kiyomi, Boosters
    Optics measurements - Yuri
  Booster SS: Stations are operating – controls / shunt problems (One more shut failure)
    Booster voltage still low – but after 7 repair should be near operating levels (2 weeks?)
  Booster RF cavity rework – RF1 installed yesterday – being aligned today
    Cavity from RF15 – tuners being reworked
    Spare cavity work – Any news?
    Booster RF Cavity 7 (8 also but less) has been pulled for RF leak issue
    We will have 17/19 cavities after the next swap (up from 16) – may allow high-intensity
  Booster Ferrites
    Low Frequency tester – shipped – Any news?
    Second LF tester completed and tested – looks good
  RFQ –2nd source will be ready for operations next week! Trim will be installed in May
  HLRF –site visit at vendor (Fernanda and Al – Past Monday)
  Linac Modulator – Talk by Mark from SLAC Friday (Thursday talk on Klystron Mod)
  Booster Shielding – First part of document given to ES&H, Another scan next week…
  Booster Transverse damper needs to be re-commissioned, Long damper plans started
  MI Startup: End of May/Early June – delays due to water…not sure what day
Startup comments (Fernanda, Todd)

## Slide 4
Low Power Ferrite Tester
Repaired Tuner after last 4 sections were repaired
Booster LCW leak

## Slide 5: Upcoming Talks
Future Meetings:
Today:
Eliana Gianfelice - Booster Optics Correction Procedure and Results
To be Scheduled:
Dave Augustine - Vacuum Installations Finished and in Planning
Jean-Paul Carneiro - TraceWin 3D Simulations of the Fermilab Linac
Bill Pellico - Loss Test Scans for Shielding Assessment
John Reid - Solid State Installation - Final Report

## Slide 6: Upcoming
Reports
  Update of PIP Design Report – Yearly update work
  PMG & Quarterly report in April (Completed – submit today)
Budget Issues – No change from last week -
  Lots of talk about next year – nothing is certain but could be a tough year…..
- Please use the E-Log to put general work in progress updates/photos – weekly would be nice – if progress is being made in task