## Sheet1
System | Description | Status | Amount | Subtotal | Total | status | Date
773188
Linac
Linac low energy | Replace tank 2 valve. This valve is defective and chews it's self apart. |  | 1 | 3000 | 3000 | installed | 2012-07-01
Linac low energy | Replace tank 3 valve. This valve is defective and chews it's self apart. |  | 1 | 3000 | 3000 | installed | 2012-07-01
Linac low energy | Replace tank 4 valve. This valve is defective and chews it's self apart. |  | 1 | 3000 | 3000 | installed | 2012-07-01
Linac low energy | Replace tank 5 valve. This valve is defective and chews it's self apart. |  | 1 | 3000 | 3000 | installed | 2012-07-01
Linac low energy | Replace tank NTF valve. This valve is defective and chews it's self apart. |  | 1 | 3000 | 3000 | installed | 2012-07-01
Linac low energy | Purchase spare valve for Low energy tanks and NTF |  | 1 | 3000 | 3000 | Storage
Linac low energy | Replace 1397 sargent welch oil sealed roughing with scroll pump. This pump used to pump on tank one stem box |  | 1 | 7000 | 7000 | Not Purchased
Linac low energy | Replace 1397 sargent welch oil sealed roughing with scroll pump. This pump used to pump on tank one stem box |  | 1 | 7000 | 7000 | Not Purchased
Linac low energy | Replace 1397 sargent welch oil sealed roughing with scroll pump. This pump used to pump on tank one stem box |  | 1 | 7000 | 7000 | Not Purchased
Linac low energy | Roots Blower |  | 1 | 58000 | 58000 | Installed | 2013-09-01
Linac low energy | Roots Blower |  | 1 | 58000 | 58000 | Installed | 2013-09-01
Linac low energy | Roots Blower |  | 1 | 58000 | 58000 | Not Purchased
Linac low energy | Purchase custom o-rings for low energy end bell vacuum seal. No spares, no stack available. | Found a vendor and have a cost | 1 | 5000 | 5000 | Not Purchased
High Energy Linac | 2 spare ion pumps for bridge couplers, no spares |  | 2 | 2000 | 4000 | Not Purchased
400 MEV and dump line
400 MEV and dump line | Replace sargent welch turbo station on 400 mev line top of chute |  | 1 | 7500 | 7500 | Not Purchased
400 MEV and dump line | Replace sargent welch turbo station on Booster BD1 |  | 1 | 7500 | 7500 | Not Purchased
400 MEV and dump line | Replace sargent welch turbo station on Chopper |  | 1 | 7500 | 7500 | Not Purchased
400 MEV and dump line | Replace sargent welch turbo station on 400 mev line top of chute |  | 1 | 7500 | 7500 | Not Purchased
400 MEV and dump line | Replace oil sealed roughing pump with scroll pump at momentun dump |  | 1 | 7000 | 7000 | Not Purchased
400 MEV and dump line | Replace oil sealed roughing pump with scroll pump at 400 mev chute |  | 1 | 7000 | 7000 | Not Purchased
400 MEV and dump line | Replace oil sealed roughing pump with scroll pump at Booster BD1 |  | 1 | 7000 | 7000 | Not Purchased
400 MEV and dump line | Replace oil sealed roughing pump with scroll pump at Chopper |  | 1 | 7000 | 7000 | Not Purchased
400 MEV and dump line | replace vacuum valve on Momentun dump turbo pump |  | 1 | 3000 | 3000 | Not Purchased
400 MEV and dump line | replace vacuum valve on Chopper turbo pump |  | 1 | 3000 | 3000 | Not Purchased
400 MEV and dump line | replace vacuum valve on BD1 turbo pump |  | 1 | 3000 | 3000 | Not Purchased
400 MEV and dump line | replace vacuum valve on Chute turbo pump |  | 1 | 3000 | 3000 | Not Purchased
400 MEV and dump line | Replace VLNLAM to a valve that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
400 MEV and dump line | Replace VLNDMP to a valve that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
400 MEV and dump line | Replace VI-LAM to a valve that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
400 MEV and dump line | Replace VI-Q5 to a valve that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
400 MEV and dump line | Purchase spare valve for 400 MEV and dump area that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased in storage
0
Liquid Nitrogen | Repair dewar 09 | Paid by MSD funds | 1 | 39000 | 39000 | Complete | 2011-05-25
Liquid Nitrogen | Repair dewar 01 |  | 1 | 39000 | 39000 | Complete | 2012-10-04
Liquid Nitrogen | Add Bypass Line around building in case underground fails | Added to plan in FY2013 | 1 | 15000 | 15000 | Not Purchased
Booster | Short 1 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Short 2 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Short 3 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Short 4 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Short 5 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Short 6 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Short 7 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 8 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 9 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 10 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 11 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 12 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 13 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 14 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 15 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 16 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 17 Replace Sargent Welch turbo | Purchased by MSD | 1 | 7500 | 7500 | complete | installed 2010
Booster | Short 18 Replace Sargent Welch turbo | Purchased by MSD | 1 | 7500 | 7500 | complete | installed 2010
Booster | Short 19 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 20 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 21 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 22 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Purchased not installed
Booster | Short 23 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Short 24 Replace Sargent Welch turbo |  | 1 | 7500 | 7500 | Not Purchased
Booster | Replace Roots blower station West gallery South |  | 1 | 17000 | 17000 | Complete | 2012-12-01
Booster | Replace Roots blower station West gallery North |  | 1 | 17000 | 17000 | Complete | 2012-12-01
Booster | Replace Roots blower station East gallery South | Purchased by MSD | 1 | 17000 | 17000 | Complete | installed 2010
Booster | Replace Roots blower station East gallery North | Purchased by MSD | 1 | 17000 | 17000 | Complete | installed 2010
Booster | 24,1,2 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
Booster | 3, 4,5,6 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
Booster | 7,8,9,10 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
Booster | 11,12 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Installed | 2013-02-25
Booster | 13,14,15,16 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Installed | 2013-02-25
Booster | 17, 18 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
Booster | 19,20 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Purchased not installed
Booster | 21,22,23 Replace gate valve to a type that will mechanically lock when closed. |  | 1 | 4043 | 4043 | Installed | 2013-02-25
Booster | Replace sargent welch turbo pump 400 mev to Injection girder |  | 1 | 7500 | 7500 | Not Purchased
Booster | Replace sargent welch roughing pump 400 mev to Injection girder |  | 1 | 7000 | 7000 | Not Purchased
| Replace vacuum valve on 400 MEV to inj girder line |  | 1 | 4043 | 4043 | Purchased not installed
Booster | Replace sargent welch turbo pump on foil box |  | 1 | 7500 | 7500 | Not Purchased
Booster | Replace sargent welch roughing pump on foil box |  | 1 | 7000 | 7000 | Not Purchased
| Replace vacuum valve on MP02 |  | 1 | 3000 | 3000 | Not Purchased
Booster | Replace sargent welch turbo pump on MP02 |  | 1 | 7500 | 7500 | Not Purchased
Booster | Replace sargent welch roughing pump on MP02 |  | 1 | 7000 | 7000 | Not Purchased
| Replace vacuum valve on us 8 Gev line |  | 1 | 4043 | 4043 | Purchased not installed
Booster | Replace sargent welch turbo pump for US 8 GeV |  | 1 | 7500 | 7500 | Not Purchased
Booster | Replace sargent welch roughing pump for US 8 GeV |  | 1 | 7000 | 7000 | Not Purchased
| Replace vacuum valve on 400 MEV to Linac |  | 1 | 4043 | 4043 | Purchased not installed
Booster | Replace sargent welch turbo pump 400 mev to Linac |  | 1 | 7500 | 7500 | Not Purchased
Booster | Replace sargent welch roughing pump 400 mev to Linac |  | 1 | 7000 | 7000 | Not Purchased