## Slide 1: PIP Update
May 8th 2013

## Slide 2: Agenda
Summary Update
  Current Activities/Updates
  Startup Plans
  Upcoming Talks, Reports, Meetings
Updates/Talks:
Ryan Crawford – Booster Transformer/ Linac Hatch Schedule
Dave Augustine – Vacuum work summary

## Slide 3: Update
General Info
  Booster Beam: Running still at reduced levels:
    Still need to push higher intensity -> would like 4E12 before MI starts up -> More RF
  Studies are underway:
    Apertures / Orbit Smoothing will continue – Kiyomi, Boosters
    Optics measurements – Yuri
    Cogging software work continues
    Booster optics software – Tan, Eliana -> streamlining and documenting https://cdcvs.fnal.gov/redmine/projects/booster_loco/wiki/Wiki
  Booster SS: Stations are operating – controls / shunt problems (station 8 today!)
  Booster RF cavity rework – RF1 installed yesterday – being aligned today
    Cavity from RF15 – being reassembled
    Spare cavity work – on hold for the most part – some parts in shop
    Booster RF Cavity 7 RF leak investigation ongoing (8 will need to have outer tuner replaced)
    We will have 17/19 cavities after the next swap (up from 16) – may allow high-intensity
  Booster Ferrites
    National Magnetics visited and toured site – discussed options
    Delivery of 5 low u ferrites arrived yesterday – next step is to verify and HP test
  RFQ –2nd source will be ready for operations next week! Trim will be delivered 5/17
  HLRF – Exchanging documentation with CPI
    SLAC (Ongoing discussions about role and Klystron issues – very helpful)
    BNL interested in staying in loop and early stages of design
  Linac Modulator – Talk by Mark from SLAC -> Need to follow-up with plans for next step
  Booster Shielding – Did a another scan – new data helpful – but looking at one more scan L11
  Booster Transverse damper – Work on recommissioning: Long damper plans started
  MI Startup: End of May/Early June – delays due to water…not sure what day
Startup comments (Fernanda, Todd)

## Slide 4
RF leakage at tuner

## Slide 5: Upcoming Talks
Future Meetings to be Scheduled:
Jean-Paul Carneiro - TraceWin 3D Simulations of the Fermilab Linac
Bill Pellico - Loss Test Scans for Shielding Assessment
John Reid - Solid State Installation - Final Report
Kiymoi – Booster cogging plans
Eddy – Booster damper plans
Tan – RFQ Summary (after install of corrector and source B operating)

## Slide 6: Upcoming
Reports
  Update of PIP Design Report – Yearly update work
  PMG May 22nd
  Quarterly submitted – no comments
Budget Issues – No change from last week -
Please use the E-Log to put general work in progress updates/photos – weekly would be nice – if progress is being made in task
  Need to post