## Slide 1: PIP Update
Aug. 21st 2013

## Slide 2: Agenda
Summary Update
  Current Activities/Updates
  Startup Plans
  Upcoming Talks, Reports, Meetings
Updates/Talks:
B Pellico – Recent Budget/Labor exercise
Kiyomi Seiya – Magnet Moves/Scans

## Slide 3: Update
General Info
  PreAcc Beam: Source Current > 68ma
    Running on source ‘A’
      Spark rate about 1/15 minutes
      Source ‘B’ ready to go
  Linac Beam: Tank 7 ~26ma
  Booster Beam: Tuning - studies
    Studies at lower intensity
  Studies still underway:
    Transverse damper studies – not yet started – need to put system back together
    Cogging software work continues
    Booster optics software – Tan stream lining code (talking to AD controls people)
    Booster RF cavity rework
    Cavity from RF17 being refurbished (cooler than RF 19) – On test stand
    Booster RF19 will be next – has been out of tunnel for some time to allow for extra cool down
    Spare Cavity Work – next step to furnace weld end pieces then mate with corona rings?
  Booster Ferrites
    Were due 2nd or 3rd week of July –
      High mu cores – will be shipped EOW 7/26 – tested, looks similar to old cores but mu lower – next step?
      Low Mu cores 60 on 8/23, 60 on 9/6 and 76 (balance) on 9/27 (this week – first batch?)
  HLRF – PO all signed off – but issues with purchasing agreement CPFF is causing issues!!!
  Linac Modulator - 3 cell tested – up to 900v/cell with peak current of 27 amps
  Booster Shielding – Need to finish up energy/loss simulations
  Booster Longitudinal dampers –software effort just starting, PO for new board signed…..
  MI Startup: Not sure
Startup comments (Fernanda)

## Slide 4
1 | DTI switches and controller for extractor (and spare for Einzel Chopper) | 100,000
2 | Booster Transformer (MCC and spare breaker) | 167,000
3 | Buncher Solid State RF power | 40,000
4 | 12 Scroll Pumps for Booster | 90,000
5 | Linac Roughing Station | 57,000
6 | Laser Amp for Linac Notcher | 50,000
7 | 1st Linac 7835 | 239,000
8 | RFQ Turbo and Roughing station/controls | 40,000
9 | 400 MeV line pumps | 20,000
10 | 2nd Linac 7835 | 239,000
11 | 14 Booster roughing and turbo pumps stations | 90,000
12 | Replace 5 Booster valves | 28,000
13 | Linac Modulator (SLAC Version) | 47,000
14 | SS amp for Linac Driver system | 50,000
15 | Booster Anode Supply Transformers | 260,000
16 | Laser notch pulser | 20,000
17 | 201 MHz Circulator | 121,000
18 | Linac 55 chilled water pump and plumbing | 38,000
19 | 3rd Linac 7835 | 239,000
20 | Injector Solenoid and trim PS | 40,000
21 | RF work room | 25,000
Supplemental Funding

## Slide 5: Upcoming Talks
Future Meetings to be Scheduled:
Bill Pellico - Loss Test Scans for Shielding Assessment
John Reid - Solid State Installation - Final Report
Kiymoi – Booster cogging plans
Eddy – Booster damper plans
Tan – RFQ Summary (after install of corrector and source B operating)

## Slide 6: Recent PIP Budget/News
Meeting new director Nigel at MI-60!
  Fernanda, Matt and John gave a 30 minute tour and PIP talk
Reports
  Update of PIP Design Report – Yearly update work
  3rd quarter PMG – this morning
Budget Issues – Submitted FY14 labor and Budget
  Labor given to other divisions/AD departments
    Have discussed issues with AD department head (small changes)
    Had some changes to TD labor – added some names left off list
  PIP 11 M FY14 budget given to Ann
Supplemental Funding – approved and nearly spent
    There are several POs still needing to get finished
Please use the E-Log to put general work in progress updates/photos – weekly would be nice – if progress is being made in task
  Need to post