## Slide 1: PIP Update
Dec. 4th 2013

## Slide 2: Agenda
Summary Update
  Current Activities/Updates
  Recent PIP News
  Upcoming Talks, Reports, Meetings
Updates/Talks:
Ken Domann
K. Seiya (Cogging)
C. Jenson (Notch PS)

## Slide 3: Update
General Info
  PreAcc Beam: Switched to source B – ‘A’ ran for about 4 weeks only- too much sparkie
  Linac Beam: General Tuning
  Linac SBK looks to be in final stages – finishing up contract which should be done soon
  Linac Laser Notching –
  Linac – received trombone for RFQ system – waiting on mechanical support
  Modulator work – progressing on building up 9 cell – 3 cell testing was very useful (talk 2 weeks)
    Trevor will be visiting the SLAC team to discuss their progress and plans
  Booster Beam: Tuning – beam for HEP and studies
    Transverse damper – fixed damper a month ago – trying to get to get system back up and running
    Cogging software work continues – old system used in operation but new system being tested – talk today
    Booster orbit smoothing – no recent changes
    Booster optics software – Still need to move forward on software – waiting upon Russian scientist
    Booster Longitudinal dampers – hopefully will start/started firmware?
  Booster RF cavity rework
    Booster RF8 is being re-installed today – ran well on test stand for about a week
    Booster RF3 is being removed (this was already refurbished but has a RF sparking on BTM tuner)
    Spare Cavity Work – waiting for tuners/labor – not likely to happen for some time
    New Cavities – some meetings to start up process – looking to set timetable/milestones
    Perpendicular Cavities – progress in modeling now looking to refine and fix issues (Talk after holidays)
  Booster Ferrites
      Low Mu cores all tested – results posted in log….good to go on new tuners
      High mu cores – we have asked to one last trial batch on 10 tuners – hopefully will validate vendor and then purchase
        We have placed an order for 10 high mu cores – not sure how long it will take!
  Booster Shielding – Discussions on how to proceed with beam based measurements and MARS
  Short Kickers tested good – will be used for PS testing
  Notcher PS system being built – talk today

## Slide 4: Recent PIP Budget/News
Supplemental Funding – Spent nearly all of allotted $$
  Materials starting to arrive (will help FY14 M&S – but need labor)
Budget Issues – Submitted FY14 labor and Budget
  Labor: Many projects cut AD labor – PIP should benefit
    Managers should make sure they update schedules - M&S /Labor changes
  PIP 11 M FY14 budget – spending M&S should not be an issue?
  New director
    PIP is recognized as essential – now PX is called PIP2
    Rumor has it that we may have to do more formal reviews – mangers help
  New AD director (Sergei) says he wants to do what it takes for PIP
    Several meeting to discuss labor and funds – will see changes!
  We may be asked to give some AD PIP seminars
    Creating list – you may be asked to talk – in front of large hostile crowd
Please use the E-Log to put general work in progress updates/photos – weekly would be nice – if progress is being made in task
  Other than Refurb no other use of log!!! Need to change that…

## Slide 5
 | Values |  | 
Row Labels | Sum of FY2014 Direct M&S TOTAL | Sum of FY2014 Overhead TOTAL | Sum of FY2014 Direct M&S + Overhead
2103 Proton Improvement Plan (PIP) | 4,782,178.42 | 835,576.94 | 5,617,755.36
2103.00.00.01.AD AD-Proton Improvement Plan Management Reserve OP | 121,091.62 | 0.00 | 121,091.62
Contingency Allocation | 121,091.62 | 0.00 | 121,091.62
2103.00.01.AD AD-Proton Improvement Plan Program Management | 56,000.00 | 11,952.00 | 67,952.00
2103.01.01.01.02.AD AD-Linac PIP 200 MHz RF PS PA Prototype | 460,000.00 | 107,300.00 | 567,300.00
2103.01.01.02.01.AD AD-Linac PIP 200 MHz RF PS Modulator Prelim Design | 237,000.00 | 55,813.50 | 292,813.50
2103.01.01.02.02.AD AD-Linac PIP 200 MHz RF PS Prototype | 76,000.00 | 17,898.00 | 93,898.00
2103.01.01.04.AD AD-Linac PIP 7835 Tube Acquisitions | 600,000.00 | 0.00 | 600,000.00
2103.01.02.03.AD AD-Linac PIP Notching System Improvements | 285,000.00 | 67,117.50 | 352,117.50
2103.01.05.02.AD AD-Linac PIP Dual Temp/LCW System Maint & Repairs | 5,000.00 | 2,739.50 | 7,739.50
2103.01.05.03.AD AD-Linac PIP Vacuum Systems Replacement | 160,000.00 | 37,680.00 | 197,680.00
2103.02.01.01.02.AD AD-Booster PIP RF Anode PS Fabrication | 700,000.00 | 164,850.00 | 864,850.00
2103.02.01.02.02.AD AD-Booster PIP RF Bias Supp Design & Specs | 180,000.00 | 42,390.00 | 222,390.00
2103.02.01.05.02.AD AD-Booster PIP RF Cavities and Tuners Rework | 310,086.80 | 73,025.44 | 383,112.24
2103.02.01.06.03.AD AD-Booster PIP New RF Tuners Fabrication | 510,000.00 | 0.00 | 510,000.00
2103.02.01.07.03.AD AD-Booster PIP New RF Cavity Final Design and Prototype | 875,000.00 | 206,062.50 | 1,081,062.50
2103.02.02.01.AD AD-Booster PIP Accelerator Physics Studies | 7,500.00 | 1,766.25 | 9,266.25
2103.02.02.03.AD AD-Booster PIP Notching System Improvements | 13,500.00 | 3,179.25 | 16,679.25
2103.02.02.05.01.AD AD-Booster PIP Collimation System Improvements | 80,000.00 | 18,840.00 | 98,840.00
2103.02.03.02.AD AD-Booster PIP Damper Systems Improvements | 50,000.00 | 11,775.00 | 61,775.00
2103.02.05.03.AD AD-Booster PIP Vacuum Systems Replacement | 56,000.00 | 13,188.00 | 69,188.00
Grand Total | 4,782,178.42 | 835,576.94 | 5,617,755.36
FY14 has funding and labor –

## Slide 6: Upcoming Talks
Future Meetings to be Scheduled:
Howie – Linac Modulator
Trevor – Linac Modulator (SLAC)
Eddy – Booster damper plans
Bill Pellico - Loss Scans and Shielding Assessment
Jon Reid - Solid State Installation - Final Report