## Slide 1: PIP Update
March 12th 2014

## Slide 2: Agenda
Summary Update
  Current Activities/Updates
  Upcoming Talks, Reports, Meetings
Updates/Talks:
Chaurize – Notcher PS
Crawford – Anode Supply Update

## Slide 3: Update
  Linac SBK – No recent upgrade – CPI AT WORK -
  Linac Laser Notching – Optical pulse generator has been repackaged and tested and setting up the equipment rack and loading all the necessary drivers
  Modulator work – EE: Proceeding with build up of 20 cell. SLAC: issues with the current design which does not accommodate a feedback system. Trevor is working with them on their plan/issues.
  Linac Beam Physics: Linac – waiting for JP on RFQ injector sims
  Injector Lens issue – swapped lens but also now working on new design
  Booster Beam:
    Transverse damper – work started last week on turning on system – some issue with clock lock
    Cogging software work continues – Kiyomi working on notch creation/sync with present system
    Booster optics software – meeting to decide operational issues – talked to controls about how to implement (software vs Hardware)
    Booster Longitudinal dampers - old system repaired and running well – waiting for firmware development of new card
  Booster RF
    Booster RF3 cavity on test stand – issues with vacuum and a water leak has delayed work
    RF19 – being repaired – Cavity has had tuners removed (at least side tuners)
    Cone work continues – TD has a batch that is having cooling attached
    New Cavities – working to set some cavity design specifications (Tom is setting up meeting)
    Perpendicular Cavities – progress on simulations and testing of TRIUMF cavity – working on solenoid design. Issues with solenoid/heating still being worked on.
    High mu cores - A new batch, initial results are good μ but q lower than our trial batch
      The two samples tested as expected!
      Next sample set should be finished soon according to last email…Ralph has not heard anything yet.
    Booster Anode Supplies – update slides
    Booster Bias supplies – Work being done with EE supt. help - plan to have a prototype done in Feb. March – updated schedule.
  Booster Shielding – bi-weekly safety meetings – discussing simulations and next step(s)
    When weather clears – will try and set up another round of testing –
  Booster Nothcer – Update slides

## Slide 4: Potentials.

## Slide 5: Recent PIP Budget/News
Budget Issues: Meeting today with Ann but no news
Labor: Looked at Feb labor numbers – some are over – some are under but FTL seem to be increasing
  General
    PIP2: Review (CY Tan, B Zwaska – talked)
    Keeping an eye on it for impact to PIP but alignment did come up
  PIP talks planned
PMG – March
Sergei
  DOE Talk
Lots of Lab talk
  Proton Needs
  New Experiments
Update of RLS just about done – needed for review!
P5 should report back to lab in April – PIP impact likely

## Slide 6: Upcoming Talks
Future Meetings to be Scheduled:
Pat Sheehan – Booster Bias Supplies
Tom Kubicki – New Booster Cavity Plan
Eddy – Booster damper plans
CY Tan – Perpendicular Cavities
Bill Pellico - Loss Scans and Shielding Assessment
John Reid - Solid State Installation - Final Report