## Slide 1: PIP Update
April 30th 2014

## Slide 2: Agenda
Summary Update
  Current Activities/Updates
  Nathan Eddy – Booster Longitudinal Damper

## Slide 3: Update
  Linac SBK: Working on gallery issues – Transformer Oil, Floor loading: (CDR in June)
  Linac LN: Mode hopping in the laser diode source, acquiring a new seed source, mechanical drawings for optical cavity
  Modulator work: EE support is proceeding with build up of 25 cell
  Linac Beam Physics: No news
  Injector: Both sources up and running, testing larger volume source in test stand, Gas Testing Next
  Booster Beam:
    Transverse damper – Trying to get tune measurement up and running
    Cogging software work continues – testing on MI cycles continues
    Booster optics software – Tested 465 cards for tune control – adjusting software for finer control.
    Booster Longitudinal dampers - Update Talk Today
  Booster RF
    Booster RF2 being worked on, lathe work, tuner work– ready for testing in 2 weeks?
    RF19 – Testing started this weekend -
    Looking at extra tuners: One that was stored in box removed, One on large bore cavity?
    New Parallel Cavities –Perpendicular Cavities – Working on ferrite measurements and simulations /heating estimates - buying ferrite samples
    Starting to build new tuner with the new ferrite!! Assembly being done at IB2.
      Lots of documentation to go along with new tuner
    Booster Anode Supplies – Work continues – Ordering continues
    Booster Bias supplies – First one is done and should be part of the test stand cavity testing
  Booster Shielding – setting up another round of scans – during cavity install & next day
  Booster BPM work – Finishing up specification and documentation, Some parts being ordered
  Booster Nothcer – Working out a logic issue on a monitoring card
    Need about a week of 24/7 running on our TLG system
    Like to connect three loads in gallery to ensure it can work for 700 MeV notching

## Slide 4
Cavities Refurbishment
  10 of 19 cavities have been refurbished
Install refurbished cavity in slot 2
Pull Cavity RF 5 (need to fix taper)
Pull another cavity for refurb?
RF 5 will be removed for repair

## Slide 5: Recent PIP Budget/News
Budget Issues: no news from DOE/Lab meeting
  Another budget meeting in June (after dust settles)
General: Lots of talk about P5 and DOE – PIPII/PIP
PMG – 4/26 has been canceled – Stuart is departing
  Who will replace Stuart – not sure but he has listed PIP as one of his important tasks
Lots of shutdown talk – Regular SD planning
Update of RLS – Some Booster items remain
P5 should report back to lab in April – PIP impact likely
Director is interested in 20 Hz – potential users…..
  Too soon to affect what we are doing
Post-Doc position for PIP is open/receiving resumes

## Slide 6: Upcoming Talks
Future Meetings to be Scheduled:
Peter/Craig – New Booster BPM Plan
Matt/John – New Tuner
Tom Kubicki – New Booster Cavity Plan
Bill Pellico - Loss Scans and Shielding Assessment
John Reid - Solid State Installation - Final Report