## Slide 1: PIP Shutdown Status
9/17/2014

## Slide 2: RIL/Linac Jobs
L1 Transformer
  Rigging complete
  Electrical work started
  Turn on this coming weekend
Laser notcher flange installed
25 cell test on LRF1 will not be performed this shutdown
400MeV vacuum to start after the NTF quad magnet replacement
Dual temp system work to start soon

## Slide 3: Booster Jobs
Anode supply upgrade
  Unlikely to occur this shutdown
Cable pulls for new turbos is completed
  May get a couple of new turbos installed
New sector valve installation
  Depends on other jobs
New east/west yard transformers to be installed weekends of 9/27 & 10/4
S12 corrector & absorber work on schedule for later in the shutdown

## Slide 4: Booster Jobs
TLM shielding work ongoing
  Most cables pulled except 7/8 inch heliax
Kicker maintenance underway
  Replace notcher long kickers to short kickers
Cavity refurbishment underway
  About two weeks out from next cavity change
L1 corrector & NTF work may delay some jobs until next shutdown

## Slide 5: RIL

## Slide 6: L1 Transformer

## Slide 7: Booster Notcher Kickers PS