## Slide 1: PIP Update
Feb 11th 2015

## Slide 2: Agenda
Summary Update
  Current Activities
  Updates (Ken Domann, Bill Robotham, Matt Slabaugh, Trevor Butler)
  Additional Meetings/Notes

## Slide 3: Updates
  Linac
  SBK: Work at CPI continues – discussing testing items/location at CPI – no formal agreement yet.
  LN: Received laser – starting to test, working on vertical beam size issue
  Modulator: Update today
  Utilities: completed – task closed
    Booster
  Beam Studies:
    Cogging: Kiyomi has tried using new system in operations: finishing up support hardware
    Booster optics software –more Beta corrections last week – eff. ~90% (not sure why low)
    Booster Longitudinal dampers –ACNET software ready for testing, damping tests performed…
    Booster BPMs – Peter taking data and working on hardware –
  RF:
    Refurbished cavity work: Another cavity installed last Wed. (#16)
    Cavity # 17 will be given to John for testing this week – install in about two weeks…..
    New Tuners – Talk today
    Bias Supplies: Supply # 5 has been ready for high power testing……needs Johns time
    Anode Supplies: Filling cabinet #1, mounting load disconnect switches then series resistors
      Update next week
    Perpendicular cavity: Regular meetings, progressing on cooling design and ferrite testing
    Stations 20, 21 & 22: starting to ramp up activity on 20th upstairs – Tomlin contracted to help
    Rework of cavities 21 & 22: Need to put together plan – looking at options/floor space
    New cavities: Dialogue with management still ongoing – working on design details
  Shielding: TLMs functioning in tunnel after modifications last shutdown – looking at operations
  Transformer: Waiting for shutdown
  Absorber/Kicker: Completed for now – working on optimizing positions/reduction of losses

## Slide 4
Chart: RF Cavity Refurbishment Projections
| 40973 | 41108 | 41176 | 41226 | 41323 | 41339 | 41383 | 41410 | 41449 | 41516 | 41527 | 41568 | 41605 | 41612 | 41687 | 41722 | 41765 | 41772 | 41842 | 41872 | 41918 | 41969 | 42013 | 42051
Cavity Certified | 1 | 2 | 3 | 4 | 5 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 8 | 9 | 10 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Cavity Decertified | 1 | 2 | 3 | 4 | 5 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 8 | 9 | 10 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Cavity Recertified | 1 | 2 | 3 | 4 | 5 | 4 | 5 | 6 | 7 | 8 | 7 | 8 | 9 | 8 | 9 | 10 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Cavity Number 20 | 12
6 weeks per cavity | 17 | 18 | 19 | 20
7 weeks per cavity | 17 | 18 | 19 | 20
8 weeks per cavity | 17 | 18 | 19 | 20
9 weeks per cavity | 17 | 18 | 19 | 20
10 weeks per cavity | 17 | 18 | 19 | 20
11 weeks per cavity | 17 | 18 | 19 | 20
12 weeks per cavity | 17 | 18 | 19 | 20
Shutdown

## Slide 5: Recent PIP Budget/News
FY15 Budget:
    No updates
Update of RLS – Some Booster items remain
  Mostly cavities related
Meetings to discuss transition PIP to PIP-II continue….
DOE REVIEW of PIP
    Waiting for official document
Ann and company are going through dept. budgets
PIP PMG – March 5th

## Slide 6: Upcoming Talks
Bias Supplies – Pat
Proton Source (PIP) shutdown plan – Joe (next week)
Anode S. – update, testing and install – Ryan (Next Wk)
15 Hz East gallery – John
Laser Notcher – Dave
Cogging – Kiyomi (next week?)
Salah Chaurize – Notch system operations
Keith/Tony – TLM install and operations
Nathan Eddy / Alexei Semenov - Longitudinal Dampers
New Cavities(plans)
Collimator – Status and plans (V. Kapin)
Install of Cavity 21 and 22 (plans)