## Slide 1: BOOSTER STATION 20 Updates
Tom Kubicki
PIP Meeting
20 May 2015

## Slide 2: PROGRESS TO DATE
Plumbing in the Gallery has been completed.
Buss Bar for the FBS is in the penetration
  More Buss Bar has been ordered to be installed during the shutdown. Delivery date 5/27/15.
All gallery equipment (Modulator, Bias Supply, SSD Rack, RMU rack) will be ready for installation. No hold-ups here.
½” Heliax cables have been pre-cut and ends terminated with appropriate connectors. All other cables are here or on order with delivery expected around the beginning of the shutdown.
Plan for relocation of interfering equipment is done.
150kW PA is complete.

## Slide 3: Work to do (Shutdown Work)
  Fabrication of Buss Bar
  Long Buss run in tunnel will require some coordination to move into the tunnel (i.e. many helping hands to carry it).
  Have electricians pull all cables in tunnel and wire in all utilities. Circuit breaker installation and receptacles. Pull Anode PS cable as well.
Phase match all cables to proper electrical lengths.
Install all RF equipment in Gallery once corrector elements are removed.
Alignment and vacuum guys for cavity installation.
New valves for Supply and Return in tunnel installed by water guys.
New Board designed for the Fanback Sum box in the RCC rack.
  Needs to accept Station 20 either as an A or B station.
  Finished with board design, just needs to be ordered.