## Slide 1: Anode Supply Update

## Slide 2: Current Status
Capacitor Bank
  Completely built and hipotted
Diode Bridge
  Built up
  Needs refrigeration tubing connections
  Needs surge arresters mounted
    Mocked one up, the rest of the mounts need to be made
Switch Rack
  Built
  Load up completely by the end of the week
Mount water cooled resistors (1 day)
Wiring (2-3 days, with additional time during install)
Step start cabinet
  Modify second cabinet (2-3 days)
  Install Ross Gear (1 day)
Controls (1 week)

## Slide 3: Current Status