## Slide 1: Status update for BRF20, BRF21 and BRF22
Tom Kubicki
PIP
28 October 2015

## Slide 2: BRF20 Status
Station is up and running!
  Credit and a big thank you from the RF group to all who helped out in assisting with bringing this station online
  RF techs worked especially hard during the shutdown to ensure BRF20 was online ASAP.
    Bus bar fabrication required several pieces and precision machining by RF techs to ensure resistivity of joints is acceptable.
    Many cables were phased matched, all equipment was installed, cabled up, and prepped for operations.
    This was not the only job they had to deal with and they accomplished quite a bit of work during the shutdown. Their hard work and dedication was paramount in achieving this significant milestone.

## Slide 3: BRF20 Issues
Several issues were discovered upon commissioning the station
  All of the cables for BRF20 were cut short ~7.1ns due to network analyzer calibration error.
    Not sure where this arose but speculation is a cable was replaced during cable phasing and was not recalibrated.
    Mixup of the A RF and B RF fanout cables to BRF19’s RMU rack.
    The new switching circuit to convert BRF19B and BRF20A from an A for BRF19 and a B for BRF20 was removed to eliminate a potential source of error.
      Replaced with equivalent electrical length RG58 cables.
  Fanout cable distribution is different relative to other stations
    To keep fanout distribution simpler, cables for BRF19 and BRF20 had to be cut down to ensure the fanout cable from BRF19 that provides the RF input to BRF20 and the RF switch circuitry maintains the same delay down in the tunnel. This ensures BRF19 and BRF20 have the same electrical length down into the tunnel as every other station.
      Fanout for BRF19 and BRF20 was checked and verified correct with a phase detector.
  New fanback board has an issue
    It’s been “fixed” but it’s not the permanent solution. Will need to be looked at during downtime and/or shutdown.

## Slide 4: BRF21 and BRF22 status updates
Room is getting cleared out, not quite done just yet.
Update on civil engineering that needs to be done
  Penetrations for LCW and electrical, cutout of door, wall construction, etc.
  FESS needs a drawing of dimensions to proceed with work.
LCW
  Provided by reclaiming wasted flows. Cost is free.
  200 GPM is available as backup for $60K
  Cheapest LCW option: Finding flow elsewhere
    28GPM: Valve out PEI’s and Klystron in XGW-003B
    30GPM: Gained when bypass closed at end of TG-9
    150-350GPM +/-50GPM: Close bypass at XGW-000 basement, end of tunnel by operator storage room. Flow determined by subtracting supply flow from return flow on large 8” pipe, so error may be large.
    50GPM: Cut flow to both APS skids by half
    160GPM required for BRF21 and BRF22, and the above changes will meet this need.

## Slide 5: BRF21 and BRF22 Status updates
Electrical utility
  Power can be had from Y-L4. Cost is <$15K.
  800KVA required for operation of BRF21 and BRF22, can be met with Y-L4
    Ranson has a good idea how to get AC piped in there
    Requires conduit from APS to modulators to extend into room.
      Need to determine best way to pipe this in with respect to all other LCW pipes, cable trays, and bus bar hangars.
  Cooling
    Each RF station produces 10kW of heat into local environment.
    Requires 70,000BTU/hr of cooling to maintain local ambient temperature.
    Roof mounted AC unit or some other heat exchanger needed.

## Slide 6: BRF21 and BRF22 status updates
One (and only?) choice of penetration by Instrumentation rack.
  Will require opening a hole in the roof to get bus bar in penetration.
    Safest way to do this is with a crane and RF group guiding operator.
    Will have to double up on bus bars in one penetration, be aware of overheating of the busses
  Tunnel bus bar routing is going to require major re-work of existing bus bar for BRF17 and BRF18 to accommodate BRF21 and BRF22
    As it currently stands, the busses BRF17 and BRF18 will interfere with PA installation/removal for BRF21 and BRF22.
    Easiest fix is to add a jog in the bus for BRF17 and BRF18.
      Not trivial, but it can be done.

## Slide 7: BRF21 and BRF22 Equipment needs
Biggest obstacle to meeting deadline for next summer shutdown will be buying parts and fabricating Ferrite Bias Power Supplies.
  RF group will be having internal meetings to check on progress.
  Many custom parts need to be ordered and/or fabricated.
  Inventory of what is available will be carried out in near term (beginning this week hopefully).
  Would be great to get help from other groups once parts and frames begin to come in for building FBS up.
Cavity fabrication will have to be done, fortunately with refurbishment winding down should free up techs for building 2 Booster cavities.
  Any parts required for building cavities needs to get ordered soon.
    Tuners being built or available for these cavities?
Equipment needs
  4 1kw SSD amps (will build 16 for this to have spares)
  2 modulators – Use prototype modulators.
    Have all the parts for modulators
  2 RMU relay racks
    Need HRM digital I/O equipment
  2 FBS Power supplies
  Copper Bus bar material
  Any additional cables (i.e. ½” heliax, okonite, etc.) required not in house.
  2 Booster cavities with tuners
  2 150kW Power Amplifiers
  New MEIU design
    This will replace all the existing MEIU’s in the future

## Slide 8: Additional Comments
Fire safety considerations are easily accommodated.
  Not an impediment
There IS enough room in BGW-124 to accommodate 2 RF stations
  Cooling will have to be addressed
Office space can be preserved.
Cost of water, power, and civil engineering <$90K (R. Tomlin)