## Slide 1: PIP Update
Jan 13th 2016

## Slide 2: Agenda
Summary Update
Additional Meetings/Notes

## Slide 3
  Linac
  SBK: Finishing up final tests – may ship this week or early next
  LN:
  Modulator: 28 cell run on station 1 testing continues – looking to get interlocks in place for unattended running modes. 54 cell progressing in areas where labor is available – Rack work
  Booster
  Beam Studies:
    Booster optics software: several more rounds of beta corrections and early injection capture
      Investigating lower efficiency with corrected beta functions
      Early injection did not increase efficiency but do see slightly better longitudinal emittances
    Booster Longitudinal dampers: Task is done
    Booster BPMs: Transition board done, Timing board still being layed out, Alexei coding digitizer
    Collimators: Ready to install primaries – working with secondary's/positions, simulations continue
    Refurbished cavity:
      Cavity #20: Done
      Station 20, Completed - Completed
      15 Hz: Some operations at higher rep rates - up to 14Hz, users demand/studies not consistent
    New Tuners: # 13 underway
      Ferrite: The last 70 low mu have arrived and going through testing – but so far they look good!
    Bias Supplies: Completed
    Anode Supplies: Completed
    Transformer: Completed
    Perpendicular bias cavity: Meeting tomorrow, machine shop delays, testing of ferrites continues
    Rework of cavities 21 & 22: Preparing to put wide bore on stand (tuners being installed)
    New cavities: Notes later
  Shielding: Tony and Keith – working on documentation
  Absorber/Kicker: Scans and orbit work continues –
  Flux – record hourly and weekly flux last week – pushing 1.7E17 pph

## Slide 4: Recent PIP Budget/News
Budget:
  Reduction of 1.5 M FY16 to cover AD shortfall – still do not know
    Update of RLS to reflect this change
  Replacement cavities schedule being revised (T. Kroc)
Meetings to discuss transition PIP to PIP-II continue
  Not much is happening until budgets are completed and PIP II funds required labor
PIP PMG – Next PMG Feb. 4th – Quarterly report to be provided

## Slide 5
Chart: 
| 41913 | 41944 | 41975 | 42006 | 42037 | 42068 | 42099 | 42130 | 42161 | 42192 | 42223 | 42254 | 42285 | 42316 | 42347 | 42378 | 42409 | 42440 | 42471 | 42502 | 42533 | 42564 | 42595 | 42626
Planned FTEs | 25.2 | 30.1 | 35.4 | 28.2 | 25.5 | 28 | 24.6 | 22.4 | 28.4 | 24.3 | 18.1 | 16.6 | 18.83 | 26.6 | 29.08 | 25.83 | 23.96 | 20.7 | 18.08 | 12.62 | 10.71 | 18.12 | 35.75 | 40.59
Actual FTEs | 26.6 | 24 | 27.7 | 32.9 | 34.8 | 31.7 | 35.7 | 29.3 | 29.5 | 42.2 | 38.3 | 46.7 | 31.8 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 6
Booster Operation Summary Jan 1st – Jan 8th 2016
Total proton: 2.38E19
proton/hour:1.71E17
Eff. : 92%
~$15: 4.7E12 p/p
~$1D: 4.7E12 p/p
~$13: 0.52E12 p/p
Rep. rate : 14Hz

## Slide 7: Upcoming Talks
Keith/Tony – TLM install and operations
New Cavities (plans) Tom Kroc