## Sheet1
Item	quantity	units	cost/unit	cost	Source

Bias Supply					RF Group
Bias Supply Parts	1	each	$80,000	$80,000
Bias Supply Labor	800	Hours	$100	$80,000
						$160,000

Bias Buss
Bias Buss Bar Material	2100	lbs	2.67	$5,607	M. Vincent 030215		online quote
Bias Buss Bar Labor	80	Hours	$100	$8,000
						$13,607

Modulator					RF Group
Modulator Parts	1	each	$60,000	$60,000
Modulator Labor	480	Hours	$100	$48,000
						$108,000

Solid State Driver					RF Group
SSD Parts	1	each	$26,000	$26,000
SSD Labor	400	Hours	$100	$40,000
						$66,000

Item	quantity	units	cost/unit	cost	Source
RF Station cabling in BGW-124
Pull 2 30KV cables from WAPS	1	job	$3,520	$3,520	24 hrs x $110/hr
Okonite + 750V + ground cable	500	feet	$2,500	$2,500	$5/ft
Remove 4 and pull 6 from WAPS	1	job	$7,040	$7,040
Okonite + 750V + ground cable	3000	feet	$15,000	$15,000
Pull RF bundle to tunnel	2	bundles 200'	$1,760	$1,760
RF bundle cable	2	bundles 200'	$9,000	$9,000	~3000' heliax +262	Low		High
						$16,780		$32,800
						2 new feeds		6 new feeds

Item	quantity	units	cost/unit	cost	Source
Upgrade 13.8 transformer Y-L5					R Crawford 031515
1000 KVA transformer	1	each	$72,000	72000					Alternate plan
Install 1000 KVA transformer	1	job	$10,000	10000	RT $6k crane, 2days FESS, 2 days x 2 electricians
1200 A + 600 A panel with breakers	2	each	$6,000	12000	JR upgrade to 1200 A at PHP-L5-1+ 600A in BGW-124
450 ft 4” Conduit + boxes	450	ft	$2,400	2400	RT $5/ft
Power cable	2250	ft	$4,500	4500	RT $2/ft
Pull power Cables	1	job	$3,520	3520	RT 4 men 1 day
						$104,420

Item	quantity	units	cost/unit	cost	Source
Steal power from USS-Y-L3
Move PHP-L4-3 + PHP-L4-3 to DHP—L3-4	1	Job		$3,520		4 man days, $110/hr. Re-use the old cabling
Pull 800 A from DHP-L4-1 to BGW-124	1	Job		$3,520		4 man days, $110/hr.
Cable				$5,000		4” conduit?

									Savings over new 1000 KVA Y-L5
						$12,040				$92,380

Item	quantity	units	cost/unit	cost	Source
LCW to modulator, Bias supply, and SSD
LCW Manifolds	2	each	$6,500	$13,000	Hixson
LCW Manifold labor	80	Hours	$100	$8,000	Hixson
LCW lines to west gallery	1	job +material	$6,000	$6,000	Hixson + Tomlin		Do we need pipefitter?
LCW lines to west gallery labor	80	Hours	$100	$8,000	Hixson

						$35,000

Item	quantity	units	cost/unit	cost	Source
Refurbish Room BGW-124					Scott Crowel

cut hole in gallery ceiling and cover	1	job	$1,000	$1,000
Cutting concrete walls in BGW_124	1	job	$1,500	$1,500
remove unused ICW and fire-water lines	1	job	$1,500	$1,500
Take out old door	1	job	$900	$900
New divider wall and reinstall 36” door	1	job	$1,200	$1,200
Cut back the carpet 6 to 12 inches.	1	job	$400	$400
Remove north, east drywall & studs, paint	1	job	$1,000	$400
Redo the duct work on northside.	1	job	$900	$900
Remove office 120 VAC from room.	1	job	$600	$600
						$8,400
								Pull 6 MV105 Okonites
					Total infrastructure	$72,220		$88,240

					Two RF stations	$695,214		$695,214

					Project total	$767,434	+ 2 cavitys	$783,454	+ 2 cavitys