## Slide 1: PIP Update
Feb 10th 2016

## Slide 2: Agenda
Summary Update
Additional Meetings/Notes
Ken Domann budget controls update
Trevor – Linac Modulator

## Slide 3
  Linac
  SBK: Delivered (working on gallery drawings)
  LN: Working to resolve issue with pulse stability – no splicing done yet….
  Modulator: Update talk
Booster
    Booster optics software: several more rounds of beta corrections and early injection capture
      Investigating lower efficiency with corrected beta functions
    Booster BPMs:
    Instrumentation department busy with Recycler DCCT and other issues – but should now be a point to start some testing….
    Collimators:
    Installed primaries – will start studies next week? Update talk next week.
    RF:
    Waiting for welder to lap on material for Cavity 21 (as of Monday)
    Wide bore Cavity 22 will be re-worked – when time permits
    Tuner 13 tested good – tuner 14 will be completed by end of week – need to ship next set of ferrite
    11 cones completed and pressure tested – waiting for electrical testing
    A requisition for an additional 20 castings?
    Replacement cavity – still working on simulations for perpendicular design and waiting on wide bore tests
    Perpendicular bias cavity: Meeting tomorrow – discuss mechanical assembly/issues
    PA tester nearly ready – test PA at higher frequency
  Shielding: Tony and Keith – running at limit now – Will complete write-up this month
  Absorber/Kicker: Scans and orbit work continues –
  Flux – Running at 1.8E17 pph limit – loss limit not much higher these days

## Slide 4: Present Operations

## Slide 5
Budget:
  Reduction of 1.5 M FY16 to cover AD shortfall – still do not know
    Update of RLS to reflect this change
Meetings to discuss transition PIP to PIP-II put on hold – Steve Holmes
PMG – Feb. 4th – No real comments or concerns
Quarterly report completed – will be release today

## Slide 6: Upcoming Talks
Collimator – Simulations and plans: V Kapin
TLM install and operations: Tony
Shielding assessment: Keith
New Cavities (plans) Tom Kroc