## Slide 1: PIP – General Update Oct 26th 2016
Linac Modulator: Electrical work nearly done – waiting for hardware – move planned for Fri.
Laser Notcher: Setting up small review and ordering parts
Booster Stations 21 & 22: Room is 80% complete – Electrical work will continue when labor available –
Status of RF hardware?
Cavity 21 & 22: Cavity 21 being tested –should be done this week and ready to install – results?
Station 22 in progress – update?
New Tuners: Ferrites all tested and they look good…writing up final report – close task next week.
Booster BPMs: Parts were ordered end of FY16 – not sure of status of testing?
Booster Beam Physics: talk today
Absorber: Finished MARS run – adding to shielding studies – Did some initial scans – more after we start to run to MI/Recycler.
Perpendicular Cavity: Preparing to test Tomco amp, confirming details on solenoid ps,
Shielding Assessment: Preparing final document.

## Slide 2
Should be done this year
Should be done before AAC review in Dec!
5 Tasks remaining 2017

## Slide 3
Upcoming events….
  PMG Nov 3rd – summary of FY16 and FY17 plans
  AAC – will present PIP updates for past year – need to show progress
  Replacement cavity meeting – had first meeting – more to come
  Still no budget table – but hoping for one soon…
  Beam studies still being planned for next couple of week .ie collimators!