2nd Harmonic Cavity Updates
C.Y. Tan
16 Feb 2017

---
Work done and will be done
- Testing of PA at 76 MHz is complete
  - Successfully tested to ~140 kW.
  - Sucessfully tested Tomco SS amplifier.
- Testing of PA at 106 MHz to be done
  - Cavity is scheduled to be completed in mid-March.
  - Expect PA test to be complete by end of March
- Cathode resonator design is being finalized
  - Compromise between 76 MHz and 106 MHz for matching to SS driver.
  - Requires stub tuner for this to work.
    - Low power tests and analytic calculations show that this should work.
- Garnet tests
  - Witness pieces testing continues
    - Testing mechanics, and required computer programs are complete.
    - Initial tests were with amplifier that has insufficient power for garnet degaussing.
    - New amplifier (1.5 kW) has been bought. Testing continues. Expected completion by mid March.
      - New amplifier died on power on. New one on the way.

---
Work done and will be done (cont’d)
- First garnet ring received 11 Jan 2017.
  - Gluing of garnets to alumina had slippage.
    - OD larger by 35 mils and ID’s smaller by 41 mils
  - Next garnet ring should have the above error corrected.

---
Work done and will be done (cont’d)
- Garnet ring test stand
  - Design is complete (~Dec 2016)
  - Parts being procured
    - 1 req has been approved
    - 2 others are in the process, MSV-3917 and 3 Procard orders are in route for approvals.
    - Expect to be all ordered by end of Feb.
- RF windows with brazed copper parts
  - Should be delivered soon …?
- Eddy current calculations to optimize cuts in tuner shell and solenoid ramp effects
  - Completed.
- Solenoid design
  - Finalizing design with mechanical design.
- Bias supply for solenoid
  - Mike Kufer not working on it until g-2 is done. March?
- Mechanical design
  - Work continues to integrate tuner into cavity and solenoid.
  - More meetings to make sure that both Sasha and Kevin are in agreement.

---
IPAC17
- Tan will be going to IPAC17 pending DOE approval.
  - Three papers submitted:
    - Status of the Perpendicular Biased 2nd Harmonic Cavity for the Fermilab Booster
    - Tuner of a Second Harmonic Cavity of the Fermilab Booster
    - Static Magnetization Properties of AL800 Garnet Material