## Rad Mon (2)
Assembly Name | Cost Basis | Cost Estimate | Quantity Needed | Total Cost for Item | Interlock Technician Procurement Time in Hours | Engineering Physicist Procurement Time in Hours | Interlock Tech Assembly Time in Hours per Unit | Total Interlock Tech Assembly Time in Hours | Bench Testing Interlock Technician Time in Hours per unit | Total Bench Testing Interlock Technician Time in Hours
TLM Chassis | 2017 Cost | 1537 | 3 | 4611 | 40 | 1 | 32 | 96 | 8 | 24
TLM Resistor Box | 2014 Cost | 226 | 3 | 678 | 4 | 1 | 3 | 9
TLM Gas System | 2014 Cost | 3281.8 | 1 | 3281.8 | 16 | 1 | 32 | 32
TLM End Cap | 2014 Cost | 84.82 | 6 | 508.92 | 4 | 1 | 1.5 | 9
Radiation Monitor Interface Card 16 | 2016 Cost Est. | 175 | 3 | 525 | 8 | 1 | 12 | 36 | 1 | 3
Andrew HJ-50 Heliax Standard Air Dielectric Cable 7/8" Black PE Jacket Cable 6 Segments, 450 ft. | 2016 Cost | 9.2 | 1265 | 11638 | 2 | 1 |  | 0
RG-58 Green Fermi Stock # 1170-034000 | 2016 Cost | 0.23 | 5000 | 1150 | 1 |  |  | 0
RG-58 Red Fermi Stock # 1170-036000 | 2016 Cost | 0.23 | 3000 | 690 | 1 |  |  | 0
BNC Crimp Type Cable End Tyco 2-5329082-1 Fermi Stock # 1435-285000 | 2016 Cost | 14.81 | 18 | 266.58 | 1 |  |  | 0
SHV Crimp Type Cable End Kings 1705-2 Male Crimp Type Fermi Stock #1435-211000 | 2016 Cost | 11.78 | 6 | 70.68 | 1 |  |  | 0
Copper Tubing 1/4" Soft Refrigeration Coil 50 Ft. Fermi Stock #1065-006000 $0.50 / Foot | 2016 Cost | 0.5 | 1000 | 500 | 1
Totals |  | 5341.37 |  | 23919.98 | 79 | 6 |  | 182 |  | 27
Electrician, Technician, and Engineer costs | Cost per hour | Cost per ft. | Hours | Total | Electrician task manager and electrician time costed as per current T&M rates
Elec Task Manager (1 hr. / 8 hrs. of Electrician Time) | 109.3 | N/A | 23.7188 | 2592.4594
Electrician Time (2 people at 0.15 hours/ft. each) | 199 | N/A | 189.75 | 37760.25
TLM Heliax Mounting hardware ($1.00/ft.) | N/A | 1 | N/A | 1265 | AD will provide primary oversight of installation
Total Technician Time | 91.61 | N/A | 288 | 26383.68
Total Engineer Time | 153.56 | N/A | 6 | 921.36
Totals |  |  |  | 68922.7494
|  |  | Grand Total | 92842.7294