Pre-injector Upgrade Updates
(13 Oct – 27 Oct 2010)
C.Y. Tan
27 Oct 2010

---
Source Status

---
Source News
- HINS wants their source back
  - Priority must be to get the Einzel lens test work done before we return the source.
  - Status of the crowbar circuit – Jim is away.

---
LEBT Status

---
MEBT Status

---
MEBT Problems
- The quads are extremely difficult to make
  - Quads are too long, c.f. 45mm to 70mm and occupied length from 76.2mm to 105mm (1.37x longer).
  - Capture efficiency at the end of DTL1 down from 80% to about 75%. (Presently at 72.5%, still optimising)
  - Good news is that BNL has finally solved their cooling problems. Is this the type of quads that suitable for us?

---
MEBT Problems (cont'd)
- May consider getting rid of MEBT and slapping RFQ right next to the RFQ
  - Perhaps with addition of PMQ quads.
  - Previous calculations show unrealistically large quad strengths (~100 T/m!). Capture 99%!

---
RFQ Status
- Schempp (15 Oct 2010)
  - Will work on correcting the energy so that output energy is 750keV.
  - Copper plating will happen in November.
  - We need drawings!!!!!!
- PA assembly
  - Waiting for new engineer, coming on 01/01/11

---
Test Stand
- Room has been cleaned up.
  - Beam line layout in progress
    - Water – Bob Slazak
    - Electrical – Jim Ranson
- Need to test LEBT before RFQ connection
  - Wires, toroids at the end of the LEBT, same position as the RFQ.
- Design diagnostic line.
- Are drawings from Schempp sufficient to build table?

---
Test Area

---
Instrumentation
Toroids?

---
Safety
When can the beam line layout in test area be done?

---
Controls

---
RFQ reminders
- Schempp is vendor
  - Make sure that the vanes are cleaned! See ISIS email.
    - Some cleaning details supplied by ISIS.
  - Review and verify on site mechanical design and construction (already in contract).