Pre-injector Upgrade Updates
(22 Dec 2010 – 19 Jan 2011)
C.Y. Tan
19 Jan 2011

---
Review in February
- Write up has started.
  - People should start filling up their sections.
- When is it going to happen?

---
Source Status

---
LEBT Status

---
Schemmp has indicated that aperture being so close to the RFQ vanes is not a problem. (12 Jan 2011 phone conversation)

---
RFQ Status
- Copper plating of RFQ housing is complete. (Dec 2010)
- Vanes being machined. (Jan 2011)
- Visit in March (tentative)

---
Vacuum chamber
Tuners
13 Jan 2011

---
MEBT Status

---
MEBT Quads (to be changed)
2.2” core length.
Physical length 3.4” (not 3”)

---
Buncher
Concern about the insertion of grids because it will scratch the copper surface.
Discussion with BNL and Time.

---
MEBT Simulations
Beam is largest horizontally in 2nd doublet.

---
Before 1st doublets
After buncher
End of Tank 1
Before Tank 1
95.5% capture at end of Tank 1

---
Controls
Will have 4 quads
In flux

---
Test Stand
- Room has been cleaned up.
  - Beam line layout in progress
    - Water – Bob Slazak
    - Electrical – Jim Ranson
- Need to test LEBT before RFQ connection
  - Wires, toroids at the end of the LEBT, same position as the RFQ.
- Design diagnostic line.
- Drawings from Schempp are sufficient to build table.

---
Test Area

---
Safety
When can the beam line layout in test area be done?

---
RFQ reminders
- Schempp is vendor
  - Make sure that the vanes are cleaned! See ISIS email.
    - Some cleaning details supplied by ISIS.
  - Review and verify on site mechanical design and construction (already in contract).