Pre-injector Upgrade Updates
(13 Apr 2011 – 27 Apr 2011)
C.Y. Tan
27 Apr 2011

---
News
- Bob Webber gave ok for taking out the HINS source and replacing it with ours.
- New elog for us: http://www-bd.fnal.gov/cgi-mach/machlog.pl?nb=injcom

---
Reminders
- Fill in the MS Project time lines. See Elmie by end of next week
  - Steve Hays
  - Jim Lackey
  - Mike Kucera
  - Dan Bollinger
  - Brian Schupbach
- Fill in paper sections for the review.

---
June
May
July
Aug
Sep
April
Connect to LEBT, Beam test
Connect RFQ
H- testing
H- box
Vacuum, solenoids, controls etc.
New test stand
RFQ delivered
Vacuum test and lower power test
High power test
RFQ built
RFQ stand ready, RFQ driver must be ready
Solenoid delivered
Solenoid power up
Controls and ACNET

---
Source Status

---
LEBT Status

---
Solenoid status
- #1 fiducials added. Stretch wire measurements and Hall probe measurements, having problems with stepper motors etc.
- #2 is potted.
- #3 is potted?? (no info at this time)
- #4 waiting for parts.

---
RFQ Status
Delay in manufacture of electrodes (Most important part!) to Easter week as of 15 Apr.
Got first rod on 20 Apr
Earliest visit date is 8 May.

---
MEBT Status

---
Controls
Deprecated

---
Test Area

---
Safety
When can the beam line layout in test area be done?

---
RFQ reminders
- Schempp is vendor
  - Make sure that the vanes are cleaned! See ISIS email.
    - Some cleaning details supplied by ISIS.
  - Review and verify on site mechanical design and construction (already in contract).