## Slide 1: Proton source shutdown schedule
Mary Convery
12/14/11

## Slide 2: General shutdown info
Still not known whether shutdown starts in March or May (or ?)
Duration driven by ANU work in MI – at least 9 months

## Slide 3: Shutdown scheduling (Linac)
NTF can only be off for ~2 months
  When RFQ is ready (currently on track for May)
  If shutdown starts in May, will disassemble I- while still running
  All RFQ and Linac tunnel work will take place while NTF off
    2 mech support vacuum crews (split Ben’s crew)
    Biggest Linac job is momentum dump sleeve
  Mech support work in Booster will be limited during that time (try to keep BRF cavity refurbishment going)
  Linac gallery work will continue on NTF off days
Figured ~6 months of Linac gallery work (most while NTF on)

## Slide 4: Shutdown scheduling (Booster)
Then ~6 weeks for Booster girder moves for aperture (run beam between moves)
  Will be chances for continuing Booster RF and some Linac work during this time
Then ~6 weeks for commissioning
Penciled in RF cavity swaps for tuner refurbishment roughly every 25 days
  Only real difficulty scheduling will be during RFQ installation
Solid state work can take place basically at its own pace
Still understanding scope of LCW work
  Test stand for cavities may be affected by MI LCW work

## Slide 5: Shutdown schedule
Available from proton source homepage under schedules or
http://www-ad.fnal.gov/proton/protonsched/shutdown2012.html