## Slide 1: PIP Update 3
September 26th, 2012

## Slide 2: L1 Future Plans
Installation is halted until further notice (plan for 2014 shutdown or when needed)
Substation moved to ME-7
  Will be completely assembled and tested
  Program breakers
  Start SCADA programming
Moving forward with hatch installation
  Should have quotes shortly
  Paint tested positive for lead, will need to be dealt with at install
Rewriting specification for transformer to allow for three separate cores
  Design review will be held sometime in the future
Temporary wiring is nearly finished and will remain in place

## Slide 3: MCC-L1-1 Install
Installation will take place shortly
MCC will be moved downstairs sometime in October
Power will be shut off by the end of the week
  DHP-L2-2 will be taken down
  MCC
    No air conditioning
    Temporary sump pump
    Overhead Crane
    Hydraulic lift
Internal control wiring
  Completed in advance
  Electricians only need to connect 480V and some 120V circuits
    Should be a 1 day install

## Slide 4: Booster MCC
Universal Specification written
  Can be used in West or East side
Will not be a SmartStart (LINAC MCC)
  PLC and HMI will be purchased later
  Programmed in house
Will not be purchased this year

## Slide 5: Booster Substation
Contract awarded to Federal Pacific
  9/13/12
  $152,370
Extra transformer ordered
  9/25/12
  $55,254
When Booster substation replaced all oil filled transformers for Booster will be replaced with dry-type
Expect substation and transformer around Jan. or Feb.
  Federal is going to try and get them to us by the end of the year
    Siemens switchgear will likely make this impossible

## Slide 6: Booster Anode Supply
Awaiting performance requirements
Design will begin in October
Install will occur 2014 fiscal year
Steve Hays and I will be visiting a pump house manufacturer in the near future to assess their capability of producing the anode supply