## Slide 1
Refurbished Booster RF
John Reid
December 12, 2012

## Slide 2: 4 Booster Cavities Refurbished to Date
  S/N 2002 – Removed St 8 – August 2011 ?
    Refurbishment started – August 26, 2011
    Refurbishment completed – February 2012
    Electrical testing completed – March 5, 2012
    Installed in tunnel – April 2, 20212
  S/N 1011 – Removed St 7 – May 21, 2012
    Refurbishment started
    Refurbishment completed – June 6, 2012
    Electrical testing completed – July 18, 2012
    Installed in tunnel -
  S/N 1008 –Removed St 5 – June 14, 2012
    Refurbishment started June 2012
    Refurbishment completed Sept 6, 2012
    Electrical testing completed Sept 24, 2012
    Installed in tunnel – November 14, 2012
  S/N 1017 – Removed St 6 – June 14, 2012
    Refurbishment started – September 17, 2012
    Refurbishment completed – October 29, 2012
    Electrical testing completed – November 13, 2012
    Installed in tunnel – November 14, 2012

## Slide 3: Summary
Cavity S/N | Radiation | Tin Shims | Rework | Cone Cooling | Vacuum
 | Class | 0.005 | Flanges | Config | Work
2002 | 2 | Yes | No | Parallel | Yes
1011 | 3 | Yes | 3 | Series | No
1008 | 3 | Yes | 3 | Series | No
1017 | 2 | Yes | 3 | Series | No

## Slide 4: Tuner Stem Temperatures
Cavity S/N | Cavity running on standard Booster curve at 15 Hz |  |  |  | 
 | Tuner | Anode | Anode | Anode | Anode
 | Stem Temp F | 15 kV | 18kV | 21 kV | 23.5 kV
2002 |  |  |  |  | 
 | Back - Label | 130 | 140 | 160 | 160
 | Back - Probe | 124 | 138 | 155 | 165
 | Bottom - Label | 130 | 150 | 160 | 190
 | Bottom - Probe | 117 | 143 | 138 | 170
 | Front - Label | 130 | 140 | 160 | 180
 | Front Probe | 124 | 138 | 155 | 163
1011 |  |  |  |  | 
 | Back - Label | 130 | 130 | 150 | 160
 | Back - Probe | 120 | 131 | 141 | 150
 | Bottom - Label | 130 | 130 | 150 | 150
 | Bottom - Probe | 112 | 121 | 136 | 142
 | Front - Label | 130 | 130 | 150 | 160
 | Front Probe | 119 | 131 | 133 | 146
1008 |  |  |  |  | 
 | Back - Label | 130 | 130 | 150 | 160
 | Back - Probe | 120 | 128.5 | 144 | 150
 | Bottom - Label | 130 | 135 | 150 | 170
 | Bottom - Probe | 119 | 124.5 | 142 | 145
 | Front - Label | 130 | 140 | 160 | 170
 | Front Probe | 122 | 129 | 148 | 154
1017 |  |  |  |  | 
 | Back - Label | 115 | 130 | 140 | 150
 | Back - Probe | 115 | 124 | 135 | 140
 | Bottom - Label | 110 | 115 | 130 | 130
 | Bottom - Probe | 104 | 110 | 120 | 120
 | Front - Label | 115 | 130 | 130 | 150
 | Front Probe | 112 | 116 | 124 | 132

## Slide 5
Fitting stem to cavity center flange

## Slide 7
Stem to cavity interface problem
Area marked where stem does not fully contact cavity surface

## Slide 8
Finished flange after resurfacing
Partial flange facing
Added weld material to flange surface

## Slide 9
Original cavity flange surface
Added weld material to flange surface
Finished flange after resurfacing

## Slide 10
Original cavity flange surface
Added weld material to flange area
Finished flange after resurfacing

## Slide 11
Finished mating Flange on Cavity
Finished tuner Flange

## Slide 12: CONCLUSION
4 Cavities refurbished, tested, & installed
Between 50 % to 70 % of the cones had to be stripped and rebuilt due to burnt or damaged fingers.
Cavities from stations 1 and 3 (which will be cavities 5 & 6 to be refurbished) have been pulled from beam line and are waiting to be worked on.