## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variances
Cryo AIP Total |  |  |  | 3395359 | 3319975 | -75384
A1301.03 Cryo Basic Engineering | A1301.03 |  | Cryo Basic Engineering | 217233.26 | 228144.41 | 10911.15
2832 Basic Engineering OS | A1301.03 | 2832 | Basic Engineering OS | 147853.99 | 158765.14 | 10911.15
A1301.04.01 Cryo LN2 system | A1301.04.01 |  | Cryo LN2 system | 326427.37 | 325181.54 | -1245.83
2499 Outdoor Installation - LN2 System | A1301.04.01 | 2499 | Outdoor Installation - LN2 System | 94683.3 | 93437.47 | -1245.83
A1301.04.03 Cryo ODH system | A1301.04.03 |  | Cryo ODH system | 42259.86 | 41339.31 | -920.55
2583 Install ODH Equipment | A1301.04.03 | 2583 | Install ODH Equipment | 3682.22 | 2761.67 | -920.55
A1301.04.04 Cryo Refrigerator System | A1301.04.04 |  | Cryo Refrigerator System | 979009.37 | 911154.63 | -67854.74
2733 Refrig Syst Painting - Prep Req & Process PO | A1301.04.04 | 2733 | Refrig Syst Painting - Prep Req & Process PO | 343.86 | 393.78 | 49.92
2735 Refrig Syst Painting T&M | A1301.04.04 | 2735 | Refrig Syst Painting T&M | 0 | 43374.42 | 43374.42
2845 Refrig Syst DCS Detailed Engineering | A1301.04.04 | 2845 | Refrig Syst DCS Detailed Engineering | 64262.08 | 55567.8 | -8694.28
2850 Refrigeration Syst g-2 Valve Box Installation | A1301.04.04 | 2850 | Refrigeration Syst g-2 Valve Box Installation | 23505.84 | 16454.09 | -7051.75
2860 Refrigeration Syst Transfer Lines Installation | A1301.04.04 | 2860 | Refrigeration Syst Transfer Lines Installation | 83164.07 | 41582.04 | -41582.03
2861 Refrigeration Syst g-2 Transfer Lines Checkout | A1301.04.04 | 2861 | Refrigeration Syst g-2 Transfer Lines Checkout | 17338.75 | 0 | -17338.75
2872 Refrigeration Syst g-2 Test Box Installation | A1301.04.04 | 2872 | Refrigeration Syst g-2 Test Box Installation | 11025.77 | 5512.88 | -5512.89
2875 Refrigeration Syst Safety Documents | A1301.04.04 | 2875 | Refrigeration Syst Safety Documents | 3969.13 | 0 | -3969.13
2879 Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | A1301.04.04 | 2879 | Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | 17113.67 | 7400.51 | -9713.16
2892 Refrig Syst - 2nd DCS Delivery Received | A1301.04.04 | 2892 | Refrig Syst - 2nd DCS Delivery Received | 9713.16 | 11100.76 | 1387.6
2909 Refrigeration Syst Mu2e Valve Box Installation | A1301.04.04 | 2909 | Refrigeration Syst Mu2e Valve Box Installation | 18804.67 | 0 | -18804.67
A1301.04.05 Cryo Compressor System | A1301.04.05 |  | Cryo Compressor System | 390551.32 | 418695.36 | 28144.04
1161 Compressor Syst - T&M | A1301.04.05 | 1161 | Compressor Syst - T&M | 24861.75 | 33823.54 | 8961.79
856 Compressor Syst Controls | A1301.04.05 | 856 | Compressor Syst Controls | 39377.75 | 35439.97 | -3937.78
858 Compressor Syst Paint vessels & base | A1301.04.05 | 858 | Compressor Syst Paint vessels & base | 34092.23 | 57212.25 | 23120.02
A1301.04.06 Cryo Interconnect Piping | A1301.04.06 |  | Cryo Interconnect Piping | 718187.8 | 737933.91 | 19746.11
2692 OS of Interconnect piping - A0 to MC-1 Discharge & Suction Header | A1301.04.06 | 2692 | OS of Interconnect piping - A0 to MC-1 Discharge & Suction Header | 216647.31 | 236393.41 | 19746.1
A1301.04.07 Cryo Interconnect Electrical & Controls | A1301.04.07 |  | Cryo Interconnect Electrical & Controls | 166153.66 | 150402.56 | -15751.1
2697 Interconnect Electrical & Controls Engineering | A1301.04.07 | 2697 | Interconnect Electrical & Controls Engineering | 78755.5 | 63004.4 | -15751.1
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 21433.29 | 5398.01 | -16035.28
2698 Mu2e Interface - Basic Engineering | A1301.05.01 | 2698 | Mu2e Interface - Basic Engineering | 21433.29 | 5398.01 | -16035.28
A1301.06 Cryo Safety Documents | A1301.06 |  | Cryo Safety Documents | 125096.85 | 92718.84 | -32378.01
1126 Cryo Safety Documents | A1301.06 | 1126 | Cryo Safety Documents | 125096.85 | 92718.84 | -32378.01