## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryp AIP |  |  |  | 3672940.7588 | 3713361.1561 | 40420.3973
A1301.03 Cryo Basic Engineering | A1301.03 |  | Cryo Basic Engineering | 235088.8 | 234545.02 | -543.78
2832 Basic Engineering OS | A1301.03 | 2832 | Basic Engineering OS | 165709.53 | 165165.75 | -543.78
A1301.04.03 Cryo ODH system | A1301.04.03 |  | Cryo ODH system | 46383.64 | 44134.3 | -2249.34
2583 Install ODH Equipment | A1301.04.03 | 2583 | Install ODH Equipment | 7806 | 5556.67 | -2249.33
A1301.04.04 Cryo Refrigerator System | A1301.04.04 |  | Cryo Refrigerator System | 1117502.38 | 1164822.59 | 47320.21
1375 Refrig Syst Expanders Installation | A1301.04.04 | 1375 | Refrig Syst Expanders Installation | 19211.19 | 15368.95 | -3842.24
2735 Refrig Syst Painting T&M | A1301.04.04 | 2735 | Refrig Syst Painting T&M | 0 | 43374.42 | 43374.42
2845 Refrig Syst DCS Detailed Engineering | A1301.04.04 | 2845 | Refrig Syst DCS Detailed Engineering | 72022.67 | 71634.64 | -388.03
2851 Refrigeration Syst Valve Box Checkout | A1301.04.04 | 2851 | Refrigeration Syst Valve Box Checkout | 3104.24 | 3161.66 | 57.42
2856 Refrigeration Syst AP-10 Bayonet Can Checkout | A1301.04.04 | 2856 | Refrigeration Syst AP-10 Bayonet Can Checkout | 8084.25 | 8488.46 | 404.21
2872 Refrigeration Syst g-2 Test Box Installation | A1301.04.04 | 2872 | Refrigeration Syst g-2 Test Box Installation | 11025.77 | 8269.33 | -2756.44
2875 Refrigeration Syst Safety Documents | A1301.04.04 | 2875 | Refrigeration Syst Safety Documents | 8450.87 | 8239.01 | -211.86
2879 Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | A1301.04.04 | 2879 | Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | 27405.99 | 56112.47 | 28706.48
2892 Refrig Syst - 2nd DCS Delivery Received | A1301.04.04 | 2892 | Refrig Syst - 2nd DCS Delivery Received | 20005.48 | 19724.78 | -280.7
2910 Refrigeration Syst Mu2e Transfer Lines Checkout | A1301.04.04 | 2910 | Refrigeration Syst Mu2e Transfer Lines Checkout | 17798.23 | 0 | -17798.23
2913 Refrig Syst Electrical - Installation (T&M Oversight) Phase 2 | A1301.04.04 | 2913 | Refrig Syst Electrical - Installation (T&M Oversight) Phase 2 | 11032.17 | 11087.33 | 55.16
A1301.04.05 Cryo Compressor System | A1301.04.05 |  | Cryo Compressor System | 405632.78 | 426592.21 | 20959.43
1161 Compressor Syst - T&M | A1301.04.05 | 1161 | Compressor Syst - T&M | 31322.18 | 37782.61 | 6460.43
858 Compressor Syst Paint vessels & base | A1301.04.05 | 858 | Compressor Syst Paint vessels & base | 42713.26 | 57212.25 | 14498.99
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 38871.34 | 38110.8 | -760.54
2700 Mu2e Interface - Detailed Engineering | A1301.05.01 | 2700 | Mu2e Interface - Detailed Engineering | 6844.84 | 6084.3 | -760.54
A1301.06 Cryo Safety Documents | A1301.06 |  | Cryo Safety Documents | 140204.13 | 115898.55 | -24305.58
1126 Cryo Safety Documents | A1301.06 | 1126 | Cryo Safety Documents | 140204.13 | 115898.55 | -24305.58