## Report
|  |  |  | CONTRACT PERFORMANCE REPORT | [8 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [7 empty] | Dollars | OMB No. 0704-0188 (modified)
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM |  |  | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME |  |  | a. FROM (YYYYMMDD) |  | 2014-08-01
[9 empty] | Cryogenics AIP |  |  | b. TO (YYYYMMDD) |  | 2014-08-31
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  | g. CONTRACT CEILING |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 9737269.01 | 0 |  | 0 |  | 9737269.01 |  | 9737269.01 |  | 9737269.01
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. SCHED PERFORM/COST PERFORM INDEX |  |  |  | 8. CONTINGENCY (on remaining)
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | SPI = | 1.0053
|  | AT COMPLETION |  | BASE |  |  |  | CPI = | 1.0342 |  |  | Cont % = | 80.93%
|  | 7093869 |  | 7141990.6591 |  | 48121.6591
9. PERFORMANCE DATA
Control Account.WBS (1) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE |  |  |  |  | AT COMPLETION
Control Account.WBS (2) |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED | ESTIMATED | VARIANCE
CTC |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (14) | (15) | (16)
Cryo1 Muon Campus Cryogenics - AIP |  | 241198.3349 | 221660.3786 | 236857.1 | -19537.9563 | -15196.7214 | 3914139.0936 | 3935021.5348 | 3804958.27 | 20882.4412 | 130063.2648 | 7141990.6591 | 7093869 | 48121.6591
Cryo1.02 Cryo Project Management |  | 11288.0796 | 11288.0796 | 7316.9 | 0 | 3971.1796 | 176434.6101 | 176434.6101 | 113492.14 | 0 | 62942.4701 | 599014.8935 | 550893 | 48121.8935
A1301.02.01.01 Cryo AIP Gen Proj OS - FY13 |  | 0 | 0 | 0 | 0 | 0 | 51346.4223 | 51346.4223 | 43225.82 | 0 | 8120.6023 | 51346.4223 | 43225 | 8121.4223
A1301.02.01.02 Cryo AIP Gen Proj OS - FY14 |  | 11288.0796 | 11288.0796 | 7316.9 | 0 | 3971.1796 | 125088.1878 | 125088.1878 | 70266.32 | 0 | 54821.8678 | 133151.1019 | 93151 | 40000.1019
A1301.02.01.03 Cryo AIP Gen Proj OS - FY15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140082.261 | 140082.261 | 0
A1301.02.01.04 Cryo AIP Gen Proj OS - FY16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144212.2686 | 144212.2686 | 0
A1301.02.01.05 Cryo AIP Gen Proj OS - FY17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130222.8397 | 130222.8397 | 0
Cryo1.03 Cryo Basic Engineering |  | 17043.9274 | 18334.3962 | 18235.93 | 1290.4688 | 98.4662 | 252132.7305 | 252879.4169 | 269285.25 | 746.6864 | -16405.8331 | 486481.206 | 486481.206 | 0
A1301.03 Cryo Basic Engineering |  | 17043.9274 | 18334.3962 | 18235.93 | 1290.4688 | 98.4662 | 252132.7305 | 252879.4169 | 269285.25 | 746.6864 | -16405.8331 | 486481.206 | 486481.206 | 0
Cryo1.04 Cryogenic plant sub systems |  | 182474.4425 | 176419.0094 | 197446.93 | -6055.4331 | -21027.9206 | 3248905.4682 | 3308880.3343 | 3289224.02 | 59974.8661 | 19656.3143 | 3799815.1423 | 3799815.1423 | 0
A1301.04.01 LN2 system |  | 54066.6612 | 56769.9943 | 26509.32 | 2703.3331 | 30260.6743 | 410825.54 | 413528.8731 | 318793.19 | 2703.3331 | 94735.6831 | 413528.8731 | 413528.8731 | 0
A1301.04.02 Gas management system |  | 0 | 0 | 0 | 0 | 0 | 236065.7847 | 236065.7847 | 209827.85 | 0 | 26237.9347 | 236065.7847 | 236065.7847 | 0
A1301.04.03 ODH system |  | 3373.998 | 5623.33 | 1010.32 | 2249.332 | 4613.01 | 49757.6345 | 49757.6345 | 38615.08 | 0 | 11142.5545 | 49757.6345 | 49757.6345 | 0
A1301.04.04 Cryo Refrigerator system |  | 110637.8458 | 114025.6851 | 148005.08 | 3387.8393 | -33979.3949 | 1228140.2296 | 1278848.2706 | 1485987.2 | 50708.041 | -207138.9294 | 1769783.0785 | 1769783.0785 | 0
A1301.04.05 Cryo Compressor System |  | 14395.9375 | 0 | 5206.45 | -14395.9375 | -5206.45 | 420028.7163 | 426592.2083 | 424140.31 | 6563.492 | 2451.8983 | 426592.2084 | 426592.2084 | 0
A1301.04.06 Cryo Interconnect Piping |  | 0 | 0 | -2117.34 | 0 | 2117.34 | 737933.9081 | 737933.9081 | 583464.15 | 0 | 154469.7581 | 737933.9081 | 737933.9081 | 0
A1301.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 18833.1 | 0 | -18833.1 | 166153.655 | 166153.655 | 228396.24 | 0 | -62242.585 | 166153.655 | 166153.655 | 0
Cryo1.05 Experiment interfaces |  | 15971.2963 | 0 | 0 | -15971.2963 | 0 | 82041.5621 | 65309.728 | 25166.4 | -16731.8341 | 40143.328 | 1720729.0944 | 1720729.0944 | 0
A1301.05.01 Mu2e Interface Connection |  | 15971.2963 | 0 | 0 | -15971.2963 | 0 | 54842.6381 | 38110.804 | 0 | -16731.8341 | 38110.804 | 1693530.1704 | 1693530.1704 | 0
A1301.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 27198.924 | 0
Cryo1.06 Cryo Safety Documents |  | 14420.5891 | 15618.8934 | 13857.34 | 1198.3043 | 1761.5534 | 154624.7227 | 131517.4455 | 107790.46 | -23107.2772 | 23726.9855 | 155311.4174 | 155311.4174 | 0
A1301.06 Cryo Safety Documents |  | 14420.5891 | 15618.8934 | 13857.34 | 1198.3043 | 1761.5534 | 154624.7227 | 131517.4455 | 107790.46 | -23107.2772 | 23726.9855 | 155311.4174 | 155311.4174 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151583.0371 | 151583.0371 | 0
A1301.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151583.0371 | 151583.0371 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122290.7136 | 122290.7136 | 0
A1301.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122290.7136 | 122290.7136 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106765.1548 | 106765.1548 | 0
A1301.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106765.1548 | 0 | 106765.1548
a. SUBTOTAL |  | 241198.3349 | 221660.3786 | 236857.1 | -19537.9563 | -15196.7214 | 3914139.0936 | 3935021.5348 | 3804958.27 | 20882.4412 | 130063.2648 | 7141990.6591 | 7093869 | 48121.6591
b. MANAGEMENT RESERVE | [11 empty] | 2595278.36
c. TOTAL |  | 241198.3349 | 221660.3786 | 236857.1 | -19537.9563 | -15196.7214 | 3914139.0936 | 3935021.5348 | 3804958.27 | 20882.4412 | 130063.2648 | 9737269.0191

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | (YYYYMMDD) | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {CostProject.Fee} |  | {=Cell[R,C-5]+ Cell[R,C-2]} |  | {=Cell[R+7,C-6]+Cell[R,C-4]} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16)
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | f. MANAGEMENT RESERVE | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]-Cell[R-1,C]} |  | {=Cell[R-3,C]-Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2014-07-31 | PREVIOUS | 11752
2014-08-31 | TODATE | 168
2024-09-30 | ATCOMPLETE | 20280

## Data
Control Account.WBS (1) | Control Account.WBS (2) | CTC | Summary Code | Cost Set | Date | Value | Currency
|  |  | O | Budget | 2014-07-31 | 1239320.5947 | TRUE
|  |  | O | Budget | 2014-08-31 | 99300.4576 | TRUE
|  |  | O | Budget | 2024-09-30 | 1217255.4353 | TRUE
|  |  | O | Earned | 2014-07-31 | 1233372.3831 | TRUE
|  |  | O | Earned | 2014-08-31 | 96811.7965 | TRUE
|  |  | O | Actuals | 2014-07-31 | 1263054 | TRUE
|  |  | O | Actuals | 2014-08-31 | 102593.98 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Budget | 2014-07-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Earned | 2014-07-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Actuals | 2014-07-31 | 43225.82 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Budget | 2014-07-31 | 113800.1082 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Budget | 2014-08-31 | 11288.0796 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Budget | 2024-09-30 | 8062.9141 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Earned | 2014-07-31 | 113800.1082 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Earned | 2014-08-31 | 11288.0796 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Actuals | 2014-07-31 | 62949.42 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Actuals | 2014-08-31 | 7316.9 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Budget | 2024-09-30 | 140082.261 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.04 |  | Budget | 2024-09-30 | 144212.2686 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.05 |  | Budget | 2024-09-30 | 130222.8397 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Budget | 2014-07-31 | 235088.8031 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Budget | 2014-08-31 | 17043.9274 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Budget | 2024-09-30 | 234348.4755 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Earned | 2014-07-31 | 234545.0207 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Earned | 2014-08-31 | 18334.3962 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Actuals | 2014-07-31 | 251049.32 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Actuals | 2014-08-31 | 18235.93 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Budget | 2014-07-31 | 356758.8788 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Budget | 2014-08-31 | 54066.6612 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Budget | 2024-09-30 | 2703.3331 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Earned | 2014-07-31 | 356758.8788 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Earned | 2014-08-31 | 56769.9943 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Actuals | 2014-07-31 | 292283.87 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Actuals | 2014-08-31 | 26509.32 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Budget | 2014-07-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Earned | 2014-07-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Actuals | 2014-07-31 | 209827.85 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Budget | 2014-07-31 | 46383.6365 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Budget | 2014-08-31 | 3373.998 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Earned | 2014-07-31 | 44134.3045 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Earned | 2014-08-31 | 5623.33 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Actuals | 2014-07-31 | 37604.76 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Actuals | 2014-08-31 | 1010.32 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2014-07-31 | 1117502.3838 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2014-08-31 | 110637.8458 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2024-09-30 | 541642.8489 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Earned | 2014-07-31 | 1164822.5855 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Earned | 2014-08-31 | 114025.6851 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Actuals | 2014-07-31 | 1337982.12 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Actuals | 2014-08-31 | 148005.08 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Budget | 2014-07-31 | 405632.7788 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Budget | 2014-08-31 | 14395.9375 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Budget | 2024-09-30 | 6563.4921 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Earned | 2014-07-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Actuals | 2014-07-31 | 418933.86 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Actuals | 2014-08-31 | 5206.45 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Budget | 2014-07-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Earned | 2014-07-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Actuals | 2014-07-31 | 585581.49 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Actuals | 2014-08-31 | -2117.34 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Budget | 2014-07-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Earned | 2014-07-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Actuals | 2014-07-31 | 209563.14 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Actuals | 2014-08-31 | 18833.1 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2014-07-31 | 38871.3418 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2014-08-31 | 15971.2963 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2024-09-30 | 1638687.5323 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Earned | 2014-07-31 | 38110.804 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Budget | 2014-07-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Earned | 2014-07-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Actuals | 2014-07-31 | 25166.4 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Budget | 2014-07-31 | 140204.1336 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Budget | 2014-08-31 | 14420.5891 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Budget | 2024-09-30 | 686.6947 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Earned | 2014-07-31 | 115898.5521 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Earned | 2014-08-31 | 15618.8934 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Actuals | 2014-07-31 | 93933.12 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Actuals | 2014-08-31 | 13857.34 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Budget | 2024-09-30 | 151583.0371 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Budget | 2024-09-30 | 122290.7136 | TRUE
Cryo1 | Cryo1.09 | A1301.09 |  | Budget | 2024-09-30 | 106765.1548 | TRUE