## Report
|  |  |  | CONTRACT PERFORMANCE REPORT | [8 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [7 empty] | Dollars | OMB No. 0704-0188 (modified)
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM |  |  | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME |  |  | a. FROM (YYYYMMDD) |  | 2014-09-01
[9 empty] | Cryogenics AIP |  |  | b. TO (YYYYMMDD) |  | 2014-09-30
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  | g. CONTRACT CEILING |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 9737269.01 | 0 |  | 0 |  | 9737269.01 |  | 9737269.01 |  | 9737269.01
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. SCHED PERFORM INDEX/COST PERFORM INDEX |  |  |  | 8. CONTINGENCY (on remaining)
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | SPI = | 1.0001
|  | AT COMPLETION |  | BASE |  |  |  | CPI = | 1.0171 |  |  | Cont % = | 90.1%
|  | 6968452 |  | 7034404.6467 |  | 65952.6467
9. PERFORMANCE DATA
Control Account.WBS (1) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE |  |  |  |  | AT COMPLETION
Control Account.WBS (2) |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED | ESTIMATED | VARIANCE
Control Account.WBS (3) |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK
Control Account.WBS |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (14) | (15) | (16)
Cryo1 Muon Campus Cryogenics - AIP |  | 120126.927 | 99465.5543 | 161740.49 | -20661.3727 | -62274.9357 | 4034266.0208 | 4034487.0892 | 3966698.76 | 221.0684 | 67788.3292 | 7034404.6467 | 6968452 | 65952.6467
Cryo1.02 Cryo Project Management |  | 10196.9836 | 10196.9836 | 5232.6 | 0 | 4964.3836 | 186631.5938 | 186631.5938 | 118724.74 | 0 | 67906.8538 | 491428.881 | 425476 | 65952.881
Cryo1.02.01 Gen Proj OS |  | 10196.9836 | 10196.9836 | 5232.6 | 0 | 4964.3836 | 186631.5938 | 186631.5938 | 118724.74 | 0 | 67906.8538 | 491428.881 | 425476 | 65952.881
Cryo1.02.01.01 Cryo AIP Gen Proj OS - FY13 |  | 0 | 0 | 15.33 | 0 | -15.33 | 51346.4223 | 51346.4223 | 43241.15 | 0 | 8105.2723 | 51346.4223 | 43241 | 8105.4223
Cryo1.02.01.02 Cryo AIP Gen Proj OS - FY14 |  | 8062.9141 | 8062.9141 | 5037.34 | 0 | 3025.5741 | 133151.102 | 133151.102 | 75303.66 | 0 | 57847.442 | 133151.102 | 75304 | 57847.102
Cryo1.02.01.03 Cryo AIP Gen Proj OS - FY15 |  | 2134.0695 | 2134.0695 | 179.93 | 0 | 1954.1395 | 2134.0695 | 2134.0695 | 179.93 | 0 | 1954.1395 | 32496.2484 | 32496.2484 | 0
Cryo1.02.01.04 Cryo AIP Gen Proj OS - FY16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144212.2686 | 144212.2686 | 0
Cryo1.02.01.05 Cryo AIP Gen Proj OS - FY17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130222.8397 | 130222.8397 | 0
Cryo1.03 Cryo Basic Engineering |  | 17043.9274 | 16297.2411 | 9605.45 | -746.6863 | 6691.7911 | 269176.6581 | 269176.658 | 278890.7 | -0.0001 | -9714.042 | 486481.2062 | 486481.2062 | 0
Cryo1.03 Cryo Basic Engineering |  | 17043.9274 | 16297.2411 | 9605.45 | -746.6863 | 6691.7911 | 269176.6581 | 269176.658 | 278890.7 | -0.0001 | -9714.042 | 486481.2062 | 486481.2062 | 0
Cryo1.03 Cryo Basic Engineering |  | 17043.9274 | 16297.2411 | 9605.45 | -746.6863 | 6691.7911 | 269176.6581 | 269176.658 | 278890.7 | -0.0001 | -9714.042 | 486481.2062 | 486481.2062 | 0
Cryo1.04 Cryogenic plant sub systems |  | 64259.523 | 37208.8556 | 137221.53 | -27050.6674 | -100012.6744 | 3313164.991 | 3346089.1899 | 3426445.55 | 32924.1989 | -80356.3601 | 3799815.1421 | 3799815.1421 | 0
Cryo1.04.01 LN2 system |  | 2703.3331 | 0 | 9625.84 | -2703.3331 | -9625.84 | 413528.8731 | 413528.8731 | 328419.03 | 0 | 85109.8431 | 413528.8731 | 413528.8731 | 0
Cryo1.04.01 LN2 system |  | 2703.3331 | 0 | 9625.84 | -2703.3331 | -9625.84 | 413528.8731 | 413528.8731 | 328419.03 | 0 | 85109.8431 | 413528.8731 | 413528.8731 | 0
Cryo1.04.02 Gas management system |  | 0 | 0 | -2559.58 | 0 | 2559.58 | 236065.7847 | 236065.7847 | 207268.27 | 0 | 28797.5147 | 236065.7847 | 236065.7847 | 0
Cryo1.04.02 Gas management system |  | 0 | 0 | -2559.58 | 0 | 2559.58 | 236065.7847 | 236065.7847 | 207268.27 | 0 | 28797.5147 | 236065.7847 | 236065.7847 | 0
Cryo1.04.03 ODH system |  | 0 | 0 | 2481.75 | 0 | -2481.75 | 49757.6345 | 49757.6345 | 41096.83 | 0 | 8660.8045 | 49757.6345 | 49757.6345 | 0
Cryo1.04.03 ODH system |  | 0 | 0 | 2481.75 | 0 | -2481.75 | 49757.6345 | 49757.6345 | 41096.83 | 0 | 8660.8045 | 49757.6345 | 49757.6345 | 0
Cryo1.04.04 Cryo Refrigerator system |  | 54992.6978 | 37208.8556 | 131970.9 | -17783.8422 | -94762.0444 | 1283132.9274 | 1316057.1262 | 1617958.1 | 32924.1988 | -301900.9738 | 1769783.0785 | 1769783.0785 | 0
Cryo1.04.04 Cryo Refrigerator system |  | 54992.6978 | 37208.8556 | 131970.9 | -17783.8422 | -94762.0444 | 1283132.9274 | 1316057.1262 | 1617958.1 | 32924.1988 | -301900.9738 | 1769783.0785 | 1769783.0785 | 0
Cryo1.04.05 Cryo Compressor System |  | 6563.4921 | 0 | -7148.27 | -6563.4921 | 7148.27 | 426592.2082 | 426592.2083 | 416992.04 | 0.0001 | 9600.1683 | 426592.2082 | 426592.2082 | 0
Cryo1.04.05 Cryo Compressor System |  | 6563.4921 | 0 | -7148.27 | -6563.4921 | 7148.27 | 426592.2082 | 426592.2083 | 416992.04 | 0.0001 | 9600.1683 | 426592.2082 | 426592.2082 | 0
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | -7015.97 | 0 | 7015.97 | 737933.9081 | 737933.9081 | 576448.18 | 0 | 161485.7281 | 737933.9081 | 737933.9081 | 0
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | -7015.97 | 0 | 7015.97 | 737933.9081 | 737933.9081 | 576448.18 | 0 | 161485.7281 | 737933.9081 | 737933.9081 | 0
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 9866.86 | 0 | -9866.86 | 166153.655 | 166153.655 | 238263.1 | 0 | -72109.445 | 166153.655 | 166153.655 | 0
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 9866.86 | 0 | -9866.86 | 166153.655 | 166153.655 | 238263.1 | 0 | -72109.445 | 166153.655 | 166153.655 | 0
Cryo1.05 Experiment interfaces |  | 15971.2963 | 0 | 0 | -15971.2963 | 0 | 98012.8585 | 65309.728 | 25166.4 | -32703.1305 | 40143.328 | 1720729.0945 | 1720729.0945 | 0
Cryo1.05.01 Mu2e Interface Connection |  | 15971.2963 | 0 | 0 | -15971.2963 | 0 | 70813.9345 | 38110.804 | 0 | -32703.1305 | 38110.804 | 1693530.1705 | 1693530.1705 | 0
Cryo1.05.01 Mu2e Interface Connection |  | 15971.2963 | 0 | 0 | -15971.2963 | 0 | 70813.9345 | 38110.804 | 0 | -32703.1305 | 38110.804 | 1693530.1705 | 1693530.1705 | 0
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 27198.924 | 0
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 27198.924 | 0
Cryo1.06 Cryo Safety Documents |  | 686.6947 | 23793.972 | 9680.91 | 23107.2773 | 14113.062 | 155311.4174 | 155311.4175 | 117471.37 | 0.0001 | 37840.0475 | 155311.4174 | 155311.4174 | 0
Cryo1.06 Cryo Safety Documents |  | 686.6947 | 23793.972 | 9680.91 | 23107.2773 | 14113.062 | 155311.4174 | 155311.4175 | 117471.37 | 0.0001 | 37840.0475 | 155311.4174 | 155311.4174 | 0
Cryo1.06 Cryo Safety Documents |  | 686.6947 | 23793.972 | 9680.91 | 23107.2773 | 14113.062 | 155311.4174 | 155311.4175 | 117471.37 | 0.0001 | 37840.0475 | 155311.4174 | 155311.4174 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151583.0371 | 151583.0371 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151583.0371 | 151583.0371 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151583.0371 | 151583.0371 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 11968.502 | 11968.502 | 0 | 0 | 11968.502 | 11968.502 | 11968.502 | 0 | 0 | 11968.502 | 122290.7136 | 122290.7136 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 11968.502 | 11968.502 | 0 | 0 | 11968.502 | 11968.502 | 11968.502 | 0 | 0 | 11968.502 | 122290.7136 | 122290.7136 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 11968.502 | 11968.502 | 0 | 0 | 11968.502 | 11968.502 | 11968.502 | 0 | 0 | 11968.502 | 122290.7136 | 122290.7136 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106765.1548 | 106765.1548 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106765.1548 | 106765.1548 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106765.1548 | 106765.1548 | 0
a. SUBTOTAL |  | 120126.927 | 99465.5543 | 161740.49 | -20661.3727 | -62274.9357 | 4034266.0208 | 4034487.0892 | 3966698.76 | 221.0684 | 67788.3292 | 7034404.6567 | 7034404.6567 | 0
b. MANAGEMENT RESERVE | [11 empty] | 2702864.36
c. TOTAL |  | 120126.927 | 99465.5543 | 161740.49 | -20661.3727 | -62274.9357 | 4034266.0208 | 4034487.0892 | 3966698.76 | 221.0684 | 67788.3292 | 9737269.0167

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | (YYYYMMDD) | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {CostProject.Fee} |  | {=Cell[R,C-5]+ Cell[R,C-2]} |  | {=Cell[R+7,C-6]+Cell[R,C-4]} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16)
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | f. MANAGEMENT RESERVE | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]-Cell[R-1,C]} |  | {=Cell[R-3,C]-Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2014-08-31 | PREVIOUS | 11920
2014-09-30 | TODATE | 168
2024-09-30 | ATCOMPLETE | 20112

## Data
Control Account.WBS (1) | Control Account.WBS (2) | Control Account.WBS (3) | Control Account.WBS | Summary Code | Cost Set | Date | Value | Currency
|  |  |  | O | Budget | 2014-08-31 | 1338621.0524 | TRUE
|  |  |  | O | Budget | 2014-09-30 | 44180.7069 | TRUE
|  |  |  | O | Budget | 2024-09-30 | 1122779.0978 | TRUE
|  |  |  | O | Earned | 2014-08-31 | 1330184.1797 | TRUE
|  |  |  | O | Earned | 2014-09-30 | 44303.9912 | TRUE
|  |  |  | O | Actuals | 2014-08-31 | 1365647.98 | TRUE
|  |  |  | O | Actuals | 2014-09-30 | 36465.55 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Budget | 2014-08-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Earned | 2014-08-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Actuals | 2014-08-31 | 43225.82 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Actuals | 2014-09-30 | 15.33 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Budget | 2014-08-31 | 125088.1879 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Budget | 2014-09-30 | 8062.9141 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Earned | 2014-08-31 | 125088.1879 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Earned | 2014-09-30 | 8062.9141 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Actuals | 2014-08-31 | 70266.32 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Actuals | 2014-09-30 | 5037.34 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Budget | 2014-09-30 | 2134.0695 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Budget | 2024-09-30 | 30362.1789 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Earned | 2014-09-30 | 2134.0695 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Actuals | 2014-09-30 | 179.93 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Budget | 2024-09-30 | 144212.2686 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Budget | 2024-09-30 | 130222.8397 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Budget | 2014-08-31 | 252132.7307 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Budget | 2014-09-30 | 17043.9274 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Budget | 2024-09-30 | 217304.5481 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Earned | 2014-08-31 | 252879.4169 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Earned | 2014-09-30 | 16297.2411 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Actuals | 2014-08-31 | 269285.25 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Actuals | 2014-09-30 | 9605.45 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Budget | 2014-08-31 | 410825.54 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Budget | 2014-09-30 | 2703.3331 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Earned | 2014-08-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Actuals | 2014-08-31 | 318793.19 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Actuals | 2014-09-30 | 9625.84 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Budget | 2014-08-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Earned | 2014-08-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Actuals | 2014-08-31 | 209827.85 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Actuals | 2014-09-30 | -2559.58 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Budget | 2014-08-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Earned | 2014-08-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Actuals | 2014-08-31 | 38615.08 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Actuals | 2014-09-30 | 2481.75 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Budget | 2014-08-31 | 1228140.2296 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Budget | 2014-09-30 | 54992.6978 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Budget | 2024-09-30 | 486650.1511 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Earned | 2014-08-31 | 1278848.2706 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Earned | 2014-09-30 | 37208.8556 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Actuals | 2014-08-31 | 1485987.2 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Actuals | 2014-09-30 | 131970.9 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Budget | 2014-08-31 | 420028.7161 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Budget | 2014-09-30 | 6563.4921 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Earned | 2014-08-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Actuals | 2014-08-31 | 424140.31 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Actuals | 2014-09-30 | -7148.27 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Budget | 2014-08-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Earned | 2014-08-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Actuals | 2014-08-31 | 583464.15 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Actuals | 2014-09-30 | -7015.97 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Budget | 2014-08-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Earned | 2014-08-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Actuals | 2014-08-31 | 228396.24 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Actuals | 2014-09-30 | 9866.86 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2014-08-31 | 54842.6382 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2014-09-30 | 15971.2963 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2024-09-30 | 1622716.236 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Earned | 2014-08-31 | 38110.804 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Budget | 2014-08-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Earned | 2014-08-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Actuals | 2014-08-31 | 25166.4 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Budget | 2014-08-31 | 154624.7227 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Budget | 2014-09-30 | 686.6947 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Earned | 2014-08-31 | 131517.4455 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Earned | 2014-09-30 | 23793.972 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Actuals | 2014-08-31 | 107790.46 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Actuals | 2014-09-30 | 9680.91 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2024-09-30 | 151583.0371 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Budget | 2014-09-30 | 11968.502 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Budget | 2024-09-30 | 110322.2116 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Earned | 2014-09-30 | 11968.502 | TRUE
Cryo1 | Cryo1.09 | Cryo1.09 | Cryo1.09 |  | Budget | 2024-09-30 | 106765.1548 | TRUE