## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 4206675 | 4261013 | 54338
A1301.03 Cryo Basic Engineering | A1301.03 |  | Cryo Basic Engineering | 275681.35 | 269176.66 | -6504.69
988 Cryo Controls Engineering | A1301.03 | 988 | Cryo Controls Engineering | 3423.52 | 0 | -3423.52
989 Cryo Mechanical Engineering | A1301.03 | 989 | Cryo Mechanical Engineering | 1369.41 | 0 | -1369.41
990 Cryo Electrical Engineering | A1301.03 | 990 | Cryo Electrical Engineering | 1711.76 | 0 | -1711.76
A1301.04.04 Cryo Refrigerator System | A1301.04.04 |  | Cryo Refrigerator System | 1326102.32 | 1339885.82 | 13783.5
2825 Design Mu2e Transfer Line Bayonet Can | A1301.04.04 | 2825 | Design Mu2e Transfer Line Bayonet Can | 8066.81 | 4601.93 | -3464.88
2879 Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | A1301.04.04 | 2879 | Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | 58074.76 | 75323.13 | 17248.37
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 86774.39 | 70053.4 | -16720.99
2700 Mu2e Interface - Detailed Engineering | A1301.05.01 | 2700 | Mu2e Interface - Detailed Engineering | 54747.89 | 38026.9 | -16720.99
A1301.07 g-2 Cryo Checkout | A1301.07 |  | g-2 Cryo Checkout | 1635.4 | 65416.12 | 63780.72
1131 g-2 Cryo Checkout | A1301.07 | 1131 | g-2 Cryo Checkout | 1635.4 | 65416.12 | 63780.72