## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 4326330 | 4321014 | -5316
A1301.03 Cryo Basic Engineering | A1301.03 |  | Cryo Basic Engineering | 280771.98 | 269176.66 | -11595.32
988 Cryo Controls Engineering | A1301.03 | 988 | Cryo Controls Engineering | 6102.8 | 0 | -6102.8
989 Cryo Mechanical Engineering | A1301.03 | 989 | Cryo Mechanical Engineering | 2441.12 | 0 | -2441.12
990 Cryo Electrical Engineering | A1301.03 | 990 | Cryo Electrical Engineering | 3051.4 | 0 | -3051.4
A1301.04.04 Cryo Refrigerator System | A1301.04.04 |  | Cryo Refrigerator System | 1396519.37 | 1397666.5 | 1147.13
2825 Design Mu2e Transfer Line Bayonet Can | A1301.04.04 | 2825 | Design Mu2e Transfer Line Bayonet Can | 14379.96 | 6902.9 | -7477.06
2879 Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | A1301.04.04 | 2879 | Refrig Syst Electrical - 2nd Receive Matl for Electrical Work | 66698.94 | 75323.13 | 8624.19
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 99265.19 | 70053.4 | -29211.79
2700 Mu2e Interface - Detailed Engineering | A1301.05.01 | 2700 | Mu2e Interface - Detailed Engineering | 67238.69 | 38026.9 | -29211.79
A1301.07 g-2 Cryo Checkout | A1301.07 |  | g-2 Cryo Checkout | 31072.66 | 65416.12 | 34343.46
1131 g-2 Cryo Checkout | A1301.07 | 1131 | g-2 Cryo Checkout | 31072.66 | 65416.12 | 34343.46