## Report
|  |  |  | CONTRACT PERFORMANCE REPORT | [8 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [7 empty] | Dollars | OMB No. 0704-0188 (modified)
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM |  |  | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME |  |  | a. FROM (YYYYMMDD) |  | 2015-02-01
[9 empty] | Cryogenics AIP |  |  | b. TO (YYYYMMDD) |  | 2015-02-28
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  | g. CONTRACT CEILING |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 9545352 | 0 |  | 0 |  | 9545352 |  | 9545352 |  | 9545352
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. SCHED PERFORM INDEX/COST PERFORM INDEX |  |  |  | 8.CONTINGENCY (on remaining)
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | SPI = | 0.96445
|  | AT COMPLETION |  | BASE |  |  |  | CPI = | 1.0055 |  |  | Cont% = | 86.86%
|  | 7054206 |  | 7120344.0247 |  | 66138.0247
9. PERFORMANCE DATA
Control Account.WBS (1) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE |  |  |  |  | AT COMPLETION
Control Account.WBS (2) |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED | ESTIMATED | VARIANCE
CTC |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (14) | (15) | (16)
Cryo1 Muon Campus Cryogenics - AIP |  | 41175.6251 | 2466.509 | 61685.76 | -38709.1161 | -59219.251 | 4487961.0635 | 4328413.3746 | 4304882.15 | -159547.6889 | 23531.2246 | 7120344.0247 | 7054206 | 66138.0247
Cryo1.02 Cryo Project Management |  | 2466.509 | 2466.509 | 1605.94 | 0 | 860.569 | 199087.4641 | 199087.4641 | 137535.1 | 0 | 61552.3641 | 470913.7994 | 404776 | 66137.7994
A1301.02.01.01 Cryo AIP Gen Proj OS - FY13 |  | 0 | 0 | 0 | 0 | 0 | 51346.4223 | 51346.4223 | 43241.15 | 0 | 8105.2723 | 51346.4223 | 43241.15 | 8105.2723
A1301.02.01.02 Cryo AIP Gen Proj OS - FY14 |  | 0 | 0 | 0 | 0 | 0 | 133151.102 | 133151.102 | 75118.37 | 0 | 58032.732 | 133151.102 | 75118 | 58033.102
A1301.02.01.03 Cryo AIP Gen Proj OS - FY15 |  | 2466.509 | 2466.509 | 1605.94 | 0 | 860.569 | 14589.9398 | 14589.9398 | 19175.58 | 0 | -4585.6402 | 32348.8042 | 32348.8042 | 0
A1301.02.01.04 Cryo AIP Gen Proj OS - FY16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133843.068 | 133843.068 | 0
A1301.02.01.05 Cryo AIP Gen Proj OS - FY17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120224.4029 | 120224.4029 | 0
Cryo1.03 Cryo Basic Engineering |  | 5656.2541 | 0 | 25456.59 | -5656.2541 | -25456.59 | 297740.7412 | 269176.6581 | 334397.29 | -28564.0831 | -65220.6319 | 462570.3404 | 462570.3404 | 0
A1301.03 Cryo Basic Engineering |  | 5656.2541 | 0 | 25456.59 | -5656.2541 | -25456.59 | 297740.7412 | 269176.6581 | 334397.29 | -28564.0831 | -65220.6319 | 462570.3404 | 462570.3404 | 0
Cryo1.04 Cryogenic plant sub systems |  | 7014.6142 | 0 | 8704.93 | -7014.6142 | -8704.93 | 3456219.4638 | 3427698.5599 | 3574588.29 | -28520.9039 | -146889.7301 | 4048061.878 | 4048061.878 | 0
A1301.04.01 LN2 system |  | 0 | 0 | -0.72 | 0 | 0.72 | 413528.8731 | 413528.8731 | 331519.52 | 0 | 82009.3531 | 413528.8731 | 413528.8731 | 0
A1301.04.02 Gas management system |  | 0 | 0 | 0 | 0 | 0 | 236065.7847 | 236065.7847 | 207268.27 | 0 | 28797.5147 | 236065.7847 | 236065.7847 | 0
A1301.04.03 ODH system |  | 0 | 0 | 0 | 0 | 0 | 49757.6345 | 49757.6345 | 41357.53 | 0 | 8400.1045 | 49757.6345 | 49757.6345 | 0
A1301.04.04 Cryo Refrigerator system |  | 7014.6142 | 0 | 8688.12 | -7014.6142 | -8688.12 | 1426187.4001 | 1397666.4962 | 1729739 | -28520.9039 | -332072.5038 | 1756171.888 | 1756171.888 | 0
A1301.04.05 Cryo Compressor System |  | 0 | 0 | 0 | 0 | 0 | 426592.2083 | 426592.2083 | 417385.79 | 0 | 9206.4183 | 426592.2083 | 426592.2083 | 0
A1301.04.06 Cryo Interconnect Piping |  | 0 | 0 | 17.53 | 0 | -17.53 | 737933.9081 | 737933.9081 | 576465.71 | 0 | 161468.1981 | 737933.9081 | 737933.9081 | 0
A1301.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 0 | 0 | 0 | 166153.655 | 166153.655 | 270852.47 | 0 | -104698.815 | 166153.655 | 166153.655 | 0
A1301.04.08 Cryogenic Fluids |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261857.9263 | 261857.9263 | 0
Cryo1.05 Experiment interfaces |  | 26038.2478 | 0 | 13684.42 | -26038.2478 | -13684.42 | 199715.0225 | 97252.3206 | 76978.69 | -102462.7019 | 20273.6306 | 1636345.5411 | 1636345.5411 | 0
A1301.05.01 Mu2e Interface Connection |  | 26038.2478 | 0 | 13684.42 | -26038.2478 | -13684.42 | 172516.0985 | 70053.3966 | 51812.29 | -102462.7019 | 18241.1066 | 1609146.6171 | 1609146.6171 | 0
A1301.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 27198.924 | 0
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 75.08 | 0 | -75.08 | 155311.4174 | 155311.4174 | 125667.7 | 0 | 29643.7174 | 155311.4174 | 155311.4174 | 0
A1301.06 Cryo Safety Documents |  | 0 | 0 | 75.08 | 0 | -75.08 | 155311.4174 | 155311.4174 | 125667.7 | 0 | 29643.7174 | 155311.4174 | 155311.4174 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.55 | 0 | 65182.5707 | 134950.8402 | 134950.8402 | 0
A1301.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.55 | 0 | 65182.5707 | 134950.8402 | 134950.8402 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 12158.8 | 0 | -12158.8 | 114470.8338 | 114470.8338 | 55481.53 | 0 | 58989.3038 | 114470.8338 | 114470.8338 | 0
A1301.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 12158.8 | 0 | -12158.8 | 114470.8338 | 114470.8338 | 55481.53 | 0 | 58989.3038 | 114470.8338 | 114470.8338 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97719.3744 | 97719.3744 | 0
A1301.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97719.3744 | 97719.3744 | 0
a. SUBTOTAL |  | 41175.6251 | 2466.509 | 61685.76 | -38709.1161 | -59219.251 | 4487961.0635 | 4328413.3746 | 4304882.15 | -159547.6889 | 23531.2246 | 7120344.0347 | 7054206 | 66138.0347
b. MANAGEMENT RESERVE | [11 empty] | 2425007.98
c. TOTAL |  | 41175.6251 | 2466.509 | 61685.76 | -38709.1161 | -59219.251 | 4487961.0635 | 4328413.3746 | 4304882.15 | -159547.6889 | 23531.2246 | 9545352.0147

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | (YYYYMMDD) | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {CostProject.Fee} |  | {=Cell[R,C-5]+ Cell[R,C-2]} |  | {=Cell[R+7,C-6]+Cell[R,C-4]} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16)
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | f. MANAGEMENT RESERVE | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]-Cell[R-1,C]} |  | {=Cell[R-3,C]-Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2015-01-31 | PREVIOUS | 12736
2015-02-28 | TODATE | 160
2024-09-30 | ATCOMPLETE | 19304

## Data
Control Account.WBS (1) | Control Account.WBS (2) | CTC | Summary Code | Cost Set | Date | Value | Currency
|  |  | O | Budget | 2015-01-31 | 1533560.6694 | TRUE
|  |  | O | Budget | 2015-02-28 | 18368.4487 | TRUE
|  |  | O | Budget | 2024-09-30 | 837049.7066 | TRUE
|  |  | O | Earned | 2015-01-31 | 1478088.3913 | TRUE
|  |  | O | Earned | 2015-02-28 | 539.1622 | TRUE
|  |  | O | Actuals | 2015-01-31 | 1522988.24 | TRUE
|  |  | O | Actuals | 2015-02-28 | 24354.46 | TRUE
|  |  | O | EAC | 2015-01-31 | 1522988.24 | TRUE
|  |  | O | EAC | 2015-02-28 | 76422.0764 | TRUE
|  |  | O | EAC | 2024-09-30 | 802689.2352 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Budget | 2015-01-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Earned | 2015-01-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Actuals | 2015-01-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | EAC | 2015-01-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Budget | 2015-01-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Earned | 2015-01-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Actuals | 2015-01-31 | 75118.37 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | EAC | 2015-01-31 | 75118.37 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Budget | 2015-01-31 | 12123.4308 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Budget | 2015-02-28 | 2466.509 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Budget | 2024-09-30 | 17758.8644 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Earned | 2015-01-31 | 12123.4308 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Earned | 2015-02-28 | 2466.509 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Actuals | 2015-01-31 | 17569.64 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Actuals | 2015-02-28 | 1605.94 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | EAC | 2015-01-31 | 17569.64 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | EAC | 2015-02-28 | 4072.449 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | EAC | 2024-09-30 | 17758.8644 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.04 |  | Budget | 2024-09-30 | 133843.068 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.04 |  | EAC | 2024-09-30 | 133843.068 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.05 |  | Budget | 2024-09-30 | 120224.4029 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.05 |  | EAC | 2024-09-30 | 120224.4029 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Budget | 2015-01-31 | 292084.4871 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Budget | 2015-02-28 | 5656.2541 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Budget | 2024-09-30 | 164829.5992 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Earned | 2015-01-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Actuals | 2015-01-31 | 308940.7 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Actuals | 2015-02-28 | 25456.59 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | EAC | 2015-01-31 | 308940.7 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | EAC | 2015-02-28 | 31764.1702 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | EAC | 2024-09-30 | 188969.5797 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Budget | 2015-01-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Earned | 2015-01-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Actuals | 2015-01-31 | 331520.24 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Actuals | 2015-02-28 | -0.72 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | EAC | 2015-01-31 | 331520.24 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | EAC | 2015-02-28 | -0.72 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Budget | 2015-01-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Earned | 2015-01-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Actuals | 2015-01-31 | 207268.27 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | EAC | 2015-01-31 | 207268.27 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Budget | 2015-01-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Earned | 2015-01-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Actuals | 2015-01-31 | 41357.53 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | EAC | 2015-01-31 | 41357.53 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2015-01-31 | 1419172.7859 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2015-02-28 | 7014.6142 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2024-09-30 | 329984.4879 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Earned | 2015-01-31 | 1397666.4962 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Actuals | 2015-01-31 | 1721050.88 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Actuals | 2015-02-28 | 8688.12 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | EAC | 2015-01-31 | 1721050.88 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | EAC | 2015-02-28 | 96507.4128 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | EAC | 2024-09-30 | 264888.5893 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Budget | 2015-01-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Earned | 2015-01-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Actuals | 2015-01-31 | 417385.79 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | EAC | 2015-01-31 | 417385.79 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Budget | 2015-01-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Earned | 2015-01-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Actuals | 2015-01-31 | 576448.18 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Actuals | 2015-02-28 | 17.53 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | EAC | 2015-01-31 | 576448.18 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | EAC | 2015-02-28 | 17.53 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Budget | 2015-01-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Earned | 2015-01-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Actuals | 2015-01-31 | 270852.47 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | EAC | 2015-01-31 | 270852.47 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Budget | 2024-09-30 | 261857.9263 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2015-01-31 | 146477.8507 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2015-02-28 | 26038.2478 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2024-09-30 | 1436630.5186 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Earned | 2015-01-31 | 70053.3966 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Actuals | 2015-01-31 | 38127.87 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Actuals | 2015-02-28 | 13684.42 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | EAC | 2015-01-31 | 38127.87 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | EAC | 2015-02-28 | 72228.5971 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | EAC | 2024-09-30 | 1480450.6885 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Budget | 2015-01-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Earned | 2015-01-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Actuals | 2015-01-31 | 25166.4 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | EAC | 2015-01-31 | 25166.4 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Budget | 2015-01-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Earned | 2015-01-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Actuals | 2015-01-31 | 125592.62 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Actuals | 2015-02-28 | 75.08 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | EAC | 2015-01-31 | 125592.62 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | EAC | 2015-02-28 | 75.08 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Budget | 2015-01-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Budget | 2024-09-30 | 69534.7195 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Earned | 2015-01-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Actuals | 2015-01-31 | 233.55 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | EAC | 2015-01-31 | 233.55 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | EAC | 2015-02-28 | 700.8869 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | EAC | 2024-09-30 | 67248.744 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Budget | 2015-01-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Earned | 2015-01-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Actuals | 2015-01-31 | 43322.73 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Actuals | 2015-02-28 | 12158.8 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | EAC | 2015-01-31 | 43322.73 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | EAC | 2015-02-28 | 12158.8 | TRUE
Cryo1 | Cryo1.09 | A1301.09 |  | Budget | 2024-09-30 | 97719.3744 | TRUE
Cryo1 | Cryo1.09 | A1301.09 |  | EAC | 2024-09-30 | 75431.3358 | TRUE