## Report
|  |  |  | CONTRACT PERFORMANCE REPORT | [8 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [7 empty] | Dollars | OMB No. 0704-0188 (modified)
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM |  |  | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME |  |  | a. FROM (YYYYMMDD) |  | 2015-04-01
[9 empty] | Cryogenics AIP |  |  | b. TO (YYYYMMDD) |  | 2015-04-30
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  | g. CONTRACT CEILING |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 9545352 | 0 |  | 0 |  | 9545352 |  | 9545352 |  | 9545352
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. SCHED PERFORM INDEX/COST PERFORM INDEX |  |  |  | 8. CONTINGENCY (on remaining)
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | SPI = | 0.97549
|  | AT COMPLETION |  | BASE |  |  |  | CPI = | 1.0188 |  |  | Cont % = | 28.49%
|  | 8389005 |  | 8455142.6677 |  | 66138
9. PERFORMANCE DATA
Control Account.WBS (1) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE |  |  |  |  | AT COMPLETION
Control Account.WBS (2) |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED | ESTIMATED | VARIANCE
CTC |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK
ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (14) | (15) | (16)
Cryo1 Muon Campus Cryogenics - AIP |  | 143642.7468 | 151169.8524 | 154022.66 | 7527.1056 | -2852.8076 | 4744306.1856 | 4628007.729 | 4542795.72 | -116298.4566 | 85212.009 | 8455142.6677 | 8389005 | 66138
Cryo1.02 Cryo Project Management |  | 14026.2067 | 14026.2067 | 6639.63 | 0 | 7386.5767 | 227139.8775 | 227139.8775 | 147170.45 | 0 | 79969.4275 | 615977.0641 | 549839 | 66138
A1301.02.01.01 Cryo AIP General Project Oversight - FY13 |  | 0 | 0 | 0 | 0 | 0 | 51346.4223 | 51346.4223 | 43241.15 | 0 | 8105.2723 | 51346.4223 | 43241.15 | 8105.2723
A1301.02.01.02 Cryo AIP General Project Oversight - FY14 |  | 0 | 0 | 0 | 0 | 0 | 133151.102 | 133151.102 | 75118.37 | 0 | 58032.732 | 133151.102 | 75118.37 | 58032.732
A1301.02.01.03 Cryo AIP General Project Oversight - FY15 |  | 2713.1598 | 2713.1598 | 4879.61 | 0 | -2166.4502 | 20016.2594 | 20016.2594 | 27050.91 | 0 | -7034.6506 | 32348.8041 | 32348.8041 | 0
A1301.02.01.04 Cryo AIP General Project Oversight - FY16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164602.2945 | 164602.2945 | 0.0001
A1301.02.01.05 Cryo AIP General Project Oversight - FY17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160479.4071 | 160479.4071 | 0.0001
A1301.02.01.07 Cryo AIP Gen Proj OS - FY15 Supp |  | 11313.0469 | 11313.0469 | 1760.02 | 0 | 9553.0269 | 22626.0938 | 22626.0938 | 1760.02 | 0 | 20866.0738 | 74049.0341 | 74049.0341 | 0
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 649.56 | 0 | -649.56 | 269176.6581 | 269176.6581 | 342333.09 | 0 | -73156.4319 | 269176.6581 | 269176.6581 | 0
A1301.03 Cryo Basic Engineering |  | 0 | 0 | 649.56 | 0 | -649.56 | 269176.6581 | 269176.6581 | 342333.09 | 0 | -73156.4319 | 269176.6581 | 269176.6581 | -73156.4319
Cryo1.04 Cryogenic plant sub systems |  | 29959.3813 | 77055.5058 | 141583.58 | 47096.1245 | -64528.0742 | 3678828.1347 | 3604389.1034 | 3789085.92 | -74439.0313 | -184696.8166 | 3727547.1191 | 3727547.1191 | 0
A1301.04.01 LN2 system |  | 0 | 0 | 0 | 0 | 0 | 413528.8731 | 413528.8731 | 331519.52 | 0 | 82009.3531 | 413528.8731 | 413528.8731 | 0
A1301.04.02 Gas management system |  | 0 | 0 | 0 | 0 | 0 | 236065.7847 | 236065.7847 | 207268.27 | 0 | 28797.5147 | 236065.7847 | 236065.7847 | 0
A1301.04.03 ODH system |  | 0 | 0 | 0 | 0 | 0 | 49757.6345 | 49757.6345 | 41357.53 | 0 | 8400.1045 | 49757.6345 | 49757.6345 | 0
A1301.04.04 Cryo Refrigerator system |  | 1753.6535 | 0 | 9476.65 | -1753.6535 | -9476.65 | 1435657.1292 | 1435657.1292 | 1750248.87 | 0 | -314591.7408 | 1435657.1292 | 1435657.1292 | 0
A1301.04.05 Cryo Compressor System |  | 0 | 0 | 0 | 0 | 0 | 426592.2083 | 426592.2083 | 417385.79 | 0 | 9206.4183 | 426592.2083 | 426592.2083 | 0
A1301.04.06 Cryo Interconnect Piping |  | 0 | 0 | 0 | 0 | 0 | 737933.9081 | 737933.9081 | 577324.94 | 0 | 160608.9681 | 737933.9081 | 737933.9081 | 0
A1301.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 0 | 0 | 0 | 166153.655 | 166153.655 | 270852.47 | 0 | -104698.815 | 166153.655 | 166153.655 | 0
A1301.04.08 Cryogenic Fluids |  | 28205.7278 | 77055.5058 | 132106.93 | 48849.778 | -55051.4242 | 213138.9418 | 138699.9105 | 193128.53 | -74439.0313 | -54428.6195 | 261857.9262 | 261857.9262 | 0
Cryo1.05 Experiment interfaces |  | 50388.9395 | 4580.8126 | 3650.58 | -45808.1269 | 930.2326 | 184694.9241 | 136596.3908 | 81324.17 | -48098.5333 | 55272.2208 | 1154614.03 | 1154614.03 | 0
A1301.05.01 Mu2e Interface Connection |  | 50388.9395 | 4580.8126 | 3650.58 | -45808.1269 | 930.2326 | 157496.0001 | 109397.4668 | 56157.77 | -48098.5333 | 53239.6968 | 1127415.106 | 1127415.106 | 0
A1301.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 27198.924 | 0
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125667.7 | 0 | 29643.7174 | 155311.4174 | 155311.4174 | 0
A1301.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125667.7 | 0 | 29643.7174 | 155311.4174 | 155311.4174 | 29643.7174
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.55 | 0 | 65182.5707 | 134950.8402 | 134950.8402 | 0
A1301.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.55 | 0 | 65182.5707 | 134950.8402 | 134950.8402 | 66712.1809
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55481.53 | 0 | 58989.3038 | 114470.8338 | 114470.8338 | 0
A1301.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55481.53 | 0 | 58989.3038 | 114470.8338 | 114470.8338 | 58989.3038
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97719.3744 | 97719.3744 | 0
A1301.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97719.3744 | 97719.3744 | 0
Cryo1.10 Cryo Distribution Box (CDB) |  | 49268.2193 | 55507.3273 | 1499.31 | 6239.108 | 54008.0173 | 49268.2193 | 55507.3273 | 1499.31 | 6239.108 | 54008.0173 | 2185375.3306 | 2185375.3306 | 0
A1301.10 Cryo Distribution Box (CDB) |  | 49268.2193 | 55507.3273 | 1499.31 | 6239.108 | 54008.0173 | 49268.2193 | 55507.3273 | 1499.31 | 6239.108 | 54008.0173 | 2185375.3306 | 2186874.6406 | -1499.31
a. SUBTOTAL |  | 143642.7468 | 151169.8524 | 154022.66 | 7527.1056 | -2852.8076 | 4744306.1856 | 4628007.729 | 4542795.72 | -116298.4566 | 85212.009 | 8455142.6877 | 8389005 | 66138
b. MANAGEMENT RESERVE | [11 empty] | 1090209.33
c. TOTAL |  | 143642.7468 | 151169.8524 | 154022.66 | 7527.1056 | -2852.8076 | 4744306.1856 | 4628007.729 | 4542795.72 | -116298.4566 | 85212.009 | 9545352.0177

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | (YYYYMMDD) | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16)
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | f. MANAGEMENT RESERVE | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2015-03-31 | PREVIOUS | 13072
2015-04-30 | TODATE | 176
2024-09-30 | ATCOMPLETE | 18952

## Data
Control Account.WBS (1) | Control Account.WBS (2) | CTC | Summary Code | Cost Set | Date | Value | Currency
|  |  | O | Budget | 2015-03-31 | 1552136.8941 | TRUE
|  |  | O | Budget | 2015-04-30 | 55512.1925 | TRUE
|  |  | O | Budget | 2024-09-30 | 1022432.1496 | TRUE
|  |  | O | Earned | 2015-03-31 | 1528480.5412 | TRUE
|  |  | O | Earned | 2015-04-30 | 46990.3853 | TRUE
|  |  | O | Actuals | 2015-03-31 | 1567519.9 | TRUE
|  |  | O | Actuals | 2015-04-30 | 31384.13 | TRUE
|  |  | O | EAC | 2015-03-31 | 1567519.9 | TRUE
|  |  | O | EAC | 2015-04-30 | 87024.9735 | TRUE
|  |  | O | EAC | 2024-09-30 | 1048162.1093 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Budget | 2015-03-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Earned | 2015-03-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | Actuals | 2015-03-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.01 |  | EAC | 2015-03-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Budget | 2015-03-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Earned | 2015-03-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | Actuals | 2015-03-31 | 75118.37 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.02 |  | EAC | 2015-03-31 | 75118.37 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Budget | 2015-03-31 | 17303.0996 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Budget | 2015-04-30 | 2713.1598 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Budget | 2024-09-30 | 12332.5447 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Earned | 2015-03-31 | 17303.0996 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Earned | 2015-04-30 | 2713.1598 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Actuals | 2015-03-31 | 22171.3 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | Actuals | 2015-04-30 | 4879.61 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | EAC | 2015-03-31 | 22171.3 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | EAC | 2015-04-30 | 7592.7698 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.03 |  | EAC | 2024-09-30 | 12332.5447 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.04 |  | Budget | 2024-09-30 | 164602.2945 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.04 |  | EAC | 2024-09-30 | 164602.2944 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.05 |  | Budget | 2024-09-30 | 160479.4071 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.05 |  | EAC | 2024-09-30 | 160479.407 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | Budget | 2015-03-31 | 11313.0469 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | Budget | 2015-04-30 | 11313.0469 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | Budget | 2024-09-30 | 51422.9403 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | Earned | 2015-03-31 | 11313.0469 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | Earned | 2015-04-30 | 11313.0469 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | Actuals | 2015-04-30 | 1760.02 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | EAC | 2015-04-30 | 13073.0669 | TRUE
Cryo1 | Cryo1.02 | A1301.02.01.07 |  | EAC | 2024-09-30 | 51422.9403 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Budget | 2015-03-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Earned | 2015-03-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Actuals | 2015-03-31 | 341683.53 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | Actuals | 2015-04-30 | 649.56 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | EAC | 2015-03-31 | 341683.53 | TRUE
Cryo1 | Cryo1.03 | A1301.03 |  | EAC | 2015-04-30 | 649.56 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Budget | 2015-03-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Earned | 2015-03-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | Actuals | 2015-03-31 | 331519.52 | TRUE
Cryo1 | Cryo1.04 | A1301.04.01 |  | EAC | 2015-03-31 | 331519.52 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Budget | 2015-03-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Earned | 2015-03-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | Actuals | 2015-03-31 | 207268.27 | TRUE
Cryo1 | Cryo1.04 | A1301.04.02 |  | EAC | 2015-03-31 | 207268.27 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Budget | 2015-03-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Earned | 2015-03-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | Actuals | 2015-03-31 | 41357.53 | TRUE
Cryo1 | Cryo1.04 | A1301.04.03 |  | EAC | 2015-03-31 | 41357.53 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2015-03-31 | 1433903.4757 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Budget | 2015-04-30 | 1753.6535 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Earned | 2015-03-31 | 1435657.1292 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Actuals | 2015-03-31 | 1740772.22 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | Actuals | 2015-04-30 | 9476.65 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | EAC | 2015-03-31 | 1740772.22 | TRUE
Cryo1 | Cryo1.04 | A1301.04.04 |  | EAC | 2015-04-30 | 9476.65 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Budget | 2015-03-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Earned | 2015-03-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | Actuals | 2015-03-31 | 417385.79 | TRUE
Cryo1 | Cryo1.04 | A1301.04.05 |  | EAC | 2015-03-31 | 417385.79 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Budget | 2015-03-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Earned | 2015-03-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | Actuals | 2015-03-31 | 577324.94 | TRUE
Cryo1 | Cryo1.04 | A1301.04.06 |  | EAC | 2015-03-31 | 577324.94 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Budget | 2015-03-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Earned | 2015-03-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | Actuals | 2015-03-31 | 270852.47 | TRUE
Cryo1 | Cryo1.04 | A1301.04.07 |  | EAC | 2015-03-31 | 270852.47 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Budget | 2015-03-31 | 184933.214 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Budget | 2015-04-30 | 28205.7278 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Budget | 2024-09-30 | 48718.9844 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Earned | 2015-03-31 | 61644.4047 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Earned | 2015-04-30 | 77055.5058 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Actuals | 2015-03-31 | 61021.6 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | Actuals | 2015-04-30 | 132106.93 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | EAC | 2015-03-31 | 61021.6 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | EAC | 2015-04-30 | 187165.6484 | TRUE
Cryo1 | Cryo1.04 | A1301.04.08 |  | EAC | 2024-09-30 | 145154.8031 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2015-03-31 | 107107.0606 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2015-04-30 | 50388.9395 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Budget | 2024-09-30 | 969919.1059 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Earned | 2015-03-31 | 104816.6542 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Earned | 2015-04-30 | 4580.8126 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Actuals | 2015-03-31 | 52507.19 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | Actuals | 2015-04-30 | 3650.58 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | EAC | 2015-03-31 | 52507.19 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | EAC | 2015-04-30 | 40830.7671 | TRUE
Cryo1 | Cryo1.05 | A1301.05.01 |  | EAC | 2024-09-30 | 991864.4776 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Budget | 2015-03-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Earned | 2015-03-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | Actuals | 2015-03-31 | 25166.4 | TRUE
Cryo1 | Cryo1.05 | A1301.05.02 |  | EAC | 2015-03-31 | 25166.4 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Budget | 2015-03-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Earned | 2015-03-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | Actuals | 2015-03-31 | 125667.7 | TRUE
Cryo1 | Cryo1.06 | A1301.06 |  | EAC | 2015-03-31 | 125667.7 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Budget | 2015-03-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Budget | 2024-09-30 | 69534.7195 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Earned | 2015-03-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | Actuals | 2015-03-31 | 233.55 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | EAC | 2015-03-31 | 233.55 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | EAC | 2015-04-30 | 716.2348 | TRUE
Cryo1 | Cryo1.07 | A1301.07 |  | EAC | 2024-09-30 | 67288.8745 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Budget | 2015-03-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Earned | 2015-03-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | Actuals | 2015-03-31 | 55481.53 | TRUE
Cryo1 | Cryo1.08 | A1301.08 |  | EAC | 2015-03-31 | 55481.53 | TRUE
Cryo1 | Cryo1.09 | A1301.09 |  | Budget | 2024-09-30 | 97719.3744 | TRUE
Cryo1 | Cryo1.09 | A1301.09 |  | EAC | 2024-09-30 | 97719.3744 | TRUE
Cryo1 | Cryo1.10 | A1301.10 |  | Budget | 2015-04-30 | 49268.2193 | TRUE
Cryo1 | Cryo1.10 | A1301.10 |  | Budget | 2024-09-30 | 2136107.1113 | TRUE
Cryo1 | Cryo1.10 | A1301.10 |  | Earned | 2015-04-30 | 55507.3273 | TRUE
Cryo1 | Cryo1.10 | A1301.10 |  | Actuals | 2015-04-30 | 1499.31 | TRUE
Cryo1 | Cryo1.10 | A1301.10 |  | EAC | 2015-04-30 | 50767.5293 | TRUE
Cryo1 | Cryo1.10 | A1301.10 |  | EAC | 2024-09-30 | 2136107.1113 | TRUE