## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 4744306 | 4628008 | -116298.45
A1301.04.08 Cryogenic Fluids | A1301.04.08 |  | Cryogenic Fluids | 213138.94 | 138699.91 | -74439.03
2934 Receive 3rd Helium Delivery | A1301.04.08 | 2934 | Receive 3rd Helium Delivery | 61644.4 | 15411.1 | -46233.3
2935 Certify 2 Trailers/Connect 2 Trailers & Pump/Backfill | A1301.04.08 | 2935 | Certify 2 Trailers/Connect 2 Trailers & Pump/Backfill | 28205.73 | 0 | -28205.73
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 157496 | 109397.47 | -48098.53
2988 Mu2e Interface - Transfer Line System Design | A1301.05.01 | 2988 | Mu2e Interface - Transfer Line System Design | 52679.35 | 4580.81 | -48098.54
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 49268.22 | 55507.33 | 6239.11
2939 Cryo Distribution Box Requirements | A1301.10 | 2939 | Cryo Distribution Box Requirements | 19624.22 | 17661.8 | -1962.42
2940 Preliminary Specification | A1301.10 | 2940 | Preliminary Specification | 3309.22 | 6382.06 | 3072.84
2941 Preliminary Drawings | A1301.10 | 2941 | Preliminary Drawings | 2691.76 | 5191.25 | 2499.49
2945 Complete CDB Prelim. Eng. Design | A1301.10 | 2945 | Complete CDB Prelim. Eng. Design | 21894.62 | 25543.72 | 3649.1
2969 Specify Helium Dewar | A1301.10 | 2969 | Specify Helium Dewar | 1748.41 | 728.5 | -1019.91