## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 4878968 | 4758586 | -120382
A1301.04.08 Cryogenic Fluids | A1301.04.08 |  | Cryogenic Fluids | 238780.51 | 169522.11 | -69258.4
2934 Receive 3rd Helium Delivery | A1301.04.08 | 2934 | Receive 3rd Helium Delivery | 61644.4 | 46223.3 | -15421.1
2935 Certify 2 Trailers/Connect 2 Trailers & Pump/Backfill | A1301.04.08 | 2935 | Certify 2 Trailers/Connect 2 Trailers & Pump/Backfill | 53847.3 | 0 | -53847.3
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 203304.13 | 150624.78 | -52679.35
2988 Mu2e Interface - Transfer Line System Design | A1301.05.01 | 2988 | Mu2e Interface - Transfer Line System Design | 98487.47 | 45808.13 | -52679.34
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 99728.88 | 101285.13 | 1556.25
2943 Conduct & Evaluate RFI | A1301.10 | 2943 | Conduct & Evaluate RFI | 716.01 | 5370.04 | 4654.03
2945 Complete CDB Prelim. Eng. Design | A1301.10 | 2945 | Complete CDB Prelim. Eng. Design | 58385.65 | 57473.37 | -912.28
2969 Specify Helium Dewar | A1301.10 | 2969 | Specify Helium Dewar | 2914.02 | 728.5 | -2185.52