## Report
|  |  |  | CONTRACT PERFORMANCE REPORT | [8 empty] | FORM APPROVED
|  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [7 empty] | Dollars | OMB No. 0704-0188 (modified)
1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM |  |  | 4. REPORT PERIOD
a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME |  |  | a. FROM (YYYYMMDD) |  | 2015-06-01
[9 empty] | Cryogenics AIP |  |  | b. TO (YYYYMMDD) |  | 2015-06-30
5. CONTRACT DATA
a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  | g. CONTRACT CEILING |  | i. DATE OF OTB/OTS (YYYYMMDD)
| COST | AUTHORIZED UNPRICED WORK
1 | 9545352 | 0 |  | 0 |  | 9545352 |  | 9545352 |  | 9545352
6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. SCHED PERFORM INDEX/COST PERFORM INDEX |  |  |  | 8. CONTINGENCY (on remaining)
|  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | SPI = | 0.98089
|  | AT COMPLETION |  | BASE |  |  |  | CPI = | 1.0157 |  |  | Cont % = | 30.82%
|  | 8389005 |  | 8455142.6671 |  | 66137.6671
9. PERFORMANCE DATA
Control Account.WBS (1) |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE |  |  |  |  | AT COMPLETION
Control Account.WBS (2) |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED | ESTIMATED | VARIANCE
Control Account.WBS (3) |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK
Control Account.WBS (4) |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST
(1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (14) | (15) | (16)
Cryo1 Muon Campus Cryogenics - AIP |  | 134076.7428 | 158675.1681 | 89736.27 | 24598.4253 | 68938.8981 | 5013044.3817 | 4917261.3099 | 4841208.28 | -95783.0718 | 76053.0299 | 8455142.6671 | 8389005 | 66137.6671
Cryo1.02 Cryo Project Management |  | 14026.2067 | 14026.2067 | 8606.64 | 0 | 5419.5667 | 253917.1811 | 253917.1811 | 164974.17 | 0 | 88943.0111 | 615977.0638 | 549839 | 66138.0638
Cryo1.02.01 Gen Proj OS |  | 14026.2067 | 14026.2067 | 8606.64 | 0 | 5419.5667 | 253917.1811 | 253917.1811 | 164974.17 | 0 | 88943.0111 | 615977.0638 | 519839 | 96138.0638
Cryo1.02.01.01 Cryo AIP Gen Proj OS - FY13 |  | 0 | 0 | 0 | 0 | 0 | 51346.4223 | 51346.4223 | 43241.15 | 0 | 8105.2723 | 51346.4223 | 43241.15 | 8105.2723
Cryo1.02.01.02 Cryo AIP Gen Proj OS - FY14 |  | 0 | 0 | 0 | 0 | 0 | 133151.102 | 133151.102 | 75118.37 | 0 | 58032.732 | 133151.102 | 75118.37 | 58032.732
Cryo1.02.01.03 Cryo AIP Gen Proj OS - FY15 |  | 2713.1598 | 2713.1598 | 1853.02 | 0 | 860.1398 | 25195.9282 | 25195.9282 | 32115.82 | 0 | -6919.8918 | 32348.8041 | 32349 | -0.1959
Cryo1.02.01.04 Cryo AIP Gen Proj OS - FY16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164602.2943 | 164602.2944 | -0.0001
Cryo1.02.01.05 Cryo AIP Gen Proj OS - FY17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160479.4071 | 160479.4071 | 0
Cryo1.02.01.07 Cryo AIP Gen Proj OS - FY15 Supp |  | 11313.0469 | 11313.0469 | 6753.62 | 0 | 4559.4269 | 44223.7286 | 44223.7286 | 14498.83 | 0 | 29724.8986 | 74049.034 | 74049.034 | 0
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 342333.09 | 0 | -73156.4319 | 269176.6581 | 269176.6581 | 0
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 342333.09 | 0 | -73156.4319 | 269176.6581 | 269176.6581 | 0
Cryo1.03 Cryo Basic Engineering |  | 0 | 0 | 0 | 0 | 0 | 269176.6581 | 269176.6581 | 342333.09 | 0 | -73156.4319 | 269176.6581 | 269176.6581 | 0
Cryo1.04 Cryogenic plant sub systems |  | 23077.4136 | 12328.8809 | 0 | -10748.5327 | 12328.8809 | 3727547.119 | 3647540.1866 | 3853865.5 | -80006.9324 | -206325.3134 | 3727547.119 | 3727547.119 | 0
Cryo1.04.01 LN2 system |  | 0 | 0 | 0 | 0 | 0 | 413528.8731 | 413528.8731 | 331519.52 | 0 | 82009.3531 | 413528.8731 | 413528.8731 | 0
Cryo1.04.01 LN2 system |  | 0 | 0 | 0 | 0 | 0 | 413528.8731 | 413528.8731 | 331519.52 | 0 | 82009.3531 | 413528.8731 | 413528.8731 | 0
Cryo1.04.02 Gas management system |  | 0 | 0 | 0 | 0 | 0 | 236065.7847 | 236065.7847 | 207268.27 | 0 | 28797.5147 | 236065.7847 | 236065.7847 | 0
Cryo1.04.02 Gas management system |  | 0 | 0 | 0 | 0 | 0 | 236065.7847 | 236065.7847 | 207268.27 | 0 | 28797.5147 | 236065.7847 | 236065.7847 | 0
Cryo1.04.03 ODH system |  | 0 | 0 | 0 | 0 | 0 | 49757.6345 | 49757.6345 | 41357.53 | 0 | 8400.1045 | 49757.6345 | 49757.6345 | 0
Cryo1.04.03 ODH system |  | 0 | 0 | 0 | 0 | 0 | 49757.6345 | 49757.6345 | 41357.53 | 0 | 8400.1045 | 49757.6345 | 49757.6345 | 0
Cryo1.04.04 Cryo Refrigerator system |  | 0 | 0 | 0 | 0 | 0 | 1435657.1292 | 1435657.1292 | 1750248.87 | 0 | -314591.7408 | 1435657.1292 | 1435657.1292 | 0
Cryo1.04.04 Cryo Refrigerator system |  | 0 | 0 | 0 | 0 | 0 | 1435657.1292 | 1435657.1292 | 1750248.87 | 0 | -314591.7408 | 1435657.1292 | 1435657.1292 | 0
Cryo1.04.05 Cryo Compressor System |  | 0 | 0 | 0 | 0 | 0 | 426592.2083 | 426592.2083 | 417385.79 | 0 | 9206.4183 | 426592.2083 | 426592.2083 | 0
Cryo1.04.05 Cryo Compressor System |  | 0 | 0 | 0 | 0 | 0 | 426592.2083 | 426592.2083 | 417385.79 | 0 | 9206.4183 | 426592.2083 | 426592.2083 | 0
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | 0 | 0 | 0 | 737933.9081 | 737933.9081 | 577324.94 | 0 | 160608.9681 | 737933.9081 | 737933.9081 | 0
Cryo1.04.06 Cryo Interconnect Piping |  | 0 | 0 | 0 | 0 | 0 | 737933.9081 | 737933.9081 | 577324.94 | 0 | 160608.9681 | 737933.9081 | 737933.9081 | 0
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 0 | 0 | 0 | 166153.655 | 166153.655 | 270852.47 | 0 | -104698.815 | 166153.655 | 166153.655 | 0
Cryo1.04.07 Cryo Interconnect Electrical & Controls |  | 0 | 0 | 0 | 0 | 0 | 166153.655 | 166153.655 | 270852.47 | 0 | -104698.815 | 166153.655 | 166153.655 | 0
Cryo1.04.08 Cryogenic Fluids |  | 23077.4136 | 12328.8809 | 0 | -10748.5327 | 12328.8809 | 261857.9261 | 181850.9937 | 257908.11 | -80006.9324 | -76057.1163 | 261857.9261 | 261857.9261 | 0
Cryo1.04.08 Cryogenic Fluids |  | 23077.4136 | 12328.8809 | 0 | -10748.5327 | 12328.8809 | 261857.9261 | 181850.9937 | 257908.11 | -80006.9324 | -76057.1163 | 261857.9261 | 261857.9261 | 0
Cryo1.05 Experiment interfaces |  | 50388.9395 | 68712.1901 | 35551.26 | 18323.2506 | 33160.9301 | 280891.9903 | 246535.8951 | 150941.04 | -34356.0952 | 95594.8551 | 1154614.0299 | 1154614.0299 | 0
Cryo1.05.01 Mu2e Interface Connection |  | 50388.9395 | 68712.1901 | 35551.26 | 18323.2506 | 33160.9301 | 253693.0663 | 219336.9711 | 125774.64 | -34356.0952 | 93562.3311 | 1127415.1059 | 1127415.1059 | 0
Cryo1.05.01 Mu2e Interface Connection |  | 50388.9395 | 68712.1901 | 35551.26 | 18323.2506 | 33160.9301 | 253693.0663 | 219336.9711 | 125774.64 | -34356.0952 | 93562.3311 | 1127415.1059 | 1127415.1059 | 0
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 27198.924 | 0
Cryo1.05.02 g-2 interface connection |  | 0 | 0 | 0 | 0 | 0 | 27198.924 | 27198.924 | 25166.4 | 0 | 2032.524 | 27198.924 | 27198.924 | 0
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125592.62 | 0 | 29718.7974 | 155311.4174 | 155311.4174 | 0
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125592.62 | 0 | 29718.7974 | 155311.4174 | 155311.4174 | 0
Cryo1.06 Cryo Safety Documents |  | 0 | 0 | 0 | 0 | 0 | 155311.4174 | 155311.4174 | 125592.62 | 0 | 29718.7974 | 155311.4174 | 155311.4174 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.55 | 0 | 65182.5707 | 134950.8402 | 134950.8402 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.55 | 0 | 65182.5707 | 134950.8402 | 134950.8402 | 0
Cryo1.07 Testing/Checkout |  | 0 | 0 | 0 | 0 | 0 | 65416.1207 | 65416.1207 | 233.55 | 0 | 65182.5707 | 134950.8402 | 134950.8402 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55481.53 | 0 | 58989.3038 | 114470.8338 | 114470.8338 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55481.53 | 0 | 58989.3038 | 114470.8338 | 114470.8338 | 0
Cryo1.08 Cryo g-2 Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 114470.8338 | 114470.8338 | 55481.53 | 0 | 58989.3038 | 114470.8338 | 114470.8338 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97719.3744 | 97719.3744 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97719.3744 | 97719.3744 | 0
Cryo1.09 Cryo Mu2e Acceptance Tests |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97719.3744 | 97719.3744 | 0
Cryo1.10 Cryo Distribution Box (CDB) |  | 46584.183 | 63607.8904 | 45578.37 | 17023.7074 | 18029.5204 | 146313.0613 | 164893.0171 | 147786.78 | 18579.9558 | 17106.2371 | 2185375.3305 | 2185375.3305 | 0
Cryo1.10 Cryo Distribution Box (CDB) |  | 46584.183 | 63607.8904 | 45578.37 | 17023.7074 | 18029.5204 | 146313.0613 | 164893.0171 | 147786.78 | 18579.9558 | 17106.2371 | 2185375.3305 | 2185375.3305 | 0
Cryo1.10 Cryo Distribution Box (CDB) |  | 46584.183 | 63607.8904 | 45578.37 | 17023.7074 | 18029.5204 | 146313.0613 | 164893.0171 | 147786.78 | 18579.9558 | 17106.2371 | 2185375.3305 | 2185375.3305 | 0
a. SUBTOTAL |  | 134076.7428 | 158675.1681 | 89736.27 | 24598.4253 | 68938.8981 | 5013044.3817 | 4917261.3099 | 4841208.28 | -95783.0718 | 76053.0299 | 8455142.6771 | 8389005 | 66137.6771
b. MANAGEMENT RESERVE | [11 empty] | 1090209.33
c. TOTAL |  | 134076.7428 | 158675.1681 | 89736.27 | 24598.4253 | 68938.8981 | 5013044.3817 | 4917261.3099 | 4841208.28 | -95783.0718 | 76053.0299 | 9545352.0071

## Template
<Header>{Report} | [7 empty] | {CostProject.Classification}
<Header>{Report} | CLASSIFICATION (When Filled In)
<Header>{Report} |  |  |  |  | CONTRACT PERFORMANCE REPORT | [13 empty] | FORM APPROVED
<Header>{Report} |  |  |  |  | FORMAT 1 - WORK BREAKDOWN STRUCTURE | [11 empty] | DOLLARS IN | {ReportSetting.ScaleCaption} | OMB No. 0704-0188
<Header>{Report} | 1. CONTRACTOR |  |  |  | 2. CONTRACT |  |  |  |  | 3. PROGRAM | [7 empty] | 4. REPORT PERIOD
<Header>{Report} | a. NAME |  |  |  | a. NAME |  |  |  |  | a. NAME | [7 empty] | a. FROM (YYYYMMDD)
<Header>{Report} | {CostProject.ContractorName} |  |  |  | {CostProject.ContractName} |  |  |  |  | {CostProject.Description}
<Header>{Report} | b. LOCATION (Address and ZIP Code) |  |  |  | b. NUMBER |  |  |  |  | b. PHASE | [7 empty] | {CostProject.PeriodStartDate}{NoCellFormat}
<Header>{Report} | {CostProject.ContractorLocation} |  |  |  | {CostProject.ContractNumber} |  |  |  |  | {CostProject.ContractPhase} | [7 empty] | b. TO (YYYYMMDD)
<Header>{Report} |  |  |  |  | c. TYPE |  |  | d. SHARE RATIO |  | c. EVMS ACCEPTANCE
<Header>{Report} |  |  |  |  | {CostProject.ContractType} |  |  | {CostProject.ShareRate} |  | {=if(CostProject.EvmsAcceptance.Id=0,"X"," ")} | NO | {=if(CostProject.EvmsAcceptance.Id=1,"X"," ")} | YES | (YYYYMMDD) | {=IF(OR(CostProject.EvmsAcceptance.Id=0,CostProject.EvmsAcceptance.Id=1), IF(CostProject.EvmsAcceptanceDate=0, " ", CostProject.EvmsAcceptanceDate), IF(CostProject.EvmsAcceptance.Id=2, "N/A"," "))}{NoCellFormat} |  |  | {CostProject.StatusDate}{NoCellFormat}
<Header>{Report} | 5. CONTRACT DATA
<Header>{Report} | a. QUANTITY | b. NEGOTIATED | c. ESTIMATED COST OF |  | d. TARGET PROFIT/FEE |  | e. TARGET PRICE |  | f. ESTIMATED PRICE |  |  | g. CONTRACT CEILING |  |  | h. ESTIMATED CONTRACT CEILING |  |  | i. DATE OF OTB/OTS (YYYYMMDD)
<Header>{Report} |  | COST | AUTHORIZED UNPRICED WORK
<Header>{Report} | {CostProject.Quantity} | {CostProject.Ctc} | {CostProject.Auw} |  | {=CostProject.Ctc*(CostProject.FeePct/100)} |  | {=CostProject.Fee+CostProject.Ctc} |  | {=CostProject.Lre+(CostProject.Cbb*(CostProject.FeePct/100))} |  |  | {CostProject.Ceiling} |  |  | {CostProject.EstCeiling} |  |  | {CostProject.OtbDate}{NoCellFormat}
<Header>{Report} | 6. ESTIMATED COST AT COMPLETION | [7 empty] | 7. AUTHORIZED CONTRACTOR REPRESENTATIVE
<Header>{Report} |  |  | MANAGEMENT ESTIMATE |  | CONTRACT BUDGET |  | VARIANCE |  | a. NAME | (Last, First, Middle Initial) |  |  |  |  | b. TITLE
<Header>{Report} |  |  | AT COMPLETION |  | BASE
<Header>{Report} |  |  | (1) |  | (2) |  | (3) |  | {CostProject.ContractRepName} | [5 empty] | {CostProject.ContractRepTitle}
<Header>{Report} | a. BEST CASE |  | {CostProject.EacBestCase} | [5 empty] | c. SIGNATURE | [8 empty] | d. DATE SIGNED | (YYYYMMDD)
<Header>{Report} | b. WORST CASE |  | {CostProject.EacWorstCase}
<Header>{Report} | c. MOST LIKELY |  | {CostProject.Lre} |  | {CostProject.Cbb} |  | {=Cell[R,C-2]-Cell[R,C-4]}
<Header>{Report} | 8. PERFORMANCE DATA
<Header>{Report} | {CriteriaN.Title}{Down}{Replace} |  | CURRENT PERIOD |  |  |  |  | CUMULATIVE TO DATE | [6 empty] | REPROGRAMMING ADJUSTMENTS |  |  | AT COMPLETION
<Header>{Report} |  |  | BUDGETED COST |  | ACTUAL | VARIANCE |  | BUDGETED COST |  | ACTUAL |  | VARIANCE | [5 empty] | BUDGETED | ESTIMATED | VARIANCE
<Header>{Report} |  |  | WORK | WORK | COST WORK |  |  | WORK | WORK | COST WORK |  |  |  |  | COST | SCHEDULE
<Header>{Report} | ITEM |  | SCHEDULED | PERFORMED | PERFORMED | SCHEDULE | COST | SCHEDULED | PERFORMED | PERFORMED |  | SCHEDULE |  | COST | VARIANCE | VARIANCE | BUDGET
<Header>{Report} | (1) |  | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |  | (10) |  | (11) | (12a) | (12b) | (13) | (14) | (15) | (16)
<Header>{CriteriaN} | {=CONCATENATE(REPT(" ",CriteriaN.Level-1),"CriteriaN.Id"," CriteriaN.Description")} |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeC} | b. COST OF MONEY |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SortCodeG} | c. GENERAL AND ADMINISTRATIVE |  | {CostSet1.Period2.Value} | {CostSet2.Period2.Value} | {CostSet3.Period2.Value} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value)} | {=(CostSet2.Period1.Value+CostSet2.Period2.Value)} | {=(CostSet3.Period1.Value+CostSet3.Period2.Value)} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=(CostSet5.Period1.Value+CostSet5.Period2.Value+CostSet5.Period3.Value)} | {=(CostSet6.Period1.Value+CostSet6.Period2.Value+CostSet6.Period3.Value)} | {=(CostSet7.Period1.Value+CostSet7.Period2.Value+CostSet7.Period3.Value)} | {=(CostSet1.Period1.Value+CostSet1.Period2.Value+CostSet1.Period3.Value)} | {=(CostSet4.Period1.Value+CostSet4.Period2.Value+CostSet4.Period3.Value)} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | d. UNDISTRIBUTED BUDGET | [16 empty] | {CostProject.Ub} | {CostProject.EstUb} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report}{SubTotal} | e. SUBTOTAL |  | {Column.Total} | {Column.Total} | {Column.Total} | {=Cell[R,C-2] - Cell[R, C-3]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R,C-3] - Cell[R, C-2]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {Column.Total} | {Column.Total} | {Column.Total} |  | {=Cell[R,C-3] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {Column.Total} | {Column.Total} | {Column.Total} | {=Column.Total+Cell[R-1,C]} | {=Column.Total+Cell[R-1,C]} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} | f. MANAGEMENT RESERVE | [16 empty] | {CostProject.Mr}
<Footer>{Report} | g. TOTAL |  | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],S,P,S48)} | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-3],C,P,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} |  | {=Cell[R-2,C]}{HIGHLIGHT(Cell[R,C-4],S,C,S48)} |  | {=Cell[R,C-5] - Cell[R, C-4]}{HIGHLIGHT(Cell[R,C-5],C,C,S48)} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C]} | {=Cell[R-2,C] + Cell[R-1,C]}
<Footer>{Report} | 9. RECONCILIATION TO CONTRACT BUDGET BASELINE
<Footer>{Report} | a. VARIANCE ADJUSTMENT | [10 empty] | {=Cell[R-2,C+4]} |  | {=Cell[R-2,C+1]}
<Footer>{Report} | b. TOTAL CONTRACT VARIANCE | [10 empty] | {=Cell[R-3,C]+Cell[R-1,C]} |  | {=Cell[R-3,C]+Cell[R-1,C]} |  |  |  | {CostProject.Cbb} | {CostProject.Lre} | {=Cell[R,C-2] - Cell[R, C-1]}{HIGHLIGHT(Cell[R,C-2],C,A,S48)}
<Footer>{Report} |  |  | (7): {CostProject.Classification}
<Footer>{Report} | CLASSIFICATION (When Filled In)
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Report Options
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Criteria: {ReportOptions.Criteria}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Calendar: {ReportOptions.CalendarSet}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Cost Sets: {ReportOptions.CostSets}
<Footer>{Report}{PRINTIF(DisplayReportOptions,True)} | Filter: {ReportOptions.Filter}
[18 empty] | $ | % | Both
[18 empty] | Dollar | Percent | Both

## Calendar
Date | 18 Label | Hours
2015-05-31 | PREVIOUS | 13408
2015-06-30 | TODATE | 176
2024-09-30 | ATCOMPLETE | 18616

## Data
Control Account.WBS (1) | Control Account.WBS (2) | Control Account.WBS (3) | Control Account.WBS (4) | Summary Code | Cost Set | Date | Value | Currency
|  |  |  | O | Budget | 2015-05-31 | 1659992.6321 | TRUE
|  |  |  | O | Budget | 2015-06-30 | 52438.2269 | TRUE
|  |  |  | O | Budget | 2024-09-30 | 917650.377 | TRUE
|  |  |  | O | Earned | 2015-05-31 | 1624418.6296 | TRUE
|  |  |  | O | Earned | 2015-06-30 | 65832.9533 | TRUE
|  |  |  | O | Actuals | 2015-05-31 | 1676591.1 | TRUE
|  |  |  | O | Actuals | 2015-06-30 | 40832.86 | TRUE
|  |  |  | O | EAC | 2015-05-31 | 1676591.1 | TRUE
|  |  |  | O | EAC | 2015-06-30 | 40832.86 | TRUE
|  |  |  | O | EAC | 2024-09-30 | 942702.701 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Budget | 2015-05-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Earned | 2015-05-31 | 51346.4223 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | Actuals | 2015-05-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.01 |  | EAC | 2015-05-31 | 43241.15 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Budget | 2015-05-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Earned | 2015-05-31 | 133151.102 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | Actuals | 2015-05-31 | 75118.37 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.02 |  | EAC | 2015-05-31 | 75118.37 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Budget | 2015-05-31 | 22482.7684 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Budget | 2015-06-30 | 2713.1598 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Budget | 2024-09-30 | 7152.8759 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Earned | 2015-05-31 | 22482.7684 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Earned | 2015-06-30 | 2713.1598 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Actuals | 2015-05-31 | 30262.8 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | Actuals | 2015-06-30 | 1853.02 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | EAC | 2015-05-31 | 30262.8 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | EAC | 2015-06-30 | 1853.02 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.03 |  | EAC | 2024-09-30 | 7152.8759 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | Budget | 2024-09-30 | 164602.2943 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.04 |  | EAC | 2024-09-30 | 164602.2944 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | Budget | 2024-09-30 | 160479.4071 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.05 |  | EAC | 2024-09-30 | 160479.4071 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Budget | 2015-05-31 | 32910.6817 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Budget | 2015-06-30 | 11313.0469 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Budget | 2024-09-30 | 29825.3054 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Earned | 2015-05-31 | 32910.6817 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Earned | 2015-06-30 | 11313.0469 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Actuals | 2015-05-31 | 7745.21 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | Actuals | 2015-06-30 | 6753.62 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | EAC | 2015-05-31 | 7745.21 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | EAC | 2015-06-30 | 6753.62 | TRUE
Cryo1 | Cryo1.02 | Cryo1.02.01 | Cryo1.02.01.07 |  | EAC | 2024-09-30 | 29825.3054 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Budget | 2015-05-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Earned | 2015-05-31 | 269176.6581 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | Actuals | 2015-05-31 | 342333.09 | TRUE
Cryo1 | Cryo1.03 | Cryo1.03 | Cryo1.03 |  | EAC | 2015-05-31 | 342333.09 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Budget | 2015-05-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Earned | 2015-05-31 | 413528.8731 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | Actuals | 2015-05-31 | 331519.52 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.01 | Cryo1.04.01 |  | EAC | 2015-05-31 | 331519.52 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Budget | 2015-05-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Earned | 2015-05-31 | 236065.7847 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | Actuals | 2015-05-31 | 207268.27 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.02 | Cryo1.04.02 |  | EAC | 2015-05-31 | 207268.27 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Budget | 2015-05-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Earned | 2015-05-31 | 49757.6345 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | Actuals | 2015-05-31 | 41357.53 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.03 | Cryo1.04.03 |  | EAC | 2015-05-31 | 41357.53 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Budget | 2015-05-31 | 1435657.1292 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Earned | 2015-05-31 | 1435657.1292 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | Actuals | 2015-05-31 | 1750248.87 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.04 | Cryo1.04.04 |  | EAC | 2015-05-31 | 1750248.87 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Budget | 2015-05-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Earned | 2015-05-31 | 426592.2083 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | Actuals | 2015-05-31 | 417385.79 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.05 | Cryo1.04.05 |  | EAC | 2015-05-31 | 417385.79 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Budget | 2015-05-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Earned | 2015-05-31 | 737933.9081 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | Actuals | 2015-05-31 | 577324.94 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.06 | Cryo1.04.06 |  | EAC | 2015-05-31 | 577324.94 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Budget | 2015-05-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Earned | 2015-05-31 | 166153.655 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | Actuals | 2015-05-31 | 270852.47 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.07 | Cryo1.04.07 |  | EAC | 2015-05-31 | 270852.47 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Budget | 2015-05-31 | 238780.5125 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Budget | 2015-06-30 | 23077.4136 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Earned | 2015-05-31 | 169522.1128 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Earned | 2015-06-30 | 12328.8809 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | Actuals | 2015-05-31 | 257908.11 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | EAC | 2015-05-31 | 257908.11 | TRUE
Cryo1 | Cryo1.04 | Cryo1.04.08 | Cryo1.04.08 |  | EAC | 2024-09-30 | 80386.2519 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2015-05-31 | 203304.1268 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2015-06-30 | 50388.9395 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Budget | 2024-09-30 | 873722.0396 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Earned | 2015-05-31 | 150624.781 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Earned | 2015-06-30 | 68712.1901 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Actuals | 2015-05-31 | 90223.38 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | Actuals | 2015-06-30 | 35551.26 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2015-05-31 | 90223.38 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2015-06-30 | 35551.26 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.01 | Cryo1.05.01 |  | EAC | 2024-09-30 | 914207.7601 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Budget | 2015-05-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Earned | 2015-05-31 | 27198.924 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | Actuals | 2015-05-31 | 25166.4 | TRUE
Cryo1 | Cryo1.05 | Cryo1.05.02 | Cryo1.05.02 |  | EAC | 2015-05-31 | 25166.4 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Budget | 2015-05-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Earned | 2015-05-31 | 155311.4174 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | Actuals | 2015-05-31 | 125592.62 | TRUE
Cryo1 | Cryo1.06 | Cryo1.06 | Cryo1.06 |  | EAC | 2015-05-31 | 125592.62 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2015-05-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Budget | 2024-09-30 | 69534.7195 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Earned | 2015-05-31 | 65416.1207 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | Actuals | 2015-05-31 | 233.55 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | EAC | 2015-05-31 | 233.55 | TRUE
Cryo1 | Cryo1.07 | Cryo1.07 | Cryo1.07 |  | EAC | 2024-09-30 | 69534.7195 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Budget | 2015-05-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Earned | 2015-05-31 | 114470.8338 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | Actuals | 2015-05-31 | 55481.53 | TRUE
Cryo1 | Cryo1.08 | Cryo1.08 | Cryo1.08 |  | EAC | 2015-05-31 | 55481.53 | TRUE
Cryo1 | Cryo1.09 | Cryo1.09 | Cryo1.09 |  | Budget | 2024-09-30 | 97719.3744 | TRUE
Cryo1 | Cryo1.09 | Cryo1.09 | Cryo1.09 |  | EAC | 2024-09-30 | 97719.3744 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2015-05-31 | 99728.8783 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2015-06-30 | 46584.183 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Budget | 2024-09-30 | 2039062.2692 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Earned | 2015-05-31 | 101285.1267 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Earned | 2015-06-30 | 63607.8904 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Actuals | 2015-05-31 | 102208.41 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | Actuals | 2015-06-30 | 45578.37 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2015-05-31 | 102208.41 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2015-06-30 | 45578.37 | TRUE
Cryo1 | Cryo1.10 | Cryo1.10 | Cryo1.10 |  | EAC | 2024-09-30 | 2020414.6778 | TRUE