## Sheet1
Task Code | CTC | WP | Name | BCWS | BCWP | Schedule Variance
Cryo AIP |  |  |  | 5013044 | 4917261 | -95783
A1301.04.08 Cryogenic Fluids | A1301.04.08 |  | Cryogenic Fluids | 261857.93 | 181850.99 | -80006.94
2934 Receive 3rd Helium Delivery | A1301.04.08 | 2934 | Receive 3rd Helium Delivery | 61644.4 | 58562.18 | -3082.22
2935 Certify 2 Trailers/Connect 2 Trailers & Pump/Backfill | A1301.04.08 | 2935 | Certify 2 Trailers/Connect 2 Trailers & Pump/Backfill | 76924.71 | 0 | -76924.71
A1301.05.01 Mu2e Interface Connection | A1301.05.01 |  | Mu2e Interface Connection | 253693.07 | 219336.97 | -34356.1
2988 Mu2e Interface - Transfer Line System Design | A1301.05.01 | 2988 | Mu2e Interface - Transfer Line System Design | 148876.41 | 114520.32 | -34356.09
A1301.10 Cryo Distribution Box (CDB) | A1301.10 |  | Cryo Distribution Box (CDB) | 146313.06 | 164893.02 | 18579.96
2945 Complete CDB Prelim. Eng. Design | A1301.10 | 2945 | Complete CDB Prelim. Eng. Design | 98525.78 | 89403.02 | -9122.76
2949 Complete Final Specification | A1301.10 | 2949 | Complete Final Specification | 0 | 29888.23 | 29888.23
2969 Specify Helium Dewar | A1301.10 | 2969 | Specify Helium Dewar | 2914.02 | 728.5 | -2185.52